## Slide 1
CLIENT ISSUE · CONTRACT BASELINE
Emirates Mumbai
Emirates Airlines · Commerz III, Oberoi Realty, Goregaon East, Mumbai
Project Programme
DnB Planning Engine v1.0.0

## Slide 2
Programme at a glance
COMMENCEMENT
2025-06-23
CONTRACT COMPLETION
2026-02-23
per agreement
AREA
33,000 sft
CONTRACT VALUE
INR 23,95,00,000
excl. taxes
Phase | Start | Completion
Construction | 2025-06-23 | 2026-02-22

## Slide 3
Payment milestones
Stage | Target date | % | Value | Scope covered
RA1 | 2025-06-23 | 0% | INR 0 | Mobilisation, kick-off and PO release
RA2 | 2025-08-22 | 15% | INR 3,59,25,000 | Design freeze, liaisoning approvals (BMC, Fire NOC), site mobilisation
RA3 | 2025-10-11 | 20% | INR 4,79,00,000 | Civil, dry-wall partitions, MEP first fix, raceways and conduiting
RA4 | 2025-11-30 | 25% | INR 5,98,75,000 | Ceilings, flooring, second fix MEP, glass partitions
RA5 | 2026-01-14 | 25% | INR 5,98,75,000 | Painting, wall finishes, modular furniture, commissioning
RA6 | 2026-02-23 | 15% | INR 3,59,25,000 | Snagging, deep cleaning, handover and close-out documents

## Slide 4
What we need from you — client & builder inputs (1/2)
Sr | Area | Description | Responsibility | Required by
1 | Kick Off | Site kick-off meeting and pooja | Client/FS | 2025-06-23
2 | Commercial | Project PO / signed agreement | Client | 2025-06-23
3 | Commercial | Project advance payment | Client | 2025-06-30
4 | Design | Layout approval | Client | 2025-09-16
5 | Design | 3D approvals | Client | 2025-09-30
6 | Design | Material sampling approval | Client/FS | 2025-10-14
7 | Design | MEP drawings approval | Client/PMC | 2025-10-10
8 | Design | Electrical / IT requirement and load confirmation | Client | 2025-10-10
9 | Operation | Builder permissions and mobilisation clearance | FS/Builder | 2025-09-19
10 | Operation | Mathadi clearance | FS | 2025-09-19
11 | Operation | Fire NOC / CFO approval | FS/Builder | 2025-09-29
12 | Operation | BMC / statutory approval | FS/Builder | 2025-09-12

## Slide 5
What we need from you — client & builder inputs (2/2)
Sr | Area | Description | Responsibility | Required by
13 | Operation | Temporary power and water availability | Builder | 2025-10-19
14 | Operation | Lift availability for material movement | Builder | 2025-09-23
15 | Operation | Work hours clarity in building | Builder | 2025-09-23
16 | Operation | Heat load approval / CFM availability | Builder | 2025-10-17
17 | Operation | Wi-Fi and access point locations | Client | 2025-11-11
18 | Operation | Modular vendor closure for site marking | Client | 2025-12-10
19 | Design/Operation | Client-supplied items (IT / AV) delivery | Client | 2025-11-11
20 | Operation | Store space and debris removal area | Builder | 2025-09-23

## Slide 6
Design deliverables — approval dates (1/7)
Category | Deliverable | Criticality | Approval by
GFC | Base Build Layout | Very Critical | 2025-09-25
GFC | Furniture Layout | Very Critical | 2025-12-23
GFC | Furniture Dimensions Layout | High | 2025-12-23
GFC | Partition Layout | Very Critical | 2025-10-09
GFC | Flooring Layout | High | 2025-10-23
GFC | Floor Marking Layout | Medium | 2025-10-23
GFC | Raised Flooring Layout | High | 2025-10-23
GFC | Door Schedule Layout | High | 2025-10-14
GFC | Wall Finishes Layout | High | 2025-11-06
GFC | Modular Layout | Very Critical | 2025-12-23
GFC | RCP Layout | Very Critical | 2025-10-16
GFC | Lighting Layout (with dimensions) | Very Critical | 2025-10-23
GFC | Wallpaper & Graphics | Low | 2025-07-08
GFC | Fire Evacuation Plan | Medium | 2025-07-06

## Slide 7
Design deliverables — approval dates (2/7)
Category | Deliverable | Criticality | Approval by
GFC | 3D Views — Detailed & Client Approval | Very Critical | 2025-10-09
MEP | Electrical DBR | Very Critical | 2025-10-23
MEP | Electrical SLD Layout | Very Critical | 2025-10-23
MEP | Electrical Load Calculation | Very Critical | 2025-10-23
MEP | Power, Data & Switch Board Layout | Very Critical | 2025-10-23
MEP | Raceway Layout | Very Critical | 2025-10-23
MEP | Cable Tray Layout | High | 2025-10-23
MEP | Lighting Looping Layout | High | 2025-10-23
MEP | Panel & DB Position Layout | High | 2025-10-23
MEP | UPS Calculation & Specification | High | 2025-10-23
MEP | HVAC DBR | Very Critical | 2025-10-30
MEP | HVAC Heat Load | Very Critical | 2025-10-30
MEP | HVAC Layout | Very Critical | 2025-10-30
MEP | PHE DBR & Plumbing Layout | High | 2025-10-13

## Slide 8
Design deliverables — approval dates (3/7)
Category | Deliverable | Criticality | Approval by
MEP | Fire Sprinkler Layout | Very Critical | 2025-10-12
MEP | FA / PA System Layout | High | 2025-11-20
MEP | ACS / CCTV / WiFi Layout | High | 2025-11-20
MEP | LV DBR | High | 2025-11-20
SAMPLING | Floor and Dado Tiles — Reception & Lounge | High | 2025-10-23
SAMPLING | Floor and Dado Tiles — Workstations | High | 2025-10-23
SAMPLING | Floor and Dado Tiles — Cabins & Meeting Rooms | High | 2025-10-23
SAMPLING | Floor and Dado Tiles — Boardroom | High | 2025-10-23
SAMPLING | Floor and Dado Tiles — Cafeteria & Pantry | High | 2025-10-23
SAMPLING | Floor and Dado Tiles — Toilets | High | 2025-10-23
SAMPLING | Floor and Dado Tiles — Support & Server | High | 2025-10-23
SAMPLING | Carpentry Laminates & Veneer Shades — Reception & Lounge | High | 2025-10-14
SAMPLING | Carpentry Laminates & Veneer Shades — Workstations | High | 2025-10-14
SAMPLING | Carpentry Laminates & Veneer Shades — Cabins & Meeting Rooms | High | 2025-10-14

## Slide 9
Design deliverables — approval dates (4/7)
Category | Deliverable | Criticality | Approval by
SAMPLING | Carpentry Laminates & Veneer Shades — Boardroom | High | 2025-10-14
SAMPLING | Carpentry Laminates & Veneer Shades — Cafeteria & Pantry | High | 2025-10-14
SAMPLING | Carpentry Laminates & Veneer Shades — Toilets | High | 2025-10-14
SAMPLING | Carpentry Laminates & Veneer Shades — Support & Server | High | 2025-10-14
SAMPLING | Paint Shades — Reception & Lounge | Medium | 2025-11-06
SAMPLING | Paint Shades — Workstations | Medium | 2025-11-06
SAMPLING | Paint Shades — Cabins & Meeting Rooms | Medium | 2025-11-06
SAMPLING | Paint Shades — Boardroom | Medium | 2025-11-06
SAMPLING | Paint Shades — Cafeteria & Pantry | Medium | 2025-11-06
SAMPLING | Paint Shades — Toilets | Medium | 2025-11-06
SAMPLING | Paint Shades — Support & Server | Medium | 2025-11-06
SAMPLING | Carpet / SPC Flooring — Reception & Lounge | High | 2025-10-23
SAMPLING | Carpet / SPC Flooring — Workstations | High | 2025-10-23
SAMPLING | Carpet / SPC Flooring — Cabins & Meeting Rooms | High | 2025-10-23

## Slide 10
Design deliverables — approval dates (5/7)
Category | Deliverable | Criticality | Approval by
SAMPLING | Carpet / SPC Flooring — Boardroom | High | 2025-10-23
SAMPLING | Carpet / SPC Flooring — Cafeteria & Pantry | High | 2025-10-23
SAMPLING | Carpet / SPC Flooring — Toilets | High | 2025-10-23
SAMPLING | Carpet / SPC Flooring — Support & Server | High | 2025-10-23
SAMPLING | Demountable Glass Partition | Very Critical | 2026-01-06
SAMPLING | Backpainted Glass | Medium | 2026-01-06
SAMPLING | Grid & Stretch Ceiling — Reception & Lounge | High | 2025-10-16
SAMPLING | Grid & Stretch Ceiling — Workstations | High | 2025-10-16
SAMPLING | Grid & Stretch Ceiling — Cabins & Meeting Rooms | High | 2025-10-16
SAMPLING | Grid & Stretch Ceiling — Boardroom | High | 2025-10-16
SAMPLING | Grid & Stretch Ceiling — Cafeteria & Pantry | High | 2025-10-16
SAMPLING | Grid & Stretch Ceiling — Toilets | High | 2025-10-16
SAMPLING | Grid & Stretch Ceiling — Support & Server | High | 2025-10-16
SAMPLING | Acoustics / Fluted Panel — Reception & Lounge | Medium | 2025-10-16

## Slide 11
Design deliverables — approval dates (6/7)
Category | Deliverable | Criticality | Approval by
SAMPLING | Acoustics / Fluted Panel — Workstations | Medium | 2025-10-16
SAMPLING | Acoustics / Fluted Panel — Cabins & Meeting Rooms | Medium | 2025-10-16
SAMPLING | Acoustics / Fluted Panel — Boardroom | Medium | 2025-10-16
SAMPLING | Acoustics / Fluted Panel — Cafeteria & Pantry | Medium | 2025-10-16
SAMPLING | Acoustics / Fluted Panel — Toilets | Medium | 2025-10-16
SAMPLING | Acoustics / Fluted Panel — Support & Server | Medium | 2025-10-16
SAMPLING | Switch Sockets | Medium | 2025-10-23
SAMPLING | Decorative Lights | High | 2025-10-23
SAMPLING | Sanitary Fixtures | Medium | 2025-10-13
SAMPLING | Chairs & Loose Furniture | High | 2025-12-23
SAMPLING | Blinds | Medium | 2025-07-08
SAMPLING | Skirting & T Profile | Low | 2025-07-05
GFC | TD — Civil & Interior | Very Critical | 2025-10-09
GFC | TD — Soft Cost (furniture & furnishing) | Very Critical | 2025-12-23

## Slide 12
Design deliverables — approval dates (7/7)
Category | Deliverable | Criticality | Approval by
GFC | Elevation — Reception & Lounge | High | 2025-10-09
GFC | Elevation — Workstations | High | 2025-10-09
GFC | Elevation — Cabins & Meeting Rooms | High | 2025-10-09
GFC | Elevation — Boardroom | High | 2025-10-09
GFC | Elevation — Cafeteria & Pantry | High | 2025-10-09
GFC | Elevation — Toilets | High | 2025-10-09
GFC | Elevation — Support & Server | High | 2025-10-09

## Slide 13
Procurement — delivery dates required on site
Package | Criticality | Delivery required
Civil & Interior | Medium | 2025-09-24
Soft Cost (furniture & furnishing) | Medium | 2025-12-22
Electrical Works | Medium | 2025-10-22
HVAC | Medium | 2025-10-29
Wet Works (PHE) | Medium | 2025-10-12
Passive Networking | Medium | 2025-11-19
Fire Fighting and Safety | Medium | 2025-10-11
UPS | Medium | —
Surveillance | Medium | —
Miscellaneous | Medium | 2025-07-18

## Slide 14
Billing milestones
RA | Due | % | Status
RA1 | 2025-06-23 | 0% | Delayed
RA2 | 2025-08-22 | 15% | Delayed
RA3 | 2025-10-11 | 20% | Delayed
RA4 | 2025-11-30 | 25% | Delayed
RA5 | 2026-01-14 | 25% | Delayed
RA6 | 2026-02-23 | 15% | Delayed