## Slide 1
INTERNAL — NOT FOR CLIENT ISSUE
SKF, Pune
SKF India (Industrial) Ltd · Units 801–802, 8th Floor, Millennium Tower 3, Wakad, Pune
Execution Plan · confidence 84% · norms norms-v1
DnB Planning Engine v1.0.0

## Slide 2
Position
INTERNAL TARGET
2026-08-14
68 wd (CPM)
CONTRACT FINISH
2026-08-22
BUFFER
8d
invariant holds
CRITICAL
9 / 69
zero float
PEAK MANPOWER
124
2026-07-25
MARGIN
27.5%
6 RA milestones
Confidence basis: 7/9 inputs provided; 3/18 packages unmapped; buffer 8d.
Phase | Start | End | On critical path
Site Prep | 2026-06-08 | 2026-06-15 | YES
Civil Work | 2026-06-21 | 2026-07-25 | YES
Partition & Paneling | 2026-06-23 | 2026-07-21 | —
Electrical & Networking | 2026-06-25 | 2026-08-05 | YES
False Ceiling | 2026-07-06 | 2026-07-19 | —
HVAC | 2026-07-04 | 2026-07-30 | —
Sprinkler Work | 2026-06-27 | 2026-08-07 | —
LV Systems | 2026-07-11 | 2026-07-30 | —
Doors & Carpentry | 2026-07-06 | 2026-07-31 | —
Finishing | 2026-07-22 | 2026-08-12 | —
Modular Placement | 2026-07-25 | 2026-08-11 | —
Handover | 2026-08-05 | 2026-08-14 | YES

## Slide 3
Critical path — 9 activities, zero float
# | Activity | Trade | Dur | Start | Finish
t1 | Site Marking & Dilapidation Report | general | 6d | 2026-06-08 | 2026-06-13
t3 | Furniture Marking | general | 4d | 2026-06-12 | 2026-06-15
t4 | Blockwork, AAC Blocks & Plastering | civil | 22d | 2026-06-21 | 2026-07-12
t21 | Raceway Trunking & Installation | electrical | 20d | 2026-06-25 | 2026-07-14
t22 | GI Conduiting & Switch/Point Back-boxes | electrical | 21d | 2026-07-09 | 2026-07-29
t23 | Point Wiring, Circuits, Mains & DB's | electrical | 21d | 2026-07-16 | 2026-08-05
t24 | LT Panel Labeling | electrical | 11d | 2026-07-21 | 2026-07-31
t25 | Panel Installation — Testing & Commissioning | electrical | 3d | 2026-07-30 | 2026-08-01
t69 | Snag List & Handover | general | 10d | 2026-08-05 | 2026-08-14

## Slide 4
Full activity schedule with float (1/5)
# | Activity | Phase | Dur | Start | Finish | Float
t1 | Site Marking & Dilapidation Report | Site Prep | 6d | 2026-06-08 | 2026-06-13 | 0d
t2 | Temporary Power | Site Prep | 2d | 2026-06-10 | 2026-06-11 | 64d
t3 | Furniture Marking | Site Prep | 4d | 2026-06-12 | 2026-06-15 | 0d
t4 | Blockwork, AAC Blocks & Plastering | Civil Work | 22d | 2026-06-21 | 2026-07-12 | 0d
t11 | 100mm Partition Framing | Partition & Paneling | 18d | 2026-06-23 | 2026-07-10 | 3d
t12 | Gypsum Panelling | Partition & Paneling | 10d | 2026-07-02 | 2026-07-11 | 3d
t13 | Gypsum Wall Punning | Partition & Paneling | 8d | 2026-07-03 | 2026-07-10 | 23d
t14 | Column Cladding (Ply/Gypsum) | Partition & Paneling | 12d | 2026-07-03 | 2026-07-14 | 31d
t15 | Glass Partition | Partition & Paneling | 14d | 2026-07-08 | 2026-07-21 | 12d
t20 | GI Cable Trays, Trunking & MS Supports | Electrical & Networking | 21d | 2026-07-02 | 2026-07-22 | 23d
t21 | Raceway Trunking & Installation | Electrical & Networking | 20d | 2026-06-25 | 2026-07-14 | 0d
t16 | Gypsum False Ceiling | False Ceiling | 8d | 2026-07-06 | 2026-07-13 | 24d
t17 | Metal / Fire-rated Ceiling | False Ceiling | 6d | 2026-07-12 | 2026-07-17 | 28d
t18 | Designer Ceiling — Laminate Finish | False Ceiling | 6d | 2026-07-07 | 2026-07-12 | 33d
t19 | Acoustic Baffle Ceiling | False Ceiling | 5d | 2026-07-15 | 2026-07-19 | 26d
t22 | GI Conduiting & Switch/Point Back-boxes | Electrical & Networking | 21d | 2026-07-09 | 2026-07-29 | 0d

## Slide 5
Full activity schedule with float (2/5)
# | Activity | Phase | Dur | Start | Finish | Float
t23 | Point Wiring, Circuits, Mains & DB's | Electrical & Networking | 21d | 2026-07-16 | 2026-08-05 | 0d
t24 | LT Panel Labeling | Electrical & Networking | 11d | 2026-07-21 | 2026-07-31 | 0d
t25 | Panel Installation — Testing & Commissioning | Electrical & Networking | 3d | 2026-07-30 | 2026-08-01 | 0d
t26 | GI Sheet Ducting Fabrication & Installation | HVAC | 18d | 2026-07-04 | 2026-07-21 | 5d
t27 | Duct Light Testing (Pre-insulation) | HVAC | 2d | 2026-07-16 | 2026-07-17 | 5d
t28 | Thermal & Acoustic Insulation | HVAC | 9d | 2026-07-18 | 2026-07-26 | 5d
t29 | Grilles, Diffusers, Fire Dampers & Actuators | HVAC | 9d | 2026-07-21 | 2026-07-29 | 5d
t30 | Battery Room Ventilation | HVAC | 4d | 2026-07-18 | 2026-07-21 | 24d
t31 | Refrigerant Piping & Cable Trays | HVAC | 11d | 2026-07-05 | 2026-07-15 | 5d
t32 | Indoor Units Installation | HVAC | 7d | 2026-07-21 | 2026-07-27 | 5d
t33 | VRV Requirements and ODUs | HVAC | 5d | 2026-07-16 | 2026-07-20 | 12d
t34 | HVAC Testing & Commissioning | HVAC | 3d | 2026-07-28 | 2026-07-30 | 5d
t35 | C-Class Sprinkler Piping (Grooved) | Sprinkler Work | 10d | 2026-06-27 | 2026-07-06 | 7d
t36 | Alarm Valve Assembly & Flow Switch | Sprinkler Work | 10d | 2026-07-29 | 2026-08-07 | 7d
t37 | Pendent/Upright Sprinklers & Flexible Drops | Sprinkler Work | 7d | 2026-07-02 | 2026-07-08 | 24d
t38 | Sprinkler Testing & Commissioning | Sprinkler Work | 3d | 2026-07-18 | 2026-07-20 | 15d

## Slide 6
Full activity schedule with float (3/5)
# | Activity | Phase | Dur | Start | Finish | Float
t39 | Red/Black Armored Cabling (FAS/PA/CCTV) | LV Systems | 15d | 2026-07-11 | 2026-07-25 | 15d
t40 | Detectors, Hooters & PAVA Rack Commissioning | LV Systems | 9d | 2026-07-20 | 2026-07-28 | 17d
t41 | EM Locks, Biometric Readers & CCTV | LV Systems | 9d | 2026-07-18 | 2026-07-26 | 19d
t42 | Emergency Exit Signage | LV Systems | 9d | 2026-07-22 | 2026-07-30 | 15d
t43 | Rodent Repellent System | LV Systems | 7d | 2026-07-22 | 2026-07-28 | 17d
t44 | Water Leak Detection System | LV Systems | 7d | 2026-07-22 | 2026-07-28 | 17d
t45 | Reception Table | Doors & Carpentry | 20d | 2026-07-06 | 2026-07-25 | 20d
t46 | Flush Doors | Doors & Carpentry | 10d | 2026-07-11 | 2026-07-20 | 25d
t47 | Glass Doors | Doors & Carpentry | 6d | 2026-07-08 | 2026-07-13 | 12d
t48 | Back Painted Glass | Doors & Carpentry | 5d | 2026-07-27 | 2026-07-31 | 12d
t5 | Plumbing Internal Piping | Civil Work | 12d | 2026-06-30 | 2026-07-11 | 2d
t56 | Internal Walls (Putty + Paint) | Finishing | 20d | 2026-07-23 | 2026-08-11 | 3d
t49 | Acoustical Panels | Doors & Carpentry | 3d | 2026-07-25 | 2026-07-27 | 18d
t57 | Ceiling Painting | Finishing | 12d | 2026-07-25 | 2026-08-05 | 5d
t51 | Manager/Meeting Room Tables | Modular Placement | 11d | 2026-07-25 | 2026-08-04 | 10d
t52 | Planter Box / OHU / File Storage | Modular Placement | 11d | 2026-07-25 | 2026-08-04 | 10d

## Slide 7
Full activity schedule with float (4/5)
# | Activity | Phase | Dur | Start | Finish | Float
t6 | Waterproofing (Floor + Walls 600mm) | Civil Work | 6d | 2026-07-11 | 2026-07-16 | 2d
t60 | Frosting | Finishing | 3d | 2026-07-30 | 2026-08-01 | 12d
t61 | Vinyl Pasting | Finishing | 3d | 2026-07-30 | 2026-08-01 | 9d
t62 | Wallpaper Pasting | Finishing | 3d | 2026-07-30 | 2026-08-01 | 5d
t63 | Logo Installation | Finishing | 2d | 2026-08-03 | 2026-08-04 | 5d
t64 | Rolling Blinds | Finishing | 2d | 2026-08-04 | 2026-08-05 | 9d
t65 | Planters & Frames | Finishing | 2d | 2026-08-04 | 2026-08-05 | 9d
t66 | Sun Control Film | Finishing | 4d | 2026-07-30 | 2026-08-02 | 12d
t67 | Signage Installation | Finishing | 4d | 2026-08-06 | 2026-08-09 | 5d
t7 | Anti-termite & Pest Control | Civil Work | 6d | 2026-06-22 | 2026-06-27 | 48d
t8 | Self Leveling & Associated Works | Civil Work | 4d | 2026-07-03 | 2026-07-06 | 2d
t9 | Vitrified Tile Works | Civil Work | 4d | 2026-07-20 | 2026-07-23 | 2d
t10 | POP on Flooring (Protection) | Civil Work | 6d | 2026-07-20 | 2026-07-25 | 2d
t53 | Raised Flooring | Modular Placement | 11d | 2026-07-25 | 2026-08-04 | 2d
t50 | Modular Workstations | Modular Placement | 12d | 2026-07-28 | 2026-08-08 | 2d
t54 | WS / Meeting Room Chair Placement | Modular Placement | 10d | 2026-08-02 | 2026-08-11 | 2d

## Slide 8
Full activity schedule with float (5/5)
# | Activity | Phase | Dur | Start | Finish | Float
t55 | Loose Furniture | Modular Placement | 7d | 2026-08-02 | 2026-08-08 | 6d
t58 | Carpet Installation | Finishing | 5d | 2026-07-25 | 2026-07-29 | 9d
t59 | Aluminium Skirting | Finishing | 2d | 2026-07-22 | 2026-07-23 | 22d
t68 | Deep Cleaning | Finishing | 12d | 2026-08-01 | 2026-08-12 | 2d
t69 | Snag List & Handover | Handover | 10d | 2026-08-05 | 2026-08-14 | 0d

## Slide 9
Design tracker — GFC / MEP / Sampling (1/4)
Category | Sub | Drawing | Crit | Issue (INT) | Status (INT) | Approval | Status (client)
GFC | GFC | Base Build Layout | Very Critical | 2026-06-15 | Delayed | 2026-06-20 | Delayed
GFC | GFC | Furniture Layout | Very Critical | 2026-07-17 | Delayed | 2026-07-24 | Delayed
GFC | GFC | Furniture Dimensions Layout | High | 2026-07-19 | Delayed | 2026-07-24 | Delayed
GFC | GFC | Partition Layout | Very Critical | 2026-06-17 | Delayed | 2026-06-22 | Delayed
GFC | GFC | Flooring Layout | High | 2026-07-14 | Delayed | 2026-07-19 | Delayed
GFC | GFC | Floor Marking Layout | Medium | 2026-07-15 | Delayed | 2026-07-19 | Delayed
GFC | GFC | Raised Flooring Layout | High | 2026-07-14 | Delayed | 2026-07-19 | Delayed
GFC | GFC | Door Schedule Layout | High | 2026-06-27 | Delayed | 2026-07-02 | Delayed
GFC | GFC | Wall Finishes Layout | High | 2026-07-17 | Delayed | 2026-07-22 | Delayed
GFC | GFC | Modular Layout | Very Critical | 2026-07-17 | Delayed | 2026-07-24 | Delayed
GFC | GFC | RCP Layout | Very Critical | 2026-06-28 | Delayed | 2026-07-05 | Delayed
GFC | GFC | Lighting Layout (with dimensions) | Very Critical | 2026-06-02 | Delayed | 2026-06-09 | Delayed
GFC | GENERAL | Wallpaper & Graphics | Low | 2026-07-16 | Delayed | 2026-07-21 | Delayed
GFC | GENERAL | Fire Evacuation Plan | Medium | 2026-07-16 | Delayed | 2026-07-21 | Delayed
GFC | 3D | 3D Views — Detailed & Client Approval | Very Critical | 2026-06-12 | Delayed | 2026-06-22 | Delayed

## Slide 10
Design tracker — GFC / MEP / Sampling (2/4)
Category | Sub | Drawing | Crit | Issue (INT) | Status (INT) | Approval | Status (client)
MEP | MEP | Electrical DBR | Very Critical | 2026-06-04 | Delayed | 2026-06-09 | Delayed
MEP | MEP | Electrical SLD Layout | Very Critical | 2026-06-02 | Delayed | 2026-06-09 | Delayed
MEP | MEP | Electrical Load Calculation | Very Critical | 2026-06-02 | Delayed | 2026-06-09 | Delayed
MEP | MEP | Power, Data & Switch Board Layout | Very Critical | 2026-06-02 | Delayed | 2026-06-09 | Delayed
MEP | MEP | Raceway Layout | Very Critical | 2026-06-04 | Delayed | 2026-06-09 | Delayed
MEP | MEP | Cable Tray Layout | High | 2026-06-04 | Delayed | 2026-06-09 | Delayed
MEP | MEP | Lighting Looping Layout | High | 2026-06-04 | Delayed | 2026-06-09 | Delayed
MEP | MEP | Panel & DB Position Layout | High | 2026-06-04 | Delayed | 2026-06-09 | Delayed
MEP | MEP | UPS Calculation & Specification | High | 2026-06-02 | Delayed | 2026-06-09 | Delayed
MEP | MEP | HVAC DBR | Very Critical | 2026-06-28 | Delayed | 2026-07-03 | Delayed
MEP | MEP | HVAC Heat Load | Very Critical | 2026-06-26 | Delayed | 2026-07-03 | Delayed
MEP | MEP | HVAC Layout | Very Critical | 2026-06-26 | Delayed | 2026-07-03 | Delayed
MEP | MEP | PHE DBR & Plumbing Layout | High | 2026-06-24 | Delayed | 2026-06-29 | Delayed
MEP | MEP | Fire Sprinkler Layout | Very Critical | 2026-06-16 | Delayed | 2026-06-26 | Delayed
MEP | MEP | FA / PA System Layout | High | 2026-07-03 | Delayed | 2026-07-10 | Delayed

## Slide 11
Design tracker — GFC / MEP / Sampling (3/4)
Category | Sub | Drawing | Crit | Issue (INT) | Status (INT) | Approval | Status (client)
MEP | MEP | ACS / CCTV / WiFi Layout | High | 2026-07-03 | Delayed | 2026-07-10 | Delayed
MEP | MEP | LV DBR | High | 2026-07-05 | Delayed | 2026-07-10 | Delayed
SAMPLING | Finishes | Floor and Dado Tiles | High | 2026-07-14 | Delayed | 2026-07-19 | Delayed
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades | High | 2026-06-27 | Delayed | 2026-07-02 | Delayed
SAMPLING | Finishes | Paint Shades | Medium | 2026-07-17 | Delayed | 2026-07-22 | Delayed
SAMPLING | Finishes | Carpet / SPC Flooring | High | 2026-07-12 | Delayed | 2026-07-19 | Delayed
SAMPLING | Partitions | Demountable Glass Partition | Very Critical | 2026-06-30 | Delayed | 2026-07-07 | Delayed
SAMPLING | Partitions | Backpainted Glass | Medium | 2026-07-02 | Delayed | 2026-07-07 | Delayed
SAMPLING | Ceiling | Grid & Stretch Ceiling | High | 2026-06-28 | Delayed | 2026-07-05 | Delayed
SAMPLING | Ceiling | Acoustics / Fluted Panel | Medium | 2026-06-30 | Delayed | 2026-07-05 | Delayed
SAMPLING | MEP | Switch Sockets | Medium | 2026-06-04 | Delayed | 2026-06-09 | Delayed
SAMPLING | MEP | Decorative Lights | High | 2026-06-02 | Delayed | 2026-06-09 | Delayed
SAMPLING | MEP | Sanitary Fixtures | Medium | 2026-06-24 | Delayed | 2026-06-29 | Delayed
SAMPLING | Furniture | Chairs & Loose Furniture | High | 2026-07-17 | Delayed | 2026-07-24 | Delayed
SAMPLING | Finishes | Blinds | Medium | 2026-07-16 | Delayed | 2026-07-21 | Delayed

## Slide 12
Design tracker — GFC / MEP / Sampling (4/4)
Category | Sub | Drawing | Crit | Issue (INT) | Status (INT) | Approval | Status (client)
SAMPLING | Finishes | Skirting & T Profile | Low | 2026-07-17 | Delayed | 2026-07-21 | Delayed

## Slide 13
Procurement — order-by and delivery required (1/2)
Category | Sub | Criticality | Order by | Delivery required | Order status | Gated by
Civil Works | Civil consumables | Low | 2026-06-12 | 2026-06-19 | Open | Base Build Layout (client approval 2026-06-20)
Interior Works | Interior boards/ply (Gyproc/ply norms) | Low | 2026-06-09 | 2026-06-21 | Open | Partition Layout (client approval 2026-06-22)
Modular Glass Partitions & Doors | Glass partitions (partition glass norm) | Very Critical | 2026-05-22 | 2026-07-06 | Open | Demountable Glass Partition (client approval 2026-07-07)
Signages | Signages | Medium | 2026-07-11 | 2026-08-01 | Open | —
Graphics & Films | Graphics & films (frosting norm) | Very Critical | 2026-06-08 | 2026-07-28 | Open | —
Blinds | Blinds | High | 2026-07-03 | 2026-08-02 | Open | —
Planters | Planters | Medium | 2026-07-02 | 2026-07-23 | Open | —
Carpet Flooring | Carpet flooring | High | 2026-06-13 | 2026-07-23 | Open | —
Modular Furniture | Modular furniture | Very Critical | 2026-06-08 | 2026-07-23 | Open | Furniture Layout (client approval 2026-07-24)
Loose Furniture & Chairs | Loose furniture & chairs | Very Critical | 2026-06-16 | 2026-07-31 | Open | —
Electrical Works | Electrical switchgear/cabling | High | 2026-05-24 | 2026-06-23 | Open | —
Light Fixtures | Light fixtures | High | — | — | Open | —
UPS | UPS | High | — | — | Open | —
Plumbing (PHE) | Plumbing | Low | 2026-06-14 | 2026-06-28 | Open | PHE DBR & Plumbing Layout (client approval 2026-06-29)

## Slide 14
Procurement — order-by and delivery required (2/2)
Category | Sub | Criticality | Order by | Delivery required | Order status | Gated by
HVAC (Low Side + VAV + VRF) | HVAC (ducting, VRF, VAV) | High | 2026-05-28 | 2026-07-02 | Open | HVAC DBR (client approval 2026-07-03)
Passive Networking | Passive networking | Medium | — | — | Open | —
Fire & Security | Fire & security | High | 2026-05-26 | 2026-06-25 | Open | Fire Sprinkler Layout (client approval 2026-06-26)
GSS / General Site Services | GSS / miscellaneous | Medium | 2026-05-16 | 2026-06-06 | Open | —

## Slide 15
Manpower — levelled contractor gangs
Trade | From | To | Days | Man-days | Core gang | Peak
carpentry | 2026-07-03 | 2026-08-04 | 33 | 448 | 14 | 16
ceiling | 2026-07-06 | 2026-07-19 | 14 | 200 | 14 | 14
civil | 2026-06-21 | 2026-07-25 | 35 | 352 | 11 | 14
cleaning | 2026-08-01 | 2026-08-12 | 12 | 120 | 10 | 10
electrical | 2026-06-10 | 2026-08-05 | 57 | 990 | 14 | 14
finishing | 2026-07-22 | 2026-08-09 | 19 | 150 | 8 | 10
flooring | 2026-07-20 | 2026-08-04 | 16 | 120 | 8 | 10
general | 2026-06-08 | 2026-08-14 | 68 | 80 | 3 | 4
glass | 2026-07-08 | 2026-07-31 | 24 | 125 | 6 | 8
hvac | 2026-07-04 | 2026-07-30 | 27 | 544 | 12 | 12
lv | 2026-07-11 | 2026-07-30 | 20 | 336 | 10 | 10
modular | 2026-07-25 | 2026-08-11 | 18 | 240 | 14 | 14
painting | 2026-07-23 | 2026-08-11 | 20 | 256 | 13 | 16
partition | 2026-06-23 | 2026-07-11 | 19 | 360 | 18 | 18
plumbing | 2026-06-30 | 2026-07-11 | 12 | 48 | 4 | 4
sprinkler | 2026-06-27 | 2026-08-07 | 42 | 150 | 4 | 5

## Slide 16
RA billing milestones — readiness against site progress
MILESTONES
6
CLAUSES TRACKED
27
CONTRACT VALUE
INR 8,21,00,400
RA | Due | % | Amount | Clauses | Status
RA1 | 2026-06-08 | 0% | INR 0 | 1 | Delayed
RA2 | 2026-06-28 | 20% | INR 1,64,20,080 | 7 | Delayed
RA3 | 2026-07-18 | 25% | INR 2,05,25,100 | 6 | Delayed
RA4 | 2026-08-02 | 25% | INR 2,05,25,100 | 5 | WIP
RA5 | 2026-08-17 | 25% | INR 2,05,25,100 | 7 | WIP
RA6 | 2026-08-22 | 5% | INR 41,05,020 | 1 | Not Started

## Slide 17
RA milestone clauses — what must be true before billing (1/2)
RA | Kind | Clause | Planned | Status
RA1 | execution | Project mobilisation (no advance payable) | 2026-06-08 | Delayed
RA2 | execution | Partition marking | 2026-06-13 | Delayed
RA2 | execution | Frameworks | 2026-06-28 | Delayed
RA2 | execution | Skinning | 2026-06-28 | Delayed
RA2 | execution | Civil walls | 2026-08-11 | WIP
RA2 | execution | Conduiting | 2026-07-29 | WIP
RA2 | execution | Raceways | 2026-06-28 | Delayed
RA2 | material | Gypsum/electrical material delivery | 2026-06-28 | Delayed
RA3 | execution | Partition closing | 2026-07-10 | Delayed
RA3 | execution | Wiring | 2026-08-05 | WIP
RA3 | execution | Sprinkler piping | 2026-07-06 | Delayed
RA3 | execution | FAS wiring | 2026-08-05 | WIP
RA3 | material | Duct/cable/ply/tile delivery | 2026-07-18 | Delayed
RA3 | material | Furniture/carpet/glass orders closed | 2026-07-18 | Delayed
RA4 | execution | Paint base coats | 2026-08-11 | WIP
RA4 | execution | Glass channels | 2026-07-21 | Delayed

## Slide 18
RA milestone clauses — what must be true before billing (2/2)
RA | Kind | Clause | Planned | Status
RA4 | execution | Duct installation | 2026-07-14 | Delayed
RA4 | execution | Ceiling framing | 2026-07-10 | Delayed
RA4 | material | Carpet/sanitary/doors/DB delivery | 2026-08-02 | WIP
RA5 | execution | Switches | 2026-08-17 | WIP
RA5 | execution | Sanitary fixtures | 2026-08-17 | WIP
RA5 | execution | Carpentry | 2026-08-17 | WIP
RA5 | execution | Doors | 2026-07-20 | Delayed
RA5 | execution | First paint coat | 2026-08-11 | WIP
RA5 | execution | False ceiling | 2026-07-13 | Delayed
RA5 | execution | Pre-commissioning | 2026-08-01 | WIP
RA6 | execution | Against 12-month DLP bank guarantee at virtual completion/handover | 2026-08-14 | WIP

## Slide 19
Resource plan
Role | Count | Basis
Project Manager | 1 | ceil(26484 sft / 40000) per norms-v1:resourceRoleNorms
Site Engineer (Civil/Interior) | 3 | ceil(26484 sft / 12000) per norms-v1:resourceRoleNorms
MEP Engineer | 2 | ceil(26484 sft / 25000) per norms-v1:resourceRoleNorms
Design Lead | 1 | ceil(26484 sft / 40000) per norms-v1:resourceRoleNorms
Procurement Owner | 1 | ceil(26484 sft / 40000) per norms-v1:resourceRoleNorms
Safety Officer | 1 | ceil(26484 sft / 30000) per norms-v1:resourceRoleNorms
QC / Snag Engineer | 1 | ceil(26484 sft / 30000) per norms-v1:resourceRoleNorms

## Slide 20
To-do list — next 21 days (1/7)
End date | Responsibility | Description | Priority | Status
2026-05-16 | Procurement | Release PO: GSS / General Site Services | MEDIUM | Delayed
2026-05-22 | Procurement | Release PO: Modular Glass Partitions & Doors | HIGH | Delayed
2026-05-24 | Procurement | Release PO: Electrical Works | HIGH | Delayed
2026-05-26 | Procurement | Release PO: Fire & Security | HIGH | Delayed
2026-05-28 | Procurement | Release PO: HVAC (Low Side + VAV + VRF) | HIGH | Delayed
2026-06-02 | Design lead | Issue for approval: Lighting Layout (with dimensions) | HIGH | Delayed
2026-06-02 | MEP design lead | Issue for approval: Electrical SLD Layout | HIGH | Delayed
2026-06-02 | MEP design lead | Issue for approval: Electrical Load Calculation | HIGH | Delayed
2026-06-02 | MEP design lead | Issue for approval: Power, Data & Switch Board Layout | HIGH | Delayed
2026-06-02 | MEP design lead | Issue for approval: UPS Calculation & Specification | HIGH | Delayed
2026-06-02 | Design lead | Issue for approval: Decorative Lights | HIGH | Delayed
2026-06-04 | MEP design lead | Issue for approval: Electrical DBR | HIGH | Delayed
2026-06-04 | MEP design lead | Issue for approval: Raceway Layout | HIGH | Delayed
2026-06-04 | MEP design lead | Issue for approval: Cable Tray Layout | HIGH | Delayed
2026-06-04 | MEP design lead | Issue for approval: Lighting Looping Layout | HIGH | Delayed

## Slide 21
To-do list — next 21 days (2/7)
End date | Responsibility | Description | Priority | Status
2026-06-04 | MEP design lead | Issue for approval: Panel & DB Position Layout | HIGH | Delayed
2026-06-04 | Design lead | Issue for approval: Switch Sockets | MEDIUM | Delayed
2026-06-08 | Procurement | Release PO: Graphics & Films | HIGH | Delayed
2026-06-08 | Procurement | Release PO: Modular Furniture | HIGH | Delayed
2026-06-09 | Procurement | Release PO: Interior Works | MEDIUM | Delayed
2026-06-12 | Procurement | Release PO: Civil Works | MEDIUM | Delayed
2026-06-12 | Design lead | Issue for approval: 3D Views — Detailed & Client Approval | HIGH | Delayed
2026-06-13 | Procurement | Release PO: Carpet Flooring | HIGH | Delayed
2026-06-14 | Procurement | Release PO: Plumbing (PHE) | MEDIUM | Delayed
2026-06-15 | Design lead | Issue for approval: Base Build Layout | HIGH | Delayed
2026-06-16 | Procurement | Release PO: Loose Furniture & Chairs | HIGH | Delayed
2026-06-16 | MEP design lead | Issue for approval: Fire Sprinkler Layout | HIGH | Delayed
2026-06-17 | Design lead | Issue for approval: Partition Layout | HIGH | Delayed
2026-06-24 | MEP design lead | Issue for approval: PHE DBR & Plumbing Layout | HIGH | Delayed
2026-06-24 | Design lead | Issue for approval: Sanitary Fixtures | MEDIUM | Delayed

## Slide 22
To-do list — next 21 days (3/7)
End date | Responsibility | Description | Priority | Status
2026-06-26 | MEP design lead | Issue for approval: HVAC Heat Load | HIGH | Delayed
2026-06-26 | MEP design lead | Issue for approval: HVAC Layout | HIGH | Delayed
2026-06-27 | Design lead | Issue for approval: Door Schedule Layout | HIGH | Delayed
2026-06-27 | Design lead | Issue for approval: Carpentry Laminates & Veneer Shades | HIGH | Delayed
2026-06-28 | Design lead | Issue for approval: RCP Layout | HIGH | Delayed
2026-06-28 | MEP design lead | Issue for approval: HVAC DBR | HIGH | Delayed
2026-06-28 | Design lead | Issue for approval: Grid & Stretch Ceiling | HIGH | Delayed
2026-06-30 | Design lead | Issue for approval: Demountable Glass Partition | HIGH | Delayed
2026-06-30 | Design lead | Issue for approval: Acoustics / Fluted Panel | MEDIUM | Delayed
2026-07-02 | Procurement | Release PO: Planters | MEDIUM | Delayed
2026-07-02 | Design lead | Issue for approval: Backpainted Glass | MEDIUM | Delayed
2026-07-03 | Procurement | Release PO: Blinds | HIGH | Delayed
2026-07-03 | MEP design lead | Issue for approval: FA / PA System Layout | HIGH | Delayed
2026-07-03 | MEP design lead | Issue for approval: ACS / CCTV / WiFi Layout | HIGH | Delayed
2026-07-05 | MEP design lead | Issue for approval: LV DBR | HIGH | Delayed

## Slide 23
To-do list — next 21 days (4/7)
End date | Responsibility | Description | Priority | Status
2026-07-11 | Procurement | Release PO: Signages | MEDIUM | Delayed
2026-07-12 | Design lead | Issue for approval: Carpet / SPC Flooring | HIGH | Delayed
2026-07-14 | Design lead | Issue for approval: Flooring Layout | HIGH | Delayed
2026-07-14 | Design lead | Issue for approval: Raised Flooring Layout | HIGH | Delayed
2026-07-14 | Design lead | Issue for approval: Floor and Dado Tiles | HIGH | Delayed
2026-07-15 | Design lead | Issue for approval: Floor Marking Layout | MEDIUM | Delayed
2026-07-16 | Design lead | Issue for approval: Wallpaper & Graphics | MEDIUM | Delayed
2026-07-16 | Design lead | Issue for approval: Fire Evacuation Plan | MEDIUM | Delayed
2026-07-16 | Design lead | Issue for approval: Blinds | MEDIUM | Delayed
2026-07-17 | Design lead | Issue for approval: Furniture Layout | HIGH | Delayed
2026-07-17 | Design lead | Issue for approval: Wall Finishes Layout | HIGH | Delayed
2026-07-17 | Design lead | Issue for approval: Modular Layout | HIGH | Delayed
2026-07-17 | Design lead | Issue for approval: Paint Shades | MEDIUM | Delayed
2026-07-17 | Design lead | Issue for approval: Chairs & Loose Furniture | HIGH | Delayed
2026-07-17 | Design lead | Issue for approval: Skirting & T Profile | MEDIUM | Delayed

## Slide 24
To-do list — next 21 days (5/7)
End date | Responsibility | Description | Priority | Status
2026-07-19 | Design lead | Issue for approval: Furniture Dimensions Layout | HIGH | Delayed
2026-07-28 | lv lead | In progress: Detectors, Hooters & PAVA Rack Commissioning | MEDIUM | WIP
2026-07-28 | lv lead | In progress: Rodent Repellent System | MEDIUM | WIP
2026-07-28 | lv lead | In progress: Water Leak Detection System | MEDIUM | WIP
2026-07-29 | electrical lead | In progress: GI Conduiting & Switch/Point Back-boxes | HIGH | WIP
2026-07-29 | hvac lead | In progress: Grilles, Diffusers, Fire Dampers & Actuators | MEDIUM | WIP
2026-07-29 | flooring lead | In progress: Carpet Installation | MEDIUM | WIP
2026-07-30 | hvac lead | Start: HVAC Testing & Commissioning | MEDIUM | Not Started
2026-07-30 | lv lead | In progress: Emergency Exit Signage | MEDIUM | WIP
2026-07-31 | electrical lead | In progress: LT Panel Labeling | HIGH | WIP
2026-07-31 | glass lead | In progress: Back Painted Glass | MEDIUM | WIP
2026-08-01 | electrical lead | Start: Panel Installation — Testing & Commissioning | HIGH | Not Started
2026-08-01 | finishing lead | Start: Frosting | MEDIUM | Not Started
2026-08-01 | finishing lead | Start: Vinyl Pasting | MEDIUM | Not Started
2026-08-01 | finishing lead | Start: Wallpaper Pasting | MEDIUM | Not Started

## Slide 25
To-do list — next 21 days (6/7)
End date | Responsibility | Description | Priority | Status
2026-08-02 | finishing lead | Start: Sun Control Film | MEDIUM | Not Started
2026-08-04 | modular lead | In progress: Manager/Meeting Room Tables | MEDIUM | WIP
2026-08-04 | carpentry lead | In progress: Planter Box / OHU / File Storage | MEDIUM | WIP
2026-08-04 | finishing lead | Start: Logo Installation | MEDIUM | Not Started
2026-08-04 | flooring lead | In progress: Raised Flooring | MEDIUM | WIP
2026-08-05 | electrical lead | In progress: Point Wiring, Circuits, Mains & DB's | HIGH | WIP
2026-08-05 | painting lead | In progress: Ceiling Painting | MEDIUM | WIP
2026-08-05 | finishing lead | Start: Rolling Blinds | MEDIUM | Not Started
2026-08-05 | finishing lead | Start: Planters & Frames | MEDIUM | Not Started
2026-08-07 | sprinkler lead | Start: Alarm Valve Assembly & Flow Switch | MEDIUM | Not Started
2026-08-08 | modular lead | Start: Modular Workstations | MEDIUM | Not Started
2026-08-08 | modular lead | Start: Loose Furniture | MEDIUM | Not Started
2026-08-09 | finishing lead | Start: Signage Installation | MEDIUM | Not Started
2026-08-11 | painting lead | In progress: Internal Walls (Putty + Paint) | MEDIUM | WIP
2026-08-11 | modular lead | Start: WS / Meeting Room Chair Placement | MEDIUM | Not Started

## Slide 26
To-do list — next 21 days (7/7)
End date | Responsibility | Description | Priority | Status
2026-08-12 | cleaning lead | Start: Deep Cleaning | MEDIUM | Not Started
2026-08-14 | general lead | Start: Snag List & Handover | HIGH | Not Started

## Slide 27
Client / builder open points (1/2)
Sr | Area | Description | Responsibility | Plan date | Status
1 | Kick Off | Site kick-off meeting and pooja | Client/FS | 2026-06-08 | Delayed
2 | Commercial | Project PO / signed agreement | Client | 2026-06-08 | Delayed
3 | Commercial | Project advance payment | Client | 2026-06-15 | Delayed
4 | Design | Layout approval | Client | 2026-05-29 | Delayed
5 | Design | 3D approvals | Client | 2026-06-13 | Delayed
6 | Design | Material sampling approval | Client/FS | 2026-07-10 | Delayed
7 | Design | MEP drawings approval | Client/PMC | 2026-05-27 | Delayed
8 | Design | Electrical / IT requirement and load confirmation | Client | 2026-05-27 | Delayed
9 | Operation | Builder permissions and mobilisation clearance | FS/Builder | 2026-06-01 | Delayed
10 | Operation | Mathadi clearance | FS | 2026-06-01 | Delayed
11 | Operation | Fire NOC / CFO approval | FS/Builder | 2026-06-13 | Delayed
12 | Operation | BMC / statutory approval | FS/Builder | 2026-06-07 | Delayed
13 | Operation | Temporary power and water availability | Builder | 2026-06-05 | Delayed
14 | Operation | Lift availability for material movement | Builder | 2026-06-18 | Delayed
15 | Operation | Work hours clarity in building | Builder | 2026-06-05 | Delayed

## Slide 28
Client / builder open points (2/2)
Sr | Area | Description | Responsibility | Plan date | Status
16 | Operation | Heat load approval / CFM availability | Builder | 2026-06-20 | Delayed
17 | Operation | Wi-Fi and access point locations | Client | 2026-07-01 | Delayed
18 | Operation | Modular vendor closure for site marking | Client | 2026-07-11 | Delayed
19 | Design/Operation | Client-supplied items (IT / AV) delivery | Client | 2026-07-01 | Delayed
20 | Operation | Store space and debris removal area | Builder | 2026-06-05 | Delayed

## Slide 29
Assumptions, gaps and risks (1/2)
Area | Note | Visibility
manpower | ceiling: 200 man-days across 14 working days needs 15 workers, above the 14 cap. Extend the window, split the front, or raise the cap in Settings. | internal only
manpower | electrical: 990 man-days across 57 working days needs 18 workers, above the 14 cap. Extend the window, split the front, or raise the cap in Settings. | internal only
manpower | hvac: 544 man-days across 27 working days needs 21 workers, above the 12 cap. Extend the window, split the front, or raise the cap in Settings. | internal only
manpower | lv: 336 man-days across 20 working days needs 17 workers, above the 10 cap. Extend the window, split the front, or raise the cap in Settings. | internal only
manpower | partition: 360 man-days across 19 working days needs 19 workers, above the 18 cap. Extend the window, split the front, or raise the cap in Settings. | internal only
procurement | Package "Light Fixtures" has no mapped site activity; order-by date not computed. | internal only
procurement | Package "UPS" has no mapped site activity; order-by date not computed. | internal only
procurement | Package "Passive Networking" has no mapped site activity; order-by date not computed. | internal only

## Slide 30
Assumptions, gaps and risks (2/2)
Area | Note | Visibility
billing | Package HVAC: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only