## Project Schedule
KOHLER PUNE - PROJECT SCHEDULE (DEMOLITION & NEW FIT-OUT)
Phase 1 - Demolition & Site Clearance: 30 Days (Day 1-30) ¦ Phase 2 - New Fit-out Works: 90 Days (Day 31-120) ¦ Total Duration: 120 Days ¦ Critical activities shown in red
Activity No. | Section | Activity Description | Pred. | Dur (Days) | Start Day | Finish Day | Float (Days) | Critical | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18
PHASE 1 - DEMOLITION & SITE CLEARANCE (DAY 1-30 ¦ 30 DAYS)
1.1 | Mobilisation | Site mobilisation & access setup | - | 3 | 2026-07-07 | 2026-07-10 | 0 | Yes
1.2 | Mobilisation | Hoarding, barricading & signages | 1.1 | 2 | 2026-07-11 | 2026-07-13 | 113 | No
1.3 | Mobilisation | HSE setup, permits & site induction | 1.1 | 2 | 2026-07-14 | 2026-07-16 | 115 | No
2.1 | Survey & Make-Safe | Existing condition / dilapidation survey | 1.1 | 2 | 2026-07-14 | 2026-07-16 | 0 | Yes
2.2 | Survey & Make-Safe | Existing services mapping & tagging | 2.1 SS+1 | 2 | 2026-07-14 | 2026-07-16 | 1 | No
1.4 | Mobilisation | Temporary power, water & lighting arrangement | 1.2 | 2 | 2026-07-17 | 2026-07-19 | 113 | No
2.3 | Survey & Make-Safe | Hazardous material check & clearance | 2.1 | 2 | 2026-07-18 | 2026-07-20 | 0 | Yes
2.4 | Survey & Make-Safe | Disconnection & isolation of existing services | 2.2, 2.3 | 3 | 2026-07-21 | 2026-07-24 | 0 | Yes
3.1 | Demolition & Dismantling | Dismantling of false ceiling & services below | 2.4 | 5 | 2026-07-17 | 2026-07-22 | 0 | Yes
3.2 | Demolition & Dismantling | Dismantling of partitions, glazing & doors | 3.1 SS+2 | 5 | 2026-07-23 | 2026-07-28 | 0 | Yes
4.1 | Debris Removal | Debris segregation & stacking | 3.1 SS+2 | 6 | 2026-07-24 | 2026-07-30 | 3 | No
3.3 | Demolition & Dismantling | Removal of existing flooring & floor chipping | 3.2 SS+2 | 4 | 2026-07-31 | 2026-08-04 | 102 | No
3.4 | Demolition & Dismantling | Dismantling of joinery, pantry & fixtures | 3.3 SS+1 | 3 | 2026-07-17 | 2026-07-20 | 102 | No
3.5 | Demolition & Dismantling | Dismantling of existing services (cable, duct, pipe) | 3.1 | 4 | 2026-07-21 | 2026-07-25 | 2 | No
3.6 | Demolition & Dismantling | Civil breaking / hard demolition | 3.2 | 4 | 2026-07-26 | 2026-07-30 | 0 | Yes
4.2 | Debris Removal | Debris removal & disposal | 3.6, 4.1, 3.5 | 2 | 2026-07-28 | 2026-07-30 | 0 | Yes
5.1 | Site Clearance & Handover | PCC & self-levelling screed preparation | 4.2 SS | 4 | 2026-07-31 | 2026-08-04 | 0 | Yes
5.2 | Site Clearance & Handover | Site deep cleaning & dust clearance | 5.1, 4.2 | 4 | 2026-08-05 | 2026-08-09 | 0 | Yes
5.3 | Site Clearance & Handover | Joint survey of cleared shell | 5.2 | 1 | 2026-08-05 | 2026-08-06 | 0 | Yes
5.4 | Milestone | Cleared shell handover - Phase 1 completion | 5.3 | 0 | 30 | 30 | 0 | Yes |  |  |  |  | ◆
PHASE 2 - NEW FIT-OUT WORKS (DAY 31-120 ¦ 90 DAYS)
6.1 | Civil Works | Setting out & marking as per layout | 5.4 | 3 | 2026-08-06 | 2026-08-09 | 0 | Yes
6.3 | Civil Works | Gypsum partition framing & ply backing | 6.1 SS+2 | 12 | 2026-08-08 | 2026-08-20 | 0 | Yes
6.2 | Civil Works | AAC block masonry work | 6.1 | 9 | 2026-08-09 | 2026-08-18 | 11 | No
6.4 | Civil Works | Self-levelling screed flooring | 6.1 | 8 | 2026-08-13 | 2026-08-21 | 79 | No
7.1 | Services - Phase I | HVAC works - Phase I (ducting & piping) | 6.3 SS+3 | 28 | 2026-08-21 | 2026-09-18 | 0 | Yes
7.2 | Services - Phase I | Electrical works - Phase I (conduiting & cabling) | 6.3 SS+3 | 20 | 2026-08-21 | 2026-09-10 | 8 | No
7.3 | Services - Phase I | FLSS works - Phase I (sprinkler piping & rough-in) | 6.3 SS+5 | 14 | 2026-08-21 | 2026-09-04 | 12 | No
7.5 | Services - Phase I | Passive networking - Phase I (cable laying) | 7.2 SS+4 | 12 | 2026-09-05 | 2026-09-17 | 12 | No
6.5 | Civil Works | Waterproofing - wet areas | 6.2 | 4 | 2026-08-21 | 2026-08-25 | 11 | No
7.4 | Services - Phase I | PHE works - Phase I (drainage & water lines) | 6.5 | 6 | 2026-08-21 | 2026-08-27 | 11 | No
TW.1 | Toilet Works | Toilet works (cubicles, cladding, ceiling & sanitaryware) | 6.5 | 22 | 2026-08-27 | 2026-09-18 | 41 | No
7.7 | Services - Phase I | Services Phase-I inspection & sign-off | 7.1, 7.2, 7.3, 7.4, 7.5 | 2 | 2026-09-10 | 2026-09-12 | 0 | Yes
9.1 | Finishes | Gypsum plaster & POP punning | 6.2, 7.7 SS | 8 | 2026-08-21 | 2026-08-29 | 12 | No
8.1 | Ceiling Works | Gypsum board Partition & ceiling - framing | 7.7 | 8 | 2026-08-25 | 2026-09-02 | 0 | Yes
8.2 | Ceiling Works | Gypsum board ceiling - boarding & services integration | 8.1 SS+3 | 9 | 2026-08-29 | 2026-09-07 | 0 | Yes
8.3 | Ceiling Works | Ceiling close-out inspection | 8.2 | 2 | 2026-09-06 | 2026-09-08 | 0 | Yes
9.4 | Finishes | Painting works - primer & first coat | 9.1, 8.2 | 8 | 2026-09-08 | 2026-09-16 | 6 | No
11.2 | Services - Phase II | HVAC works - Phase II (indoor units & diffusers) | 8.3 | 8 | 2026-09-18 | 2026-09-26 | 14 | No
11.5 | Services - Phase II | Passive networking - Phase II (termination & racks) | 8.3, 7.5 | 8 | 2026-09-17 | 2026-09-25 | 7 | No
9.2 | Finishes | Flooring works - tile, marble, wooden & carpet | 8.3 | 25 | 2026-09-25 | 2026-10-20 | 0 | Yes
9.3 | Finishes | Modular glass partitions & doors installation | 8.3 | 10 | 2026-09-25 | 2026-10-05 | 25 | No
11.1 | Services - Phase II | Electrical works - Phase II (fixtures, switches & light fixtures) | 8.3, 9.4 SS+4 | 12 | 2026-10-05 | 2026-10-17 | 6 | No
9.5 | Finishes | Graphics & films application | 9.4 SS+4 | 6 | 2026-10-07 | 2026-10-13 | 28 | No
10.1 | Joinery | Reception, display & water-body joinery | 9.2 SS+4 | 18 | 2026-09-25 | 2026-10-13 | 0 | Yes
10.2 | Joinery | Cafeteria & pantry joinery | 9.2 SS+4 | 12 | 2026-09-25 | 2026-10-07 | 7 | No
11.3 | Services - Phase II | FLSS works - Phase II (heads, detectors & PA system) | 9.2 SS+5 | 8 | 2026-09-25 | 2026-10-03 | 11 | No
11.4 | Services - Phase II | PHE works - Phase II (sanitaryware & fixtures) | 9.2 SS+6 | 5 | 2026-09-18 | 2026-09-23 | 30 | No
12.2 | IT, AV & Signage | Access control & CCTV installation | 11.1 SS+4 | 6 | 2026-09-24 | 2026-09-30 | 12 | No
10.4 | Joinery | Planters installation | 9.5 | 4 | 2026-09-27 | 2026-10-01 | 29 | No
12.3 | IT, AV & Signage | Active networking & IT commissioning | 11.5 | 6 | 2026-09-24 | 2026-09-30 | 7 | No
12.4 | IT, AV & Signage | Signage & wayfinding installation | 9.5 | 5 | 2026-09-27 | 2026-10-02 | 28 | No
14.1 | Testing & Handover | HVAC testing & balancing | 11.2 | 6 | 2026-09-26 | 2026-10-02 | 14 | No
9.6 | Finishes | Painting works - final coat | 9.2 SS+8 | 5 | 2026-09-24 | 2026-09-29 | 9 | No
10.3 | Joinery | Doors & ironmongery installation | 9.3 | 6 | 2026-09-25 | 2026-10-01 | 25 | No
12.1 | IT, AV & Signage | AV system installation | 10.1 SS+6 | 11 | 2026-09-24 | 2026-10-05 | 0 | Yes
12.5 | IT, AV & Signage | Blinds installation | 9.3 | 5 | 2026-09-29 | 2026-10-04 | 26 | No
14.3 | Testing & Handover | Fire & life-safety system testing | 11.3, 12.2 | 4 | 2026-09-29 | 2026-10-03 | 11 | No
13.1 | Furniture | Modular furniture installation | 9.6 SS+3, 11.1 | 8 | 2026-09-27 | 2026-10-05 | 6 | No
14.2 | Testing & Handover | Electrical testing & commissioning | 11.1 | 5 | 2026-10-05 | 2026-10-10 | 9 | No
13.2 | Furniture | Loose furniture & chairs installation | 13.1 SS+3, 10.2 | 6 | 2026-10-10 | 2026-10-16 | 6 | No
14.4 | Testing & Handover | AV & IT integration testing | 12.1, 12.3 | 6 | 2026-10-10 | 2026-10-16 | 0 | Yes
14.6 | Testing & Handover | Integrated systems commissioning | 14.1, 14.2, 14.3, 14.4 | 7 | 2026-10-10 | 2026-10-17 | 0 | Yes
14.7 | Testing & Handover | Snagging & de-snagging | 13.2, 14.6 SS+2, TW.1 | 11 | 2026-10-17 | 2026-10-28 | 0 | Yes
14.8 | Testing & Handover | Final cleaning | 14.7 SS+3 | 3 | 2026-10-28 | 2026-10-31 | 5 | No
14.9 | Testing & Handover | Handover documentation & training | 14.6 | 4 | 2026-10-31 | 2026-11-04 | 2 | No
14.10 | Milestone | Project handover - Phase 2 completion | 14.7, 14.8, 14.9 | 0 | 120 | 120 | 0 | Yes | [17 empty] | ◆
|  | Legend: |  | Normal activity
Critical activity
2026-08-06 | 2026-08-06 |  | ◆ | Milestone
2026-11-04 | 2026-11-04
Days | 90 | Notes:
1. Float = number of days an activity can be delayed without affecting the project completion date. Activities with zero float lie on the critical path.
2. Predecessor relationships: FS = Finish-to-Start, SS = Start-to-Start; the suffix indicates lag in days (e.g. SS+3).
3. Phase 1 concludes with handover of the cleared and conditioned shell on Day 30. All fit-out works commence on Day 31.
4. Durations are on a single-shift working basis and may be compressed through zone-wise execution or additional shifts.
Formulas:
Finish Day = [Start Day]+[Dur (Days)]
Start Day = [Finish Day, row above]+1
Start Day = [Start Day, row above]
Activity No. = [Activity No., row above]+90

## Tracker
KOHLER PUNE - PROJECT SCHEDULE (DEMOLITION & NEW FIT-OUT)
Phase 1 - Demolition & Site Clearance: 30 Days (Day 1-30) ¦ Phase 2 - New Fit-out Works: 90 Days (Day 31-120) ¦ Total Duration: 120 Days ¦ Critical activities shown in red
Activity No. | Section | Activity Description | Start Day | Finish Day | Actually Start | Actual Finish
PHASE 1 - DEMOLITION & SITE CLEARANCE (DAY 1-30 ¦ 30 DAYS)
1.1 | Mobilisation | Site mobilisation & access setup | 2026-07-07 | 2026-07-10
1.2 | Mobilisation | Hoarding, barricading & signages | 2026-07-11 | 2026-07-13
1.3 | Mobilisation | HSE setup, permits & site induction | 2026-07-14 | 2026-07-16
2.1 | Survey & Make-Safe | Existing condition / dilapidation survey | 2026-07-14 | 2026-07-16
2.2 | Survey & Make-Safe | Existing services mapping & tagging | 2026-07-14 | 2026-07-16
1.4 | Mobilisation | Temporary power, water & lighting arrangement | 2026-07-17 | 2026-07-19
2.3 | Survey & Make-Safe | Hazardous material check & clearance | 2026-07-18 | 2026-07-20
2.4 | Survey & Make-Safe | Disconnection & isolation of existing services | 2026-07-21 | 2026-07-24
3.1 | Demolition & Dismantling | Dismantling of false ceiling & services below | 2026-07-17 | 2026-07-22
3.2 | Demolition & Dismantling | Dismantling of partitions, glazing & doors | 2026-07-23 | 2026-07-28
4.1 | Debris Removal | Debris segregation & stacking | 2026-07-24 | 2026-07-30
3.3 | Demolition & Dismantling | Removal of existing flooring & floor chipping | 2026-07-31 | 2026-08-04
3.4 | Demolition & Dismantling | Dismantling of joinery, pantry & fixtures | 2026-07-17 | 2026-07-20
3.5 | Demolition & Dismantling | Dismantling of existing services (cable, duct, pipe) | 2026-07-21 | 2026-07-25
3.6 | Demolition & Dismantling | Civil breaking / hard demolition | 2026-07-26 | 2026-07-30
4.2 | Debris Removal | Debris removal & disposal | 2026-07-28 | 2026-07-30
5.1 | Site Clearance & Handover | PCC & self-levelling screed preparation | 2026-07-31 | 2026-08-04
5.2 | Site Clearance & Handover | Site deep cleaning & dust clearance | 2026-08-05 | 2026-08-09
5.3 | Site Clearance & Handover | Joint survey of cleared shell | 2026-08-05 | 2026-08-06
5.4 | Milestone | Cleared shell handover - Phase 1 completion | 1900-01-29 | 1900-01-29
PHASE 2 - NEW FIT-OUT WORKS (DAY 31-120 ¦ 90 DAYS)
6.1 | Civil Works | Setting out & marking as per layout | 2026-08-06 | 2026-08-09
6.3 | Civil Works | Gypsum partition framing & ply backing | 2026-08-08 | 2026-08-20
6.2 | Civil Works | AAC block masonry work | 2026-08-09 | 2026-08-18
6.4 | Civil Works | Self-levelling screed flooring | 2026-08-13 | 2026-08-21
7.1 | Services - Phase I | HVAC works - Phase I (ducting & piping) | 2026-08-21 | 2026-09-18
7.2 | Services - Phase I | Electrical works - Phase I (conduiting & cabling) | 2026-08-21 | 2026-09-10
7.3 | Services - Phase I | FLSS works - Phase I (sprinkler piping & rough-in) | 2026-08-21 | 2026-09-04
7.5 | Services - Phase I | Passive networking - Phase I (cable laying) | 2026-09-05 | 2026-09-17
6.5 | Civil Works | Waterproofing - wet areas | 2026-08-21 | 2026-08-25
7.4 | Services - Phase I | PHE works - Phase I (drainage & water lines) | 2026-08-21 | 2026-08-27
TW.1 | Toilet Works | Toilet works (cubicles, cladding, ceiling & sanitaryware) | 2026-08-27 | 2026-09-18
7.7 | Services - Phase I | Services Phase-I inspection & sign-off | 2026-09-10 | 2026-09-12
9.1 | Finishes | Gypsum plaster & POP punning | 2026-08-21 | 2026-08-29
8.1 | Ceiling Works | Gypsum board Partition & ceiling - framing | 2026-08-25 | 2026-09-02
8.2 | Ceiling Works | Gypsum board ceiling - boarding & services integration | 2026-08-29 | 2026-09-07
8.3 | Ceiling Works | Ceiling close-out inspection | 2026-09-06 | 2026-09-08
9.4 | Finishes | Painting works - primer & first coat | 2026-09-08 | 2026-09-16
11.2 | Services - Phase II | HVAC works - Phase II (indoor units & diffusers) | 2026-09-18 | 2026-09-26
11.5 | Services - Phase II | Passive networking - Phase II (termination & racks) | 2026-09-17 | 2026-09-25
9.2 | Finishes | Flooring works - tile, marble, wooden & carpet | 2026-09-25 | 2026-10-20
9.3 | Finishes | Modular glass partitions & doors installation | 2026-09-25 | 2026-10-05
11.1 | Services - Phase II | Electrical works - Phase II (fixtures, switches & light fixtures) | 2026-10-05 | 2026-10-17
9.5 | Finishes | Graphics & films application | 2026-10-07 | 2026-10-13
10.1 | Joinery | Reception, display & water-body joinery | 2026-09-25 | 2026-10-13
10.2 | Joinery | Cafeteria & pantry joinery | 2026-09-25 | 2026-10-07
11.3 | Services - Phase II | FLSS works - Phase II (heads, detectors & PA system) | 2026-09-25 | 2026-10-03
11.4 | Services - Phase II | PHE works - Phase II (sanitaryware & fixtures) | 2026-09-18 | 2026-09-23
12.2 | IT, AV & Signage | Access control & CCTV installation | 2026-09-24 | 2026-09-30
10.4 | Joinery | Planters installation | 2026-09-27 | 2026-10-01
12.3 | IT, AV & Signage | Active networking & IT commissioning | 2026-09-24 | 2026-09-30
12.4 | IT, AV & Signage | Signage & wayfinding installation | 2026-09-27 | 2026-10-02
14.1 | Testing & Handover | HVAC testing & balancing | 2026-09-26 | 2026-10-02
9.6 | Finishes | Painting works - final coat | 2026-09-24 | 2026-09-29
10.3 | Joinery | Doors & ironmongery installation | 2026-09-25 | 2026-10-01
12.1 | IT, AV & Signage | AV system installation | 2026-09-24 | 2026-10-05
12.5 | IT, AV & Signage | Blinds installation | 2026-09-29 | 2026-10-04
14.3 | Testing & Handover | Fire & life-safety system testing | 2026-09-29 | 2026-10-03
13.1 | Furniture | Modular furniture installation | 2026-09-27 | 2026-10-05
14.2 | Testing & Handover | Electrical testing & commissioning | 2026-10-05 | 2026-10-10
13.2 | Furniture | Loose furniture & chairs installation | 2026-10-10 | 2026-10-16
14.4 | Testing & Handover | AV & IT integration testing | 2026-10-10 | 2026-10-16
14.6 | Testing & Handover | Integrated systems commissioning | 2026-10-10 | 2026-10-17
14.7 | Testing & Handover | Snagging & de-snagging | 2026-10-17 | 2026-10-28
14.8 | Testing & Handover | Final cleaning | 2026-10-28 | 2026-10-31
14.9 | Testing & Handover | Handover documentation & training | 2026-10-31 | 2026-11-04
14.10 | Milestone | Project handover - Phase 2 completion | 1900-04-29 | 1900-04-29
Legend:
2026-08-06
2026-11-04
Days | 0 | Notes:
1. Float = number of days an activity can be delayed without affecting the project completion date. Activities with zero float lie on the critical path.
2. Predecessor relationships: FS = Finish-to-Start, SS = Start-to-Start; the suffix indicates lag in days (e.g. SS+3).
3. Phase 1 concludes with handover of the cleared and conditioned shell on Day 30. All fit-out works commence on Day 31.
4. Durations are on a single-shift working basis and may be compressed through zone-wise execution or additional shifts.
Formulas:
Activity No. = [Activity No., row above]+90
Section = [Section, row above]-B76

## Sheet2
Client expection for WPR
Change Request
Critical Highlighting
Cost and schedule imapact to highlight in wpr
Risk and issue - 1 slide
Other point
Checklist for all needed to upload on drive

## Critical Path
KOHLER PUNE - CRITICAL PATH
Continuous chain of zero-float activities from Day 1 to Day 120. Any delay to these activities delays project completion.
S.No. | Activity No. | Phase | Critical Activity | Dur | Start | Finish | Sequencing Note
1 | 1.1 | P1 | Site mobilisation & access setup | 3 | 1 | 3 | Programme start - access & permits precede all works
2 | 2.1 | P1 | Existing condition / dilapidation survey | 2 | 4 | 5 | Survey precedes make-safe activities
3 | 2.3 | P1 | Hazardous material check & clearance | 2 | 6 | 7 | Hazardous-material clearance is a stop/go for demolition
4 | 2.4 | P1 | Disconnection & isolation of existing services | 3 | 8 | 10 | No demolition until existing services are isolated
5 | 3.1 | P1 | Dismantling of false ceiling & services below | 5 | 11 | 15 | First dismantling front opens all subsequent demolition
6 | 3.2 | P1 | Dismantling of partitions, glazing & doors | 5 | 13 | 17 | Partition removal clears the floor plate
7 | 3.6 | P1 | Civil breaking / hard demolition | 4 | 18 | 21 | Civil breaking requires structural / noise clearance
8 | 4.2 | P1 | Debris removal & disposal | 2 | 22 | 23 | Final debris removal precedes shell conditioning
9 | 5.1 | P1 | PCC & self-levelling screed preparation | 4 | 22 | 25 | Slab condition governs screed and flooring
10 | 5.2 | P1 | Site deep cleaning & dust clearance | 4 | 26 | 29 | Dust clearance protects new services & finishes
11 | 5.3 | P1 | Joint survey of cleared shell | 1 | 30 | 30 | Joint survey records the cleared-shell condition
12 | 5.4 | P1 | Cleared shell handover - Phase 1 completion | 0 | 30 | 30 | Phase 1 handover gate releases all fit-out works
13 | 6.1 | P2 | Setting out & marking as per layout | 3 | 31 | 33 | Setting-out governs all subsequent trades
14 | 6.3 | P2 | Gypsum partition framing & ply backing | 12 | 33 | 44 | Partition framing precedes services in walls
15 | 7.1 | P2 | HVAC works - Phase I (ducting & piping) | 28 | 36 | 63 | HVAC ducting & piping - the governing services activity
16 | 7.7 | P2 | Services Phase-I inspection & sign-off | 2 | 64 | 65 | Services Phase-I sign-off; ceiling cannot start before this
17 | 8.1 | P2 | Gypsum board ceiling - framing | 8 | 66 | 73 | Ceiling framing governs all overhead services
18 | 8.2 | P2 | Gypsum board ceiling - boarding & services integration | 9 | 69 | 77 | Boarding & services integration precede close-out
19 | 8.3 | P2 | Ceiling close-out inspection | 2 | 78 | 79 | Ceiling close-out releases flooring & finishes
20 | 9.2 | P2 | Flooring works - tile, marble, wooden & carpet | 25 | 80 | 104 | Flooring - long-duration finishing activity
21 | 10.1 | P2 | Reception, display & water-body joinery | 18 | 84 | 101 | Reception & display joinery - fabrication-led
22 | 12.1 | P2 | AV system installation | 11 | 90 | 100 | AV installation governs integration testing
23 | 14.4 | P2 | AV & IT integration testing | 7 | 101 | 107 | AV & IT integration testing precedes commissioning
24 | 14.6 | P2 | Integrated systems commissioning | 7 | 108 | 114 | Integrated commissioning of all systems
25 | 14.7 | P2 | Snagging & de-snagging | 11 | 110 | 120 | Snagging & de-snagging precede handover
26 | 14.10 | P2 | Project handover - Phase 2 completion | 0 | 120 | 120 | Project handover & occupation