## Slide 1
CLIENT ISSUE · CONTRACT BASELINE
SKF, Pune
SKF India (Industrial) Ltd · Units 801–802, 8th Floor, Millennium Tower 3, Wakad, Pune
Project Programme
DnB Planning Engine v1.0.0

## Slide 2
Programme at a glance
COMMENCEMENT
2026-06-08
CONTRACT COMPLETION
2026-08-22
per agreement
AREA
26,484 sft
CONTRACT VALUE
INR 8,21,00,400
excl. taxes
Phase | Start | Completion
Site Prep | 2026-06-08 | 2026-06-15
Civil Work | 2026-06-21 | 2026-07-25
Partition & Paneling | 2026-06-23 | 2026-07-21
Electrical & Networking | 2026-06-25 | 2026-08-05
False Ceiling | 2026-07-06 | 2026-07-19
HVAC | 2026-07-04 | 2026-07-30
Sprinkler Work | 2026-06-27 | 2026-08-07
LV Systems | 2026-07-11 | 2026-07-30
Doors & Carpentry | 2026-07-06 | 2026-07-31
Finishing | 2026-07-22 | 2026-08-12
Modular Placement | 2026-07-25 | 2026-08-11
Handover | 2026-08-05 | 2026-08-14

## Slide 3
Payment milestones
Stage | Target date | % | Value | Scope covered
RA1 | 2026-06-08 | 0% | INR 0 | Project mobilisation (no advance payable)
RA2 | 2026-06-28 | 20% | INR 1,64,20,080 | Partition marking, frameworks, skinning, civil walls, conduiting, raceways + gypsum/electrical material delivery
RA3 | 2026-07-18 | 25% | INR 2,05,25,100 | Partition closing, wiring, sprinkler piping, FAS wiring + duct/cable/ply/tile delivery; furniture/carpet/glass orders closed
RA4 | 2026-08-02 | 25% | INR 2,05,25,100 | Paint base coats, glass channels, duct installation, ceiling framing + carpet/sanitary/doors/DB delivery
RA5 | 2026-08-17 | 25% | INR 2,05,25,100 | Switches, sanitary fixtures, carpentry, doors, first paint coat, false ceiling; pre-commissioning
RA6 | 2026-08-22 | 5% | INR 41,05,020 | Against 12-month DLP bank guarantee at virtual completion/handover

## Slide 4
What we need from you — client & builder inputs (1/2)
Sr | Area | Description | Responsibility | Required by
1 | Kick Off | Site kick-off meeting and pooja | Client/FS | 2026-06-08
2 | Commercial | Project PO / signed agreement | Client | 2026-06-08
3 | Commercial | Project advance payment | Client | 2026-06-15
4 | Design | Layout approval | Client | 2026-05-29
5 | Design | 3D approvals | Client | 2026-06-13
6 | Design | Material sampling approval | Client/FS | 2026-07-10
7 | Design | MEP drawings approval | Client/PMC | 2026-05-27
8 | Design | Electrical / IT requirement and load confirmation | Client | 2026-05-27
9 | Operation | Builder permissions and mobilisation clearance | FS/Builder | 2026-06-01
10 | Operation | Mathadi clearance | FS | 2026-06-01
11 | Operation | Fire NOC / CFO approval | FS/Builder | 2026-06-13
12 | Operation | BMC / statutory approval | FS/Builder | 2026-06-07

## Slide 5
What we need from you — client & builder inputs (2/2)
Sr | Area | Description | Responsibility | Required by
13 | Operation | Temporary power and water availability | Builder | 2026-06-05
14 | Operation | Lift availability for material movement | Builder | 2026-06-18
15 | Operation | Work hours clarity in building | Builder | 2026-06-05
16 | Operation | Heat load approval / CFM availability | Builder | 2026-06-20
17 | Operation | Wi-Fi and access point locations | Client | 2026-07-01
18 | Operation | Modular vendor closure for site marking | Client | 2026-07-11
19 | Design/Operation | Client-supplied items (IT / AV) delivery | Client | 2026-07-01
20 | Operation | Store space and debris removal area | Builder | 2026-06-05

## Slide 6
Design deliverables — approval dates (1/7)
Category | Deliverable | Criticality | Approval by
GFC | Base Build Layout | Very Critical | 2026-06-20
GFC | Furniture Layout | Very Critical | 2026-07-24
GFC | Furniture Dimensions Layout | High | 2026-07-24
GFC | Partition Layout | Very Critical | 2026-06-22
GFC | Flooring Layout | High | 2026-07-19
GFC | Floor Marking Layout | Medium | 2026-07-19
GFC | Raised Flooring Layout | High | 2026-07-19
GFC | Door Schedule Layout | High | 2026-07-02
GFC | Wall Finishes Layout | High | 2026-07-22
GFC | Modular Layout | Very Critical | 2026-07-24
GFC | RCP Layout | Very Critical | 2026-07-05
GFC | Lighting Layout (with dimensions) | Very Critical | 2026-06-09
GFC | Wallpaper & Graphics | Low | 2026-07-21
GFC | Fire Evacuation Plan | Medium | 2026-07-21

## Slide 7
Design deliverables — approval dates (2/7)
Category | Deliverable | Criticality | Approval by
GFC | 3D Views — Detailed & Client Approval | Very Critical | 2026-06-22
MEP | Electrical DBR | Very Critical | 2026-06-09
MEP | Electrical SLD Layout | Very Critical | 2026-06-09
MEP | Electrical Load Calculation | Very Critical | 2026-06-09
MEP | Power, Data & Switch Board Layout | Very Critical | 2026-06-09
MEP | Raceway Layout | Very Critical | 2026-06-09
MEP | Cable Tray Layout | High | 2026-06-09
MEP | Lighting Looping Layout | High | 2026-06-09
MEP | Panel & DB Position Layout | High | 2026-06-09
MEP | UPS Calculation & Specification | High | 2026-06-09
MEP | HVAC DBR | Very Critical | 2026-07-03
MEP | HVAC Heat Load | Very Critical | 2026-07-03
MEP | HVAC Layout | Very Critical | 2026-07-03
MEP | PHE DBR & Plumbing Layout | High | 2026-06-29

## Slide 8
Design deliverables — approval dates (3/7)
Category | Deliverable | Criticality | Approval by
MEP | Fire Sprinkler Layout | Very Critical | 2026-06-26
MEP | FA / PA System Layout | High | 2026-07-10
MEP | ACS / CCTV / WiFi Layout | High | 2026-07-10
MEP | LV DBR | High | 2026-07-10
SAMPLING | Floor and Dado Tiles — Reception & Lounge | High | 2026-07-19
SAMPLING | Floor and Dado Tiles — Workstations | High | 2026-07-19
SAMPLING | Floor and Dado Tiles — Cabins & Meeting Rooms | High | 2026-07-19
SAMPLING | Floor and Dado Tiles — Boardroom | High | 2026-07-19
SAMPLING | Floor and Dado Tiles — Cafeteria & Pantry | High | 2026-07-19
SAMPLING | Floor and Dado Tiles — Toilets | High | 2026-07-19
SAMPLING | Floor and Dado Tiles — Support & Server | High | 2026-07-19
SAMPLING | Carpentry Laminates & Veneer Shades — Reception & Lounge | High | 2026-07-02
SAMPLING | Carpentry Laminates & Veneer Shades — Workstations | High | 2026-07-02
SAMPLING | Carpentry Laminates & Veneer Shades — Cabins & Meeting Rooms | High | 2026-07-02

## Slide 9
Design deliverables — approval dates (4/7)
Category | Deliverable | Criticality | Approval by
SAMPLING | Carpentry Laminates & Veneer Shades — Boardroom | High | 2026-07-02
SAMPLING | Carpentry Laminates & Veneer Shades — Cafeteria & Pantry | High | 2026-07-02
SAMPLING | Carpentry Laminates & Veneer Shades — Toilets | High | 2026-07-02
SAMPLING | Carpentry Laminates & Veneer Shades — Support & Server | High | 2026-07-02
SAMPLING | Paint Shades — Reception & Lounge | Medium | 2026-07-22
SAMPLING | Paint Shades — Workstations | Medium | 2026-07-22
SAMPLING | Paint Shades — Cabins & Meeting Rooms | Medium | 2026-07-22
SAMPLING | Paint Shades — Boardroom | Medium | 2026-07-22
SAMPLING | Paint Shades — Cafeteria & Pantry | Medium | 2026-07-22
SAMPLING | Paint Shades — Toilets | Medium | 2026-07-22
SAMPLING | Paint Shades — Support & Server | Medium | 2026-07-22
SAMPLING | Carpet / SPC Flooring — Reception & Lounge | High | 2026-07-19
SAMPLING | Carpet / SPC Flooring — Workstations | High | 2026-07-19
SAMPLING | Carpet / SPC Flooring — Cabins & Meeting Rooms | High | 2026-07-19

## Slide 10
Design deliverables — approval dates (5/7)
Category | Deliverable | Criticality | Approval by
SAMPLING | Carpet / SPC Flooring — Boardroom | High | 2026-07-19
SAMPLING | Carpet / SPC Flooring — Cafeteria & Pantry | High | 2026-07-19
SAMPLING | Carpet / SPC Flooring — Toilets | High | 2026-07-19
SAMPLING | Carpet / SPC Flooring — Support & Server | High | 2026-07-19
SAMPLING | Demountable Glass Partition | Very Critical | 2026-07-07
SAMPLING | Backpainted Glass | Medium | 2026-07-07
SAMPLING | Grid & Stretch Ceiling — Reception & Lounge | High | 2026-07-05
SAMPLING | Grid & Stretch Ceiling — Workstations | High | 2026-07-05
SAMPLING | Grid & Stretch Ceiling — Cabins & Meeting Rooms | High | 2026-07-05
SAMPLING | Grid & Stretch Ceiling — Boardroom | High | 2026-07-05
SAMPLING | Grid & Stretch Ceiling — Cafeteria & Pantry | High | 2026-07-05
SAMPLING | Grid & Stretch Ceiling — Toilets | High | 2026-07-05
SAMPLING | Grid & Stretch Ceiling — Support & Server | High | 2026-07-05
SAMPLING | Acoustics / Fluted Panel — Reception & Lounge | Medium | 2026-07-05

## Slide 11
Design deliverables — approval dates (6/7)
Category | Deliverable | Criticality | Approval by
SAMPLING | Acoustics / Fluted Panel — Workstations | Medium | 2026-07-05
SAMPLING | Acoustics / Fluted Panel — Cabins & Meeting Rooms | Medium | 2026-07-05
SAMPLING | Acoustics / Fluted Panel — Boardroom | Medium | 2026-07-05
SAMPLING | Acoustics / Fluted Panel — Cafeteria & Pantry | Medium | 2026-07-05
SAMPLING | Acoustics / Fluted Panel — Toilets | Medium | 2026-07-05
SAMPLING | Acoustics / Fluted Panel — Support & Server | Medium | 2026-07-05
SAMPLING | Switch Sockets | Medium | 2026-06-09
SAMPLING | Decorative Lights | High | 2026-06-09
SAMPLING | Sanitary Fixtures | Medium | 2026-06-29
SAMPLING | Chairs & Loose Furniture | High | 2026-07-24
SAMPLING | Blinds | Medium | 2026-07-21
SAMPLING | Skirting & T Profile | Low | 2026-07-21
GFC | TD — Interior Works | Very Critical | 2026-06-22
GFC | TD — Planters | Very Critical | 2026-07-02

## Slide 12
Design deliverables — approval dates (7/7)
Category | Deliverable | Criticality | Approval by
GFC | TD — Modular Furniture | Very Critical | 2026-07-24
GFC | TD — Loose Furniture & Chairs | Very Critical | 2026-07-24
GFC | Elevation — Reception & Lounge | High | 2026-06-22
GFC | Elevation — Workstations | High | 2026-06-22
GFC | Elevation — Cabins & Meeting Rooms | High | 2026-06-22
GFC | Elevation — Boardroom | High | 2026-06-22
GFC | Elevation — Cafeteria & Pantry | High | 2026-06-22
GFC | Elevation — Toilets | High | 2026-06-22
GFC | Elevation — Support & Server | High | 2026-06-22

## Slide 13
Procurement — delivery dates required on site (1/2)
Package | Criticality | Delivery required
Civil Works | Low | 2026-06-19
Interior Works | Low | 2026-06-21
Modular Glass Partitions & Doors | Very Critical | 2026-07-06
Signages | Medium | 2026-08-01
Graphics & Films | Very Critical | 2026-07-28
Blinds | High | 2026-08-02
Planters | Medium | 2026-07-23
Carpet Flooring | High | 2026-07-23
Modular Furniture | Very Critical | 2026-07-23
Loose Furniture & Chairs | Very Critical | 2026-07-31
Electrical Works | High | 2026-06-23
Light Fixtures | High | —
UPS | High | —
Plumbing (PHE) | Low | 2026-06-28

## Slide 14
Procurement — delivery dates required on site (2/2)
Package | Criticality | Delivery required
HVAC (Low Side + VAV + VRF) | High | 2026-07-02
Passive Networking | Medium | —
Fire & Security | High | 2026-06-25
GSS / General Site Services | Medium | 2026-06-06

## Slide 15
Billing milestones
RA | Due | % | Status
RA1 | 2026-06-08 | 0% | Delayed
RA2 | 2026-06-28 | 20% | Delayed
RA3 | 2026-07-18 | 25% | Delayed
RA4 | 2026-08-02 | 25% | WIP
RA5 | 2026-08-17 | 25% | WIP
RA6 | 2026-08-22 | 5% | Not Started