## Slide 1
CLIENT ISSUE · CONTRACT BASELINE
KOHLER OS, Pune
Kohler India Corporation Pvt. Ltd. · 7th Floor (7A), ITC, Pune
Project Programme
DnB Planning Engine v1.0.0

## Slide 2
Programme at a glance
COMMENCEMENT
2026-07-07
CONTRACT COMPLETION
2026-11-04
per agreement
AREA
14,905 sft
CONTRACT VALUE
INR 5,70,04,000
excl. taxes
Phase | Start | Completion
Mobilisation | 2026-07-07 | 2026-07-18
Survey & Make-Safe | 2026-07-14 | 2026-07-23
Demolition & Dismantling | 2026-07-17 | 2026-08-03
Debris Removal | 2026-07-24 | 2026-07-29
Site Clearance & Handover | 2026-07-31 | 2026-08-08
Milestone | 2026-08-05 | 2026-11-03
Civil Works | 2026-08-06 | 2026-08-24
Services - Phase I | 2026-08-21 | 2026-09-17
Ceiling Works | 2026-08-25 | 2026-09-07
Services - Phase II | 2026-09-17 | 2026-10-16
IT, AV & Signage | 2026-09-24 | 2026-10-04
Testing & Handover | 2026-09-26 | 2026-11-03
Finishes | 2026-08-21 | 2026-10-19
Joinery | 2026-09-25 | 2026-10-12
Furniture | 2026-09-27 | 2026-10-15
Toilet Works | 2026-08-27 | 2026-09-17

## Slide 3
Payment milestones
Stage | Target date | % | Value | Scope covered
ADV | 2026-07-07 | 30% | INR 1,71,01,200 | Project mobilisation.
RA1 | 2026-08-21 | 20% | INR 1,14,00,800 | Execution: Demolition, partition line marking, frameworks, single-side skinning, civil wall, plastering, plumbing, ceiling and wall electrical conduiting, floor raceway laying. Material delivery: gypsum frames, gypsum sheets, electrical conduits and raceway, siporex blocks. Key order closures: HVAC, fire alarm system, carpentry.
RA2 | 2026-09-15 | 15% | INR 85,50,600 | Execution: closing of partitions from double side, electrical wiring, fire sprinkler piping, FAS wiring. Material delivery: duct material, wires/cables, ply for carpentry items, vitrified tiles. Key order closures: modular furniture, chairs, carpets, glass.
RA3 | 2026-09-30 | 15% | INR 85,50,600 | Execution: painting base-coat preparation, glass channel, HVAC duct installation, false ceiling framing. Material delivery: carpets, sanitary fittings and fixtures, doors, DB/MCB. Key order closures: decorative elements, glass films, wallpapers, canvas frames, branding.
RA4 | 2026-10-25 | 15% | INR 85,50,600 | Execution: electrical switches/sockets, sanitary fixtures, carpentry structures ready, flush doors, first coat of paint, false ceiling, before HVAC final commissioning and before LV commissioning. Material delivery: modular furniture on site, carpet on site and before chair delivery. Key order closure: deep cleaning.
RA5 | 2026-11-04 | 5% | INR 28,50,200 | Release against unconditional bank guarantee of equal amount, valid for 6 months Defects Liability Period.

## Slide 4
What we need from you — client & builder inputs (1/2)
Sr | Area | Description | Responsibility | Required by
1 | Kick Off | Site kick-off meeting and pooja | Client/FS | 2026-07-07
2 | Commercial | Project PO / signed agreement | Client | 2026-07-07
3 | Commercial | Project advance payment | Client | 2026-07-14
4 | Design | Layout approval | Client | 2026-07-04
5 | Design | 3D approvals | Client | 2026-07-17
6 | Design | Material sampling approval | Client/FS | 2026-08-03
7 | Design | MEP drawings approval | Client/PMC | 2026-08-07
8 | Design | Electrical / IT requirement and load confirmation | Client | 2026-08-07
9 | Operation | Builder permissions and mobilisation clearance | FS/Builder | 2026-07-07
10 | Operation | Mathadi clearance | FS | 2026-07-07
11 | Operation | Fire NOC / CFO approval | FS/Builder | 2026-08-07
12 | Operation | BMC / statutory approval | FS/Builder | 2026-06-30

## Slide 5
What we need from you — client & builder inputs (2/2)
Sr | Area | Description | Responsibility | Required by
13 | Operation | Temporary power and water availability | Builder | 2026-08-16
14 | Operation | Lift availability for material movement | Builder | 2026-07-11
15 | Operation | Work hours clarity in building | Builder | 2026-07-11
16 | Operation | Heat load approval / CFM availability | Builder | 2026-08-07
17 | Operation | Wi-Fi and access point locations | Client | 2026-08-26
18 | Operation | Modular vendor closure for site marking | Client | 2026-07-21
19 | Design/Operation | Client-supplied items (IT / AV) delivery | Client | 2026-08-26
20 | Operation | Store space and debris removal area | Builder | 2026-07-11

## Slide 6
Design deliverables — approval dates (1/7)
Category | Deliverable | Criticality | Approval by
GFC | Base Build Layout | Very Critical | 2026-07-13
GFC | Furniture Layout | Very Critical | 2026-07-28
GFC | Furniture Dimensions Layout | High | 2026-07-24
GFC | Partition Layout | Very Critical | 2026-07-24
GFC | Flooring Layout | High | 2026-08-12
GFC | Floor Marking Layout | Medium | 2026-08-12
GFC | Raised Flooring Layout | High | 2026-08-12
GFC | Door Schedule Layout | High | 2026-09-24
GFC | Wall Finishes Layout | High | 2026-09-07
GFC | Modular Layout | Very Critical | 2026-07-28
GFC | RCP Layout | Very Critical | 2026-08-24
GFC | Lighting Layout (with dimensions) | Very Critical | 2026-08-20
GFC | Wallpaper & Graphics | Low | 2026-08-20
GFC | Fire Evacuation Plan | Medium | 2026-08-20

## Slide 7
Design deliverables — approval dates (2/7)
Category | Deliverable | Criticality | Approval by
GFC | 3D Views — Detailed & Client Approval | Very Critical | 2026-08-06
MEP | Electrical DBR | Very Critical | 2026-08-20
MEP | Electrical SLD Layout | Very Critical | 2026-08-20
MEP | Electrical Load Calculation | Very Critical | 2026-08-20
MEP | Power, Data & Switch Board Layout | Very Critical | 2026-08-20
MEP | Raceway Layout | Very Critical | 2026-08-20
MEP | Cable Tray Layout | High | 2026-08-20
MEP | Lighting Looping Layout | High | 2026-08-20
MEP | Panel & DB Position Layout | High | 2026-08-20
MEP | UPS Calculation & Specification | High | 2026-08-20
MEP | HVAC DBR | Very Critical | 2026-08-20
MEP | HVAC Heat Load | Very Critical | 2026-08-20
MEP | HVAC Layout | Very Critical | 2026-08-20
MEP | PHE DBR & Plumbing Layout | High | 2026-08-20

## Slide 8
Design deliverables — approval dates (3/7)
Category | Deliverable | Criticality | Approval by
MEP | Fire Sprinkler Layout | Very Critical | 2026-08-20
MEP | FA / PA System Layout | High | 2026-09-04
MEP | ACS / CCTV / WiFi Layout | High | 2026-09-04
MEP | LV DBR | High | 2026-09-04
SAMPLING | Floor and Dado Tiles — Reception & Lounge | High | 2026-08-12
SAMPLING | Floor and Dado Tiles — Workstations | High | 2026-08-12
SAMPLING | Floor and Dado Tiles — Cabins & Meeting Rooms | High | 2026-08-12
SAMPLING | Floor and Dado Tiles — Boardroom | High | 2026-08-12
SAMPLING | Floor and Dado Tiles — Cafeteria & Pantry | High | 2026-08-12
SAMPLING | Floor and Dado Tiles — Toilets | High | 2026-08-12
SAMPLING | Floor and Dado Tiles — Support & Server | High | 2026-08-12
SAMPLING | Carpentry Laminates & Veneer Shades — Reception & Lounge | High | 2026-09-24
SAMPLING | Carpentry Laminates & Veneer Shades — Workstations | High | 2026-09-24
SAMPLING | Carpentry Laminates & Veneer Shades — Cabins & Meeting Rooms | High | 2026-09-24

## Slide 9
Design deliverables — approval dates (4/7)
Category | Deliverable | Criticality | Approval by
SAMPLING | Carpentry Laminates & Veneer Shades — Boardroom | High | 2026-09-24
SAMPLING | Carpentry Laminates & Veneer Shades — Cafeteria & Pantry | High | 2026-09-24
SAMPLING | Carpentry Laminates & Veneer Shades — Toilets | High | 2026-09-24
SAMPLING | Carpentry Laminates & Veneer Shades — Support & Server | High | 2026-09-24
SAMPLING | Paint Shades — Reception & Lounge | Medium | 2026-09-07
SAMPLING | Paint Shades — Workstations | Medium | 2026-09-07
SAMPLING | Paint Shades — Cabins & Meeting Rooms | Medium | 2026-09-07
SAMPLING | Paint Shades — Boardroom | Medium | 2026-09-07
SAMPLING | Paint Shades — Cafeteria & Pantry | Medium | 2026-09-07
SAMPLING | Paint Shades — Toilets | Medium | 2026-09-07
SAMPLING | Paint Shades — Support & Server | Medium | 2026-09-07
SAMPLING | Carpet / SPC Flooring — Reception & Lounge | High | 2026-08-12
SAMPLING | Carpet / SPC Flooring — Workstations | High | 2026-08-12
SAMPLING | Carpet / SPC Flooring — Cabins & Meeting Rooms | High | 2026-08-12

## Slide 10
Design deliverables — approval dates (5/7)
Category | Deliverable | Criticality | Approval by
SAMPLING | Carpet / SPC Flooring — Boardroom | High | 2026-08-12
SAMPLING | Carpet / SPC Flooring — Cafeteria & Pantry | High | 2026-08-12
SAMPLING | Carpet / SPC Flooring — Toilets | High | 2026-08-12
SAMPLING | Carpet / SPC Flooring — Support & Server | High | 2026-08-12
SAMPLING | Demountable Glass Partition | Very Critical | 2026-09-24
SAMPLING | Backpainted Glass | Medium | 2026-09-24
SAMPLING | Grid & Stretch Ceiling — Reception & Lounge | High | 2026-08-24
SAMPLING | Grid & Stretch Ceiling — Workstations | High | 2026-08-24
SAMPLING | Grid & Stretch Ceiling — Cabins & Meeting Rooms | High | 2026-08-24
SAMPLING | Grid & Stretch Ceiling — Boardroom | High | 2026-08-24
SAMPLING | Grid & Stretch Ceiling — Cafeteria & Pantry | High | 2026-08-24
SAMPLING | Grid & Stretch Ceiling — Toilets | High | 2026-08-24
SAMPLING | Grid & Stretch Ceiling — Support & Server | High | 2026-08-24
SAMPLING | Acoustics / Fluted Panel — Reception & Lounge | Medium | 2026-08-24

## Slide 11
Design deliverables — approval dates (6/7)
Category | Deliverable | Criticality | Approval by
SAMPLING | Acoustics / Fluted Panel — Workstations | Medium | 2026-08-24
SAMPLING | Acoustics / Fluted Panel — Cabins & Meeting Rooms | Medium | 2026-08-24
SAMPLING | Acoustics / Fluted Panel — Boardroom | Medium | 2026-08-24
SAMPLING | Acoustics / Fluted Panel — Cafeteria & Pantry | Medium | 2026-08-24
SAMPLING | Acoustics / Fluted Panel — Toilets | Medium | 2026-08-24
SAMPLING | Acoustics / Fluted Panel — Support & Server | Medium | 2026-08-24
SAMPLING | Switch Sockets | Medium | 2026-08-20
SAMPLING | Decorative Lights | High | 2026-08-20
SAMPLING | Sanitary Fixtures | Medium | 2026-08-20
SAMPLING | Chairs & Loose Furniture | High | 2026-07-26
SAMPLING | Blinds | Medium | 2026-08-20
SAMPLING | Skirting & T Profile | Low | 2026-08-20
GFC | TD — Interior Works | Very Critical | 2026-07-24
GFC | TD — Modular Glass Partitions & Doors | Very Critical | 2026-07-24

## Slide 12
Design deliverables — approval dates (7/7)
Category | Deliverable | Criticality | Approval by
GFC | TD — Modular Furniture | Very Critical | 2026-07-24
GFC | TD — Loose Furniture & Chairs | Very Critical | 2026-07-24
GFC | Elevation — Reception & Lounge | High | 2026-09-24
GFC | Elevation — Workstations | High | 2026-09-24
GFC | Elevation — Cabins & Meeting Rooms | High | 2026-09-24
GFC | Elevation — Boardroom | High | 2026-09-24
GFC | Elevation — Cafeteria & Pantry | High | 2026-09-24
GFC | Elevation — Toilets | High | 2026-09-24
GFC | Elevation — Support & Server | High | 2026-09-24

## Slide 13
Procurement — delivery dates required on site (1/2)
Package | Criticality | Delivery required
Civil Works | Low | 2026-07-12
Interior Works | Low | 2026-08-06
Modular Glass Partitions & Doors | Very Critical | 2026-09-23
Signages | Medium | 2026-09-25
Graphics & Films | Very Critical | 2026-10-05
Blinds | High | 2026-09-27
Planters | Medium | 2026-09-25
Toilet Works | Medium | 2026-08-25
Carpet Flooring | High | 2026-08-11
Modular Furniture | Very Critical | 2026-09-25
Loose Furniture & Chairs | Very Critical | 2026-10-08
Electrical Works | High | 2026-08-19
Light Fixtures | High | 2026-10-03
HVAC | Medium | 2026-08-19

## Slide 14
Procurement — delivery dates required on site (2/2)
Package | Criticality | Delivery required
Passive Networking | Medium | 2026-09-03
Plumbing Works | Medium | 2026-08-19
FLSS Works | Medium | 2026-08-19
Dishwash Area | Medium | 2026-08-19
Kitchen Equipments & Others | Medium | —

## Slide 15
Billing milestones
RA | Due | % | Status
ADV | 2026-07-07 | 30% | Delayed
RA1 | 2026-08-21 | 20% | Not Started
RA2 | 2026-09-15 | 15% | Not Started
RA3 | 2026-09-30 | 15% | Not Started
RA4 | 2026-10-25 | 15% | Not Started
RA5 | 2026-11-04 | 5% | Not Started