## Slide 1
INTERNAL — NOT FOR CLIENT ISSUE
Emirates Mumbai
Emirates Airlines · Commerz III, Oberoi Realty, Goregaon East, Mumbai
Execution Plan · confidence 88% · norms norms-v1
DnB Planning Engine v1.0.0

## Slide 2
Position
INTERNAL TARGET
2026-02-22
245 wd (CPM)
CONTRACT FINISH
2026-02-23
BUFFER
1d
invariant holds
CRITICAL
7 / 216
zero float
PEAK MANPOWER
130
2026-01-15
MARGIN
47.3%
6 RA milestones
Confidence basis: 8/9 inputs provided; 2/10 packages unmapped; buffer 1d.
Phase | Start | End | On critical path
Construction | 2025-06-23 | 2026-02-22 | YES

## Slide 3
Critical path — 7 activities, zero float
# | Activity | Trade | Dur | Start | Finish
e0 | Project start | general | 0d | 2025-06-23 | 2025-06-23
e387 | Signages Supply and Installation | cleaning | 3d | 2026-02-05 | 2026-02-07
e388 | Branding (Logo) | cleaning | 3d | 2026-02-17 | 2026-02-19
e392 | Deep Cleaning | cleaning | 5d | 2026-02-18 | 2026-02-22
e390 | Fire exit signages Installation | cleaning | 4d | 2026-02-19 | 2026-02-22
e391 | Fire evacuation maps Installation | general | 4d | 2026-02-19 | 2026-02-22
e389 | Fire extinguishers Installation | sprinkler | 3d | 2026-02-20 | 2026-02-22

## Slide 4
Full activity schedule with float (1/14)
# | Activity | Phase | Dur | Start | Finish | Float
e0 | Project start | Construction | 0d | 2025-06-23 | 2025-06-23 | 0d
e131 | Mobilisation Period | Construction | 7d | 2025-07-20 | 2025-07-26 | 211d
e134 | Waterproofing | Construction | 4d | 2025-09-26 | 2025-09-29 | 72d
e135 | Pest Control | Construction | 1d | 2025-09-27 | 2025-09-27 | 72d
e136 | Self Leveling | Construction | 7d | 2025-09-30 | 2025-10-06 | 72d
e141 | Blockwork/RCC Lintel | Construction | 5d | 2025-10-02 | 2025-10-06 | 72d
e142 | Plastering | Construction | 5d | 2025-10-07 | 2025-10-11 | 72d
e143 | POP Punning | Construction | 6d | 2025-10-07 | 2025-10-12 | 72d
e137 | PCC | Construction | 10d | 2025-10-12 | 2025-10-21 | 72d
e138 | Modifoam Flooring | Construction | 7d | 2025-10-24 | 2025-10-30 | 72d
e139 | Line out Marking | Construction | 2d | 2025-10-24 | 2025-10-25 | 72d
e140 | Line out Checking & Approval | Construction | 1d | 2025-10-26 | 2025-10-26 | 72d
e144 | Engineered Concrete Flooring | Construction | 10d | 2025-12-03 | 2025-12-12 | 72d
e146 | GI Framing Works | Construction | 12d | 2025-10-03 | 2025-10-14 | 118d
e147 | Single side single skinning | Construction | 9d | 2025-10-10 | 2025-10-18 | 118d
e149 | Insulation works | Construction | 5d | 2025-10-15 | 2025-10-19 | 118d

## Slide 5
Full activity schedule with float (2/14)
# | Activity | Phase | Dur | Start | Finish | Float
e148 | Clearance from Services | Construction | 3d | 2025-10-16 | 2025-10-18 | 118d
e150 | Second side single skinning | Construction | 10d | 2025-10-18 | 2025-10-27 | 118d
e152 | Delivery of Modular Glazed Partitions glass | Construction | 20d | 2025-11-12 | 2025-12-01 | 31d
e153 | Installation of glass partitions frames | Construction | 10d | 2025-12-02 | 2025-12-11 | 31d
e154 | Installation of glass for glazed partitions | Construction | 15d | 2025-12-12 | 2025-12-26 | 31d
e159 | Sliding Folding Partition | Construction | 15d | 2025-12-23 | 2026-01-06 | 31d
e155 | Installation of curved glass partition | Construction | 15d | 2026-01-01 | 2026-01-15 | 31d
e156 | Installation of solid flush doors | Construction | 7d | 2026-01-01 | 2026-01-07 | 31d
e157 | Delivery of Fire Rated Metal Doors | Construction | 7d | 2026-01-01 | 2026-01-07 | 31d
e160 | Switchable smart glass | Construction | 15d | 2026-01-07 | 2026-01-21 | 31d
e158 | Installation of Fire Rated Metal Doors | Construction | 15d | 2026-01-08 | 2026-01-22 | 31d
e162 | Delivery of Raised Flooring | Construction | 2d | 2025-11-04 | 2025-11-05 | 87d
e163 | Marking of Raised Access Flooring | Construction | 3d | 2025-11-08 | 2025-11-10 | 87d
e164 | Fixing of Pedestals | Construction | 5d | 2025-11-11 | 2025-11-15 | 87d
e165 | Fixing of Raised Flooring Tiles | Construction | 7d | 2025-11-13 | 2025-11-19 | 87d
e166 | Cutout for power/data entrys | Construction | 4d | 2025-11-21 | 2025-11-24 | 87d

## Slide 6
Full activity schedule with float (3/14)
# | Activity | Phase | Dur | Start | Finish | Float
e167 | Alignment of Raised Access Flooring | Construction | 5d | 2025-11-23 | 2025-11-27 | 87d
e169 | Vitrified Tiling | Construction | 25d | 2025-10-28 | 2025-11-21 | 8d
e173 | Protection Covering | Construction | 110d | 2025-10-28 | 2026-02-14 | 8d
e170 | Marble Flooring | Construction | 20d | 2025-11-02 | 2025-11-21 | 14d
e171 | Stone flooring | Construction | 10d | 2025-11-22 | 2025-12-01 | 14d
e172 | Carpet Installation | Construction | 15d | 2026-01-25 | 2026-02-08 | 14d
e174 | Wooden raised flooring Installation | Construction | 10d | 2026-01-25 | 2026-02-03 | 19d
e175 | Epoxy Flooring | Construction | 7d | 2026-01-25 | 2026-01-31 | 22d
e177 | GI Framing for gypsum ceiling | Construction | 10d | 2025-11-14 | 2025-11-23 | 70d
e178 | Gypsum boarding & joint finishing | Construction | 15d | 2025-11-25 | 2025-12-09 | 70d
e179 | Cafeteria Decorative Ceiling | Construction | 20d | 2025-11-25 | 2025-12-14 | 70d
e180 | Metal Fabricated Ceiling | Construction | 15d | 2025-11-30 | 2025-12-14 | 70d
e181 | Designer Ceiling | Construction | 15d | 2025-11-30 | 2025-12-14 | 70d
e183 | Delivery of Grid Tiles and frames | Construction | 4d | 2025-11-14 | 2025-11-17 | 73d
e184 | Framing for Grid Tile installation | Construction | 10d | 2025-11-25 | 2025-12-04 | 73d
e185 | Installation of Grid Tiles | Construction | 7d | 2025-12-05 | 2025-12-11 | 73d

## Slide 7
Full activity schedule with float (4/14)
# | Activity | Phase | Dur | Start | Finish | Float
e187 | Delivery of Tiles and frames | Construction | 4d | 2025-11-14 | 2025-11-17 | 82d
e188 | Framing for Tile installation | Construction | 10d | 2025-11-18 | 2025-11-27 | 82d
e189 | Installation of technogrid Tiles | Construction | 5d | 2025-11-28 | 2025-12-02 | 82d
e191 | Ply Framing for stretch ceiling installation | Construction | 10d | 2025-11-20 | 2025-11-29 | 34d
e192 | Delivery of stretch ceiling material on site | Construction | 7d | 2025-12-31 | 2026-01-06 | 34d
e193 | Installation of Stretch Ceiling | Construction | 5d | 2026-01-15 | 2026-01-19 | 34d
e196 | Putty application (walls) | Construction | 10d | 2025-11-07 | 2025-11-16 | 42d
e197 | Primer application & sanding works (walls) | Construction | 10d | 2025-11-17 | 2025-11-26 | 42d
e198 | 1st coat paint (walls) | Construction | 12d | 2025-12-01 | 2025-12-12 | 42d
e199 | 2nd & 3rd coat paint (walls) | Construction | 10d | 2025-12-13 | 2025-12-22 | 42d
e200 | Epoxy Paint | Construction | 20d | 2025-12-23 | 2026-01-11 | 42d
e202 | Putty application (ceiling) | Construction | 10d | 2025-12-14 | 2025-12-23 | 29d
e203 | Primer application & sanding works (ceiling) | Construction | 10d | 2025-12-24 | 2026-01-02 | 29d
e204 | 1st coat paint (ceiling) | Construction | 12d | 2026-01-03 | 2026-01-14 | 29d
e205 | 2nd & 3rd coat paint (ceiling) | Construction | 10d | 2026-01-15 | 2026-01-24 | 29d
e207 | Putty application (metallic) | Construction | 10d | 2026-01-03 | 2026-01-12 | 9d

## Slide 8
Full activity schedule with float (5/14)
# | Activity | Phase | Dur | Start | Finish | Float
e208 | Primer application & sanding works (metallic) | Construction | 10d | 2026-01-13 | 2026-01-22 | 9d
e209 | 1st coat paint (metallic) | Construction | 12d | 2026-01-23 | 2026-02-03 | 9d
e210 | 2nd & 3rd coat paint (metallic) | Construction | 10d | 2026-02-04 | 2026-02-13 | 9d
e212 | Putty application (stucco) | Construction | 10d | 2026-01-03 | 2026-01-12 | 9d
e213 | Primer application & sanding works (stucco) | Construction | 10d | 2026-01-13 | 2026-01-22 | 9d
e214 | 1st coat paint (stucco) | Construction | 12d | 2026-01-23 | 2026-02-03 | 9d
e215 | 2nd & 3rd coat paint (stucco) | Construction | 10d | 2026-02-04 | 2026-02-13 | 9d
e216 | Wall paper base preparation | Construction | 7d | 2025-11-15 | 2025-11-21 | 93d
e218 | Reception Table | Construction | 30d | 2025-10-15 | 2025-11-13 | 24d
e219 | CCM Cabin Table | Construction | 30d | 2025-11-14 | 2025-12-13 | 24d
e220 | Board Room Table | Construction | 30d | 2025-12-14 | 2026-01-12 | 24d
e225 | Built-In Furniture Installation | Construction | 40d | 2025-12-14 | 2026-01-22 | 24d
e223 | Acrylic Designer wall work | Construction | 15d | 2025-12-29 | 2026-01-12 | 24d
e221 | Service Counter | Construction | 10d | 2026-01-03 | 2026-01-12 | 24d
e222 | Ledge Seating | Construction | 10d | 2026-01-03 | 2026-01-12 | 24d
e224 | Pelmet Installation | Construction | 10d | 2026-01-20 | 2026-01-29 | 24d

## Slide 9
Full activity schedule with float (6/14)
# | Activity | Phase | Dur | Start | Finish | Float
e226 | Blinds Installation | Construction | 7d | 2026-01-20 | 2026-01-26 | 24d
e227 | Skirting Installation | Construction | 10d | 2026-01-20 | 2026-01-29 | 24d
e228 | Corner Guard Installation | Construction | 7d | 2026-01-23 | 2026-01-29 | 24d
e229 | Transition Profile Installation | Construction | 4d | 2026-01-26 | 2026-01-29 | 24d
e231 | Dado Installation | Construction | 14d | 2025-10-30 | 2025-11-12 | 13d
e235 | Vertical Garden/Planters | Construction | 14d | 2026-01-13 | 2026-01-26 | 13d
e236 | Fluted Panel installation | Construction | 14d | 2026-01-13 | 2026-01-26 | 13d
e233 | Lacquered Glass Panelling | Construction | 20d | 2026-01-21 | 2026-02-09 | 13d
e232 | Wallpaper Installation | Construction | 15d | 2026-01-26 | 2026-02-09 | 13d
e234 | Glass Film Installation | Construction | 10d | 2026-01-31 | 2026-02-09 | 13d
e238 | Marking of plumbing lines | Construction | 1d | 2025-10-14 | 2025-10-14 | 119d
e239 | Waterproofing (PHE) | Construction | 5d | 2025-10-15 | 2025-10-19 | 119d
e240 | BBC | Construction | 7d | 2025-10-20 | 2025-10-26 | 119d
e242 | Pipes Installation (supply) | Construction | 7d | 2025-10-15 | 2025-10-21 | 118d
e243 | Fittings Installation (supply) | Construction | 6d | 2025-10-22 | 2025-10-27 | 118d
e245 | Pipes Installation (drainage) | Construction | 10d | 2025-10-15 | 2025-10-24 | 95d

## Slide 10
Full activity schedule with float (7/14)
# | Activity | Phase | Dur | Start | Finish | Float
e246 | Fittings Installation (drainage) | Construction | 7d | 2025-10-25 | 2025-10-31 | 95d
e247 | Pumps Installation | Construction | 7d | 2025-11-01 | 2025-11-07 | 95d
e248 | Sanitary Fixtures Installation | Construction | 10d | 2025-11-08 | 2025-11-17 | 95d
e249 | Testing & Commissioning of Plumbing Line | Construction | 2d | 2025-11-18 | 2025-11-19 | 95d
e251 | Temporary Lighting work | Construction | 5d | 2025-09-30 | 2025-10-04 | 29d
e253 | Conduit marking in closed room partitions | Construction | 5d | 2025-10-19 | 2025-10-23 | 105d
e254 | Conduiting for Raw Power, UPS, lighting, IT | Construction | 10d | 2025-10-24 | 2025-11-02 | 105d
e255 | Back box fixing | Construction | 7d | 2025-10-29 | 2025-11-04 | 105d
e256 | Wiring for light circuits | Construction | 12d | 2025-10-29 | 2025-11-09 | 105d
e257 | Wiring for Power Circuits | Construction | 12d | 2025-10-29 | 2025-11-09 | 105d
e259 | Marking of floor raceway | Construction | 6d | 2025-10-31 | 2025-11-05 | 82d
e260 | Support fixing for raceway | Construction | 7d | 2025-11-06 | 2025-11-12 | 82d
e263 | Marking for ceiling cable tray | Construction | 3d | 2025-11-06 | 2025-11-08 | 82d
e264 | Support fixing for cable tray | Construction | 10d | 2025-11-09 | 2025-11-18 | 82d
e261 | Installation of floor Raceway for Power & Data | Construction | 10d | 2025-11-13 | 2025-11-22 | 82d
e265 | Installation of cable tray for IT/Data/Electrical | Construction | 14d | 2025-11-19 | 2025-12-02 | 82d

## Slide 11
Full activity schedule with float (8/14)
# | Activity | Phase | Dur | Start | Finish | Float
e262 | Junction, GI Boxes Installation | Construction | 7d | 2025-11-23 | 2025-11-29 | 85d
e267 | Cabling for power | Construction | 15d | 2025-11-10 | 2025-11-24 | 73d
e268 | Cabling for earthing | Construction | 10d | 2025-11-25 | 2025-12-04 | 73d
e269 | Cabling dressing | Construction | 7d | 2025-12-05 | 2025-12-11 | 73d
e271 | Installation of DBs | Construction | 7d | 2025-11-28 | 2025-12-04 | 43d
e272 | DB Dressing and Termination | Construction | 5d | 2025-12-05 | 2025-12-09 | 43d
e273 | Delivery of LT Panels | Construction | 7d | 2025-12-25 | 2025-12-31 | 43d
e274 | Installation of LT Panels | Construction | 7d | 2026-01-01 | 2026-01-07 | 43d
e275 | Panel Testing and commissioning | Construction | 3d | 2026-01-08 | 2026-01-10 | 43d
e278 | Supply Of Battery | Construction | 7d | 2025-12-09 | 2025-12-15 | 27d
e277 | Supply Of Ups | Construction | 7d | 2026-01-08 | 2026-01-14 | 27d
e279 | Installation of UPS | Construction | 5d | 2026-01-15 | 2026-01-19 | 27d
e280 | Installation of Battery Systems | Construction | 5d | 2026-01-20 | 2026-01-24 | 27d
e281 | Testing & Commissioning of UPS | Construction | 2d | 2026-01-20 | 2026-01-21 | 27d
e282 | Testing & Commissioning of Battery | Construction | 2d | 2026-01-25 | 2026-01-26 | 27d
e284 | Installation of Switches, Raw Power Sockets | Construction | 7d | 2026-02-05 | 2026-02-11 | 11d

## Slide 12
Full activity schedule with float (9/14)
# | Activity | Phase | Dur | Start | Finish | Float
e286 | Installation of recessed lights in closed rooms | Construction | 10d | 2026-01-15 | 2026-01-24 | 29d
e287 | Installation of suspended light fixtures in w/s area | Construction | 7d | 2026-01-15 | 2026-01-21 | 32d
e288 | Installation of Decorative light fixtures | Construction | 5d | 2026-01-15 | 2026-01-19 | 34d
e289 | Testing & Commissioning of Electrical system | Construction | 3d | 2026-01-22 | 2026-01-24 | 29d
e291 | Marking & Support fixing of Ducts | Construction | 4d | 2025-10-31 | 2025-11-03 | 6d
e292 | Installation of Ducts | Construction | 10d | 2025-11-04 | 2025-11-13 | 6d
e293 | Insulation for ducts | Construction | 10d | 2025-11-14 | 2025-11-23 | 6d
e294 | Grills, Diffusers Installation | Construction | 7d | 2025-11-24 | 2025-11-30 | 6d
e295 | Installation of VAVs | Construction | 5d | 2025-12-01 | 2025-12-05 | 6d
e296 | Supply of AHU | Construction | 30d | 2025-12-19 | 2026-01-17 | 6d
e297 | Installation of AHU | Construction | 10d | 2026-01-18 | 2026-01-27 | 6d
e298 | Installation of fire Dampers, actuators | Construction | 10d | 2026-01-28 | 2026-02-06 | 6d
e299 | Acoustic insulation of AHU room | Construction | 7d | 2026-02-07 | 2026-02-13 | 6d
e300 | Fire damper control panels Installation | Construction | 7d | 2026-02-07 | 2026-02-13 | 6d
e301 | AHU dry run | Construction | 3d | 2026-02-14 | 2026-02-16 | 6d
e303 | Cable trays Installation for copper piping | Construction | 7d | 2025-10-31 | 2025-11-06 | 3d

## Slide 13
Full activity schedule with float (10/14)
# | Activity | Phase | Dur | Start | Finish | Float
e304 | Copper piping works | Construction | 10d | 2025-11-07 | 2025-11-16 | 3d
e305 | Drain Piping works | Construction | 7d | 2025-11-17 | 2025-11-23 | 3d
e306 | Installation of VRF units | Construction | 4d | 2025-11-17 | 2025-11-20 | 3d
e307 | Testing & Commissioning of HVAC system | Construction | 3d | 2026-02-17 | 2026-02-19 | 3d
e309 | Supply of Precision Air Conditioners | Construction | 15d | 2026-01-09 | 2026-01-23 | 20d
e310 | Installation of Precision Air Conditioners | Construction | 10d | 2026-01-24 | 2026-02-02 | 20d
e313 | Marking & supports fixing for fire pipes | Construction | 4d | 2025-10-13 | 2025-10-16 | 87d
e314 | Modification of existing fire pipes | Construction | 10d | 2025-10-17 | 2025-10-26 | 87d
e315 | Modification of existing sprinkler bulbs | Construction | 5d | 2025-10-27 | 2025-10-31 | 87d
e316 | Erection of MS sprinkler pipes | Construction | 10d | 2025-11-01 | 2025-11-10 | 87d
e317 | Enamel painting of pipes | Construction | 10d | 2025-11-11 | 2025-11-20 | 87d
e318 | Flexible pipes installation for below false ceiling | Construction | 7d | 2025-11-11 | 2025-11-17 | 87d
e319 | Pendent, Upright sprinkler bulbs installation | Construction | 7d | 2025-11-18 | 2025-11-24 | 87d
e320 | Testing & Commissioning of sprinkler system | Construction | 3d | 2025-11-25 | 2025-11-27 | 87d
e322 | FA Cabling on ceiling | Construction | 20d | 2025-10-17 | 2025-11-05 | 50d
e323 | FA Cabling on walls/partitions | Construction | 9d | 2025-11-06 | 2025-11-14 | 50d

## Slide 14
Full activity schedule with float (11/14)
# | Activity | Phase | Dur | Start | Finish | Float
e324 | Multi Sensor Detectors Installation | Construction | 14d | 2025-11-15 | 2025-11-28 | 50d
e325 | Heat detectors Installation | Construction | 7d | 2025-11-29 | 2025-12-05 | 50d
e326 | RI installation | Construction | 7d | 2025-12-06 | 2025-12-12 | 50d
e327 | Modules/MCP/Strobes Installation | Construction | 7d | 2025-12-13 | 2025-12-19 | 50d
e328 | Testing & Commissioning of FA system | Construction | 15d | 2025-12-20 | 2026-01-03 | 50d
e330 | PA cabling | Construction | 20d | 2025-11-23 | 2025-12-12 | 61d
e331 | Speakers Installation | Construction | 7d | 2025-12-13 | 2025-12-19 | 61d
e332 | Testing & Commissioning of PA system | Construction | 4d | 2025-12-20 | 2025-12-23 | 61d
e334 | Conduiting & Installation of raceways (ACS) | Construction | 10d | 2025-11-23 | 2025-12-02 | 61d
e335 | Cabling (ACS/CCTV) | Construction | 10d | 2025-12-03 | 2025-12-12 | 61d
e336 | Installation of ACS & CCTV devices | Construction | 7d | 2025-12-13 | 2025-12-19 | 61d
e337 | Testing and commisioning of ACS & CCTV works | Construction | 4d | 2025-12-20 | 2025-12-23 | 61d
e339 | Conduiting & Installation of Raceway (WLD) | Construction | 10d | 2025-12-12 | 2025-12-21 | 37d
e340 | Cabling (WLD) | Construction | 10d | 2025-12-22 | 2025-12-31 | 37d
e341 | Installation of WLD Devices | Construction | 7d | 2026-01-08 | 2026-01-14 | 37d
e342 | Testing and commissioning of WLD System | Construction | 2d | 2026-01-15 | 2026-01-16 | 37d

## Slide 15
Full activity schedule with float (12/14)
# | Activity | Phase | Dur | Start | Finish | Float
e344 | Conduiting & Installation of Raceway (Rodent) | Construction | 10d | 2025-12-12 | 2025-12-21 | 42d
e345 | Cabling (Rodent) | Construction | 7d | 2025-12-22 | 2025-12-28 | 42d
e346 | Installation of Rodent Repelent Devices | Construction | 5d | 2026-01-05 | 2026-01-09 | 42d
e347 | Testing and commissioning of Rodent Repelent System | Construction | 2d | 2026-01-10 | 2026-01-11 | 42d
e349 | Supply of Gas Based Supression System | Construction | 10d | 2025-12-12 | 2025-12-21 | 39d
e350 | Installation of Gas Based Supression System | Construction | 7d | 2026-01-06 | 2026-01-12 | 39d
e351 | Testing and commissioning (gas suppression) | Construction | 2d | 2026-01-13 | 2026-01-14 | 39d
e353 | Cable laying | Construction | 30d | 2025-10-25 | 2025-11-23 | 18d
e354 | I/O port terminations | Construction | 10d | 2026-01-26 | 2026-02-04 | 18d
e356 | Supply of Fiber Cables | Construction | 15d | 2025-12-25 | 2026-01-08 | 25d
e357 | Supply of Backbone Cables | Construction | 10d | 2026-01-09 | 2026-01-18 | 25d
e358 | Supply of Network Racks | Construction | 10d | 2026-01-09 | 2026-01-18 | 25d
e359 | Cables Installation | Construction | 10d | 2026-01-09 | 2026-01-18 | 25d
e360 | Server Room Readiness | Construction | 5d | 2026-01-19 | 2026-01-23 | 25d
e361 | Network Rack Installation | Construction | 7d | 2026-01-19 | 2026-01-25 | 25d
e362 | Testing and Commissioning (networking) | Construction | 3d | 2026-01-26 | 2026-01-28 | 25d

## Slide 16
Full activity schedule with float (13/14)
# | Activity | Phase | Dur | Start | Finish | Float
e364 | AV Cabling | Construction | 10d | 2026-02-01 | 2026-02-10 | 2d
e365 | AV Systems delivery | Construction | 5d | 2026-02-11 | 2026-02-15 | 2d
e366 | AV Systems Installation | Construction | 5d | 2026-02-16 | 2026-02-20 | 2d
e368 | Supply of White Goods | Construction | 2d | 2026-02-12 | 2026-02-13 | 2d
e369 | Installation of White Goods | Construction | 3d | 2026-02-18 | 2026-02-20 | 2d
e371 | Marking of workstations, meeting room tables | Construction | 4d | 2025-11-13 | 2025-11-16 | 16d
e372 | Workstation frame, meeting room table installation | Construction | 25d | 2025-12-17 | 2026-01-10 | 16d
e373 | Routing of power, data cables & socket fixing | Construction | 15d | 2026-01-11 | 2026-01-25 | 16d
e374 | Fixing of table top, panels for workstations | Construction | 10d | 2026-01-26 | 2026-02-04 | 16d
e375 | Alignment of workstations, meeting room tables | Construction | 2d | 2026-02-05 | 2026-02-06 | 16d
e377 | Site Measurement for Modular Cubicle | Construction | 3d | 2025-12-24 | 2025-12-26 | 35d
e378 | Cubicle Material Delivery | Construction | 3d | 2025-12-27 | 2025-12-29 | 35d
e379 | Cubicle Installation | Construction | 20d | 2025-12-30 | 2026-01-18 | 35d
e381 | Delivery of Loose furniture | Construction | 10d | 2026-01-28 | 2026-02-06 | 3d
e383 | Supply & Installation of Lockers | Construction | 7d | 2026-01-30 | 2026-02-05 | 3d
e382 | Installation of Loose furniture | Construction | 3d | 2026-02-07 | 2026-02-09 | 3d

## Slide 17
Full activity schedule with float (14/14)
# | Activity | Phase | Dur | Start | Finish | Float
e384 | Supply of Chairs Materials | Construction | 7d | 2026-02-13 | 2026-02-19 | 3d
e385 | Installation Chairs | Construction | 7d | 2026-02-13 | 2026-02-19 | 3d
e387 | Signages Supply and Installation | Construction | 3d | 2026-02-05 | 2026-02-07 | 0d
e388 | Branding (Logo) | Construction | 3d | 2026-02-17 | 2026-02-19 | 0d
e392 | Deep Cleaning | Construction | 5d | 2026-02-18 | 2026-02-22 | 0d
e390 | Fire exit signages Installation | Construction | 4d | 2026-02-19 | 2026-02-22 | 0d
e391 | Fire evacuation maps Installation | Construction | 4d | 2026-02-19 | 2026-02-22 | 0d
e389 | Fire extinguishers Installation | Construction | 3d | 2026-02-20 | 2026-02-22 | 0d

## Slide 18
Design tracker — GFC / MEP / Sampling (1/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
GFC | GFC | Base Build Layout | Very Critical | 2025-09-20 | Delayed | 2025-09-25 | Delayed
GFC | GFC | Furniture Layout | Very Critical | 2025-12-16 | Delayed | 2025-12-23 | Delayed
GFC | GFC | Furniture Dimensions Layout | High | 2025-12-18 | Delayed | 2025-12-23 | Delayed
GFC | GFC | Partition Layout | Very Critical | 2025-10-04 | Delayed | 2025-10-09 | Delayed
GFC | GFC | Flooring Layout | High | 2025-10-18 | Delayed | 2025-10-23 | Delayed
GFC | GFC | Floor Marking Layout | Medium | 2025-10-19 | Delayed | 2025-10-23 | Delayed
GFC | GFC | Raised Flooring Layout | High | 2025-10-18 | Delayed | 2025-10-23 | Delayed
GFC | GFC | Door Schedule Layout | High | 2025-10-09 | Delayed | 2025-10-14 | Delayed
GFC | GFC | Wall Finishes Layout | High | 2025-11-01 | Delayed | 2025-11-06 | Delayed
GFC | GFC | Modular Layout | Very Critical | 2025-12-16 | Delayed | 2025-12-23 | Delayed
GFC | GFC | RCP Layout | Very Critical | 2025-10-09 | Delayed | 2025-10-16 | Delayed
GFC | GFC | Lighting Layout (with dimensions) | Very Critical | 2025-10-16 | Delayed | 2025-10-23 | Delayed
GFC | GENERAL | Wallpaper & Graphics | Low | 2025-07-03 | Delayed | 2025-07-08 | Delayed
GFC | GENERAL | Fire Evacuation Plan | Medium | 2025-07-01 | Delayed | 2025-07-06 | Delayed
GFC | 3D | 3D Views — Detailed & Client Approval | Very Critical | 2025-09-29 | Delayed | 2025-10-09 | Delayed

## Slide 19
Design tracker — GFC / MEP / Sampling (2/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
MEP | MEP | Electrical DBR | Very Critical | 2025-10-18 | Delayed | 2025-10-23 | Delayed
MEP | MEP | Electrical SLD Layout | Very Critical | 2025-10-16 | Delayed | 2025-10-23 | Delayed
MEP | MEP | Electrical Load Calculation | Very Critical | 2025-10-16 | Delayed | 2025-10-23 | Delayed
MEP | MEP | Power, Data & Switch Board Layout | Very Critical | 2025-10-16 | Delayed | 2025-10-23 | Delayed
MEP | MEP | Raceway Layout | Very Critical | 2025-10-18 | Delayed | 2025-10-23 | Delayed
MEP | MEP | Cable Tray Layout | High | 2025-10-18 | Delayed | 2025-10-23 | Delayed
MEP | MEP | Lighting Looping Layout | High | 2025-10-18 | Delayed | 2025-10-23 | Delayed
MEP | MEP | Panel & DB Position Layout | High | 2025-10-18 | Delayed | 2025-10-23 | Delayed
MEP | MEP | UPS Calculation & Specification | High | 2025-10-16 | Delayed | 2025-10-23 | Delayed
MEP | MEP | HVAC DBR | Very Critical | 2025-10-25 | Delayed | 2025-10-30 | Delayed
MEP | MEP | HVAC Heat Load | Very Critical | 2025-10-23 | Delayed | 2025-10-30 | Delayed
MEP | MEP | HVAC Layout | Very Critical | 2025-10-23 | Delayed | 2025-10-30 | Delayed
MEP | MEP | PHE DBR & Plumbing Layout | High | 2025-10-08 | Delayed | 2025-10-13 | Delayed
MEP | MEP | Fire Sprinkler Layout | Very Critical | 2025-10-02 | Delayed | 2025-10-12 | Delayed
MEP | MEP | FA / PA System Layout | High | 2025-11-13 | Delayed | 2025-11-20 | Delayed

## Slide 20
Design tracker — GFC / MEP / Sampling (3/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
MEP | MEP | ACS / CCTV / WiFi Layout | High | 2025-11-13 | Delayed | 2025-11-20 | Delayed
MEP | MEP | LV DBR | High | 2025-11-15 | Delayed | 2025-11-20 | Delayed
SAMPLING | Finishes | Floor and Dado Tiles — Reception & Lounge | High | 2025-10-18 | Delayed | 2025-10-23 | Delayed
SAMPLING | Finishes | Floor and Dado Tiles — Workstations | High | 2025-10-18 | Delayed | 2025-10-23 | Delayed
SAMPLING | Finishes | Floor and Dado Tiles — Cabins & Meeting Rooms | High | 2025-10-18 | Delayed | 2025-10-23 | Delayed
SAMPLING | Finishes | Floor and Dado Tiles — Boardroom | High | 2025-10-18 | Delayed | 2025-10-23 | Delayed
SAMPLING | Finishes | Floor and Dado Tiles — Cafeteria & Pantry | High | 2025-10-18 | Delayed | 2025-10-23 | Delayed
SAMPLING | Finishes | Floor and Dado Tiles — Toilets | High | 2025-10-18 | Delayed | 2025-10-23 | Delayed
SAMPLING | Finishes | Floor and Dado Tiles — Support & Server | High | 2025-10-18 | Delayed | 2025-10-23 | Delayed
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Reception & Lounge | High | 2025-10-09 | Delayed | 2025-10-14 | Delayed
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Workstations | High | 2025-10-09 | Delayed | 2025-10-14 | Delayed
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Cabins & Meeting Rooms | High | 2025-10-09 | Delayed | 2025-10-14 | Delayed
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Boardroom | High | 2025-10-09 | Delayed | 2025-10-14 | Delayed
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Cafeteria & Pantry | High | 2025-10-09 | Delayed | 2025-10-14 | Delayed
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Toilets | High | 2025-10-09 | Delayed | 2025-10-14 | Delayed

## Slide 21
Design tracker — GFC / MEP / Sampling (4/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Support & Server | High | 2025-10-09 | Delayed | 2025-10-14 | Delayed
SAMPLING | Finishes | Paint Shades — Reception & Lounge | Medium | 2025-11-01 | Delayed | 2025-11-06 | Delayed
SAMPLING | Finishes | Paint Shades — Workstations | Medium | 2025-11-01 | Delayed | 2025-11-06 | Delayed
SAMPLING | Finishes | Paint Shades — Cabins & Meeting Rooms | Medium | 2025-11-01 | Delayed | 2025-11-06 | Delayed
SAMPLING | Finishes | Paint Shades — Boardroom | Medium | 2025-11-01 | Delayed | 2025-11-06 | Delayed
SAMPLING | Finishes | Paint Shades — Cafeteria & Pantry | Medium | 2025-11-01 | Delayed | 2025-11-06 | Delayed
SAMPLING | Finishes | Paint Shades — Toilets | Medium | 2025-11-01 | Delayed | 2025-11-06 | Delayed
SAMPLING | Finishes | Paint Shades — Support & Server | Medium | 2025-11-01 | Delayed | 2025-11-06 | Delayed
SAMPLING | Finishes | Carpet / SPC Flooring — Reception & Lounge | High | 2025-10-16 | Delayed | 2025-10-23 | Delayed
SAMPLING | Finishes | Carpet / SPC Flooring — Workstations | High | 2025-10-16 | Delayed | 2025-10-23 | Delayed
SAMPLING | Finishes | Carpet / SPC Flooring — Cabins & Meeting Rooms | High | 2025-10-16 | Delayed | 2025-10-23 | Delayed
SAMPLING | Finishes | Carpet / SPC Flooring — Boardroom | High | 2025-10-16 | Delayed | 2025-10-23 | Delayed
SAMPLING | Finishes | Carpet / SPC Flooring — Cafeteria & Pantry | High | 2025-10-16 | Delayed | 2025-10-23 | Delayed
SAMPLING | Finishes | Carpet / SPC Flooring — Toilets | High | 2025-10-16 | Delayed | 2025-10-23 | Delayed
SAMPLING | Finishes | Carpet / SPC Flooring — Support & Server | High | 2025-10-16 | Delayed | 2025-10-23 | Delayed

## Slide 22
Design tracker — GFC / MEP / Sampling (5/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
SAMPLING | Partitions | Demountable Glass Partition | Very Critical | 2025-12-30 | Delayed | 2026-01-06 | Delayed
SAMPLING | Partitions | Backpainted Glass | Medium | 2026-01-01 | Delayed | 2026-01-06 | Delayed
SAMPLING | Ceiling | Grid & Stretch Ceiling — Reception & Lounge | High | 2025-10-09 | Delayed | 2025-10-16 | Delayed
SAMPLING | Ceiling | Grid & Stretch Ceiling — Workstations | High | 2025-10-09 | Delayed | 2025-10-16 | Delayed
SAMPLING | Ceiling | Grid & Stretch Ceiling — Cabins & Meeting Rooms | High | 2025-10-09 | Delayed | 2025-10-16 | Delayed
SAMPLING | Ceiling | Grid & Stretch Ceiling — Boardroom | High | 2025-10-09 | Delayed | 2025-10-16 | Delayed
SAMPLING | Ceiling | Grid & Stretch Ceiling — Cafeteria & Pantry | High | 2025-10-09 | Delayed | 2025-10-16 | Delayed
SAMPLING | Ceiling | Grid & Stretch Ceiling — Toilets | High | 2025-10-09 | Delayed | 2025-10-16 | Delayed
SAMPLING | Ceiling | Grid & Stretch Ceiling — Support & Server | High | 2025-10-09 | Delayed | 2025-10-16 | Delayed
SAMPLING | Ceiling | Acoustics / Fluted Panel — Reception & Lounge | Medium | 2025-10-11 | Delayed | 2025-10-16 | Delayed
SAMPLING | Ceiling | Acoustics / Fluted Panel — Workstations | Medium | 2025-10-11 | Delayed | 2025-10-16 | Delayed
SAMPLING | Ceiling | Acoustics / Fluted Panel — Cabins & Meeting Rooms | Medium | 2025-10-11 | Delayed | 2025-10-16 | Delayed
SAMPLING | Ceiling | Acoustics / Fluted Panel — Boardroom | Medium | 2025-10-11 | Delayed | 2025-10-16 | Delayed
SAMPLING | Ceiling | Acoustics / Fluted Panel — Cafeteria & Pantry | Medium | 2025-10-11 | Delayed | 2025-10-16 | Delayed
SAMPLING | Ceiling | Acoustics / Fluted Panel — Toilets | Medium | 2025-10-11 | Delayed | 2025-10-16 | Delayed

## Slide 23
Design tracker — GFC / MEP / Sampling (6/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
SAMPLING | Ceiling | Acoustics / Fluted Panel — Support & Server | Medium | 2025-10-11 | Delayed | 2025-10-16 | Delayed
SAMPLING | MEP | Switch Sockets | Medium | 2025-10-18 | Delayed | 2025-10-23 | Delayed
SAMPLING | MEP | Decorative Lights | High | 2025-10-16 | Delayed | 2025-10-23 | Delayed
SAMPLING | MEP | Sanitary Fixtures | Medium | 2025-10-08 | Delayed | 2025-10-13 | Delayed
SAMPLING | Furniture | Chairs & Loose Furniture | High | 2025-12-16 | Delayed | 2025-12-23 | Delayed
SAMPLING | Finishes | Blinds | Medium | 2025-07-03 | Delayed | 2025-07-08 | Delayed
SAMPLING | Finishes | Skirting & T Profile | Low | 2025-07-01 | Delayed | 2025-07-05 | Delayed
GFC | TD | TD — Civil & Interior | Very Critical | 2025-10-04 | Delayed | 2025-10-09 | Delayed
GFC | TD | TD — Soft Cost (furniture & furnishing) | Very Critical | 2025-12-18 | Delayed | 2025-12-23 | Delayed
GFC | Elevations | Elevation — Reception & Lounge | High | 2025-10-04 | Delayed | 2025-10-09 | Delayed
GFC | Elevations | Elevation — Workstations | High | 2025-10-04 | Delayed | 2025-10-09 | Delayed
GFC | Elevations | Elevation — Cabins & Meeting Rooms | High | 2025-10-04 | Delayed | 2025-10-09 | Delayed
GFC | Elevations | Elevation — Boardroom | High | 2025-10-04 | Delayed | 2025-10-09 | Delayed
GFC | Elevations | Elevation — Cafeteria & Pantry | High | 2025-10-04 | Delayed | 2025-10-09 | Delayed
GFC | Elevations | Elevation — Toilets | High | 2025-10-04 | Delayed | 2025-10-09 | Delayed

## Slide 24
Design tracker — GFC / MEP / Sampling (7/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
GFC | Elevations | Elevation — Support & Server | High | 2025-10-04 | Delayed | 2025-10-09 | Delayed

## Slide 25
Procurement — order-by and delivery required
Category | Sub | Criticality | Order by | Delivery required | Order status | Gated by
Civil & Interior | default | Medium | 2025-09-03 | 2025-09-24 | Open | Base Build Layout (client approval 2025-09-25)
Soft Cost (furniture & furnishing) | default | Medium | 2025-12-01 | 2025-12-22 | Open | Furniture Layout (client approval 2025-12-23)
Electrical Works | default | Medium | 2025-10-01 | 2025-10-22 | Open | Lighting Layout (with dimensions) (client approval 2025-10-23)
HVAC | default | Medium | 2025-10-08 | 2025-10-29 | Open | HVAC DBR (client approval 2025-10-30)
Wet Works (PHE) | default | Medium | 2025-09-21 | 2025-10-12 | Open | PHE DBR & Plumbing Layout (client approval 2025-10-13)
Passive Networking | default | Medium | 2025-10-29 | 2025-11-19 | Open | FA / PA System Layout (client approval 2025-11-20)
Fire Fighting and Safety | default | Medium | 2025-09-20 | 2025-10-11 | Open | Fire Sprinkler Layout (client approval 2025-10-12)
UPS | default | Medium | — | — | Open | —
Surveillance | default | Medium | — | — | Open | —
Miscellaneous | default | Medium | 2025-06-27 | 2025-07-18 | Open | —

## Slide 26
Manpower — levelled contractor gangs
Trade | From | To | Days | Man-days | Core gang | Peak
carpentry | 2025-10-15 | 2026-02-06 | 115 | 1920 | 16 | 16
ceiling | 2025-10-17 | 2026-01-24 | 100 | 1232 | 13 | 14
civil | 2025-09-26 | 2025-10-21 | 26 | 288 | 12 | 15
cleaning | 2025-09-27 | 2026-02-22 | 149 | 160 | 6 | 9
electrical | 2025-10-24 | 2026-02-11 | 111 | 1810 | 14 | 14
flooring | 2025-10-24 | 2026-02-08 | 108 | 942 | 9 | 14
general | 2025-06-23 | 2026-02-22 | 245 | 2116 | 8 | 8
glass | 2026-01-07 | 2026-02-09 | 34 | 125 | 4 | 4
hvac | 2025-10-31 | 2026-02-19 | 112 | 1080 | 10 | 12
lv | 2025-11-21 | 2026-02-20 | 92 | 708 | 8 | 10
modular | 2025-12-24 | 2026-02-19 | 58 | 360 | 7 | 9
painting | 2025-11-07 | 2026-02-13 | 99 | 1088 | 11 | 14
partition | 2025-10-10 | 2026-02-09 | 123 | 1430 | 12 | 15
plumbing | 2025-10-14 | 2025-11-19 | 37 | 148 | 4 | 4
sprinkler | 2025-10-13 | 2026-02-22 | 133 | 415 | 4 | 5

## Slide 27
RA billing milestones — readiness against site progress
MILESTONES
6
CLAUSES TRACKED
24
CONTRACT VALUE
INR 23,95,00,000
RA | Due | % | Amount | Clauses | Status
RA1 | 2025-06-23 | 0% | INR 0 | 3 | Delayed
RA2 | 2025-08-22 | 15% | INR 3,59,25,000 | 4 | Delayed
RA3 | 2025-10-11 | 20% | INR 4,79,00,000 | 5 | Delayed
RA4 | 2025-11-30 | 25% | INR 5,98,75,000 | 4 | Delayed
RA5 | 2026-01-14 | 25% | INR 5,98,75,000 | 4 | Delayed
RA6 | 2026-02-23 | 15% | INR 3,59,25,000 | 4 | Delayed

## Slide 28
RA milestone clauses — what must be true before billing (1/2)
RA | Kind | Clause | Planned | Status
RA1 | execution | Mobilisation | 2025-07-26 | Delayed
RA1 | execution | Kick-off | 2025-06-23 | Delayed
RA1 | execution | PO release | 2025-06-23 | Delayed
RA2 | execution | Design freeze | 2025-08-22 | Delayed
RA2 | execution | Liaisoning approvals (BMC | 2025-08-22 | Delayed
RA2 | execution | Fire NOC) | 2026-01-07 | Delayed
RA2 | execution | Site mobilisation | 2025-07-26 | Delayed
RA3 | execution | Civil | 2025-10-11 | Delayed
RA3 | execution | Dry-wall partitions | 2025-12-01 | Delayed
RA3 | execution | MEP first fix | 2025-10-11 | Delayed
RA3 | execution | Raceways | 2025-12-02 | Delayed
RA3 | execution | Conduiting | 2025-11-02 | Delayed
RA4 | execution | Ceilings | 2025-11-30 | Delayed
RA4 | execution | Flooring | 2025-10-30 | Delayed
RA4 | execution | Second fix MEP | 2025-10-27 | Delayed
RA4 | execution | Glass partitions | 2025-12-01 | Delayed

## Slide 29
RA milestone clauses — what must be true before billing (2/2)
RA | Kind | Clause | Planned | Status
RA5 | execution | Painting | 2025-11-20 | Delayed
RA5 | execution | Wall finishes | 2025-11-21 | Delayed
RA5 | execution | Modular furniture | 2025-12-01 | Delayed
RA5 | execution | Commissioning | 2025-11-19 | Delayed
RA6 | execution | Snagging | 2026-02-23 | Delayed
RA6 | execution | Deep cleaning | 2026-02-22 | Delayed
RA6 | execution | Handover | 2026-02-23 | Delayed
RA6 | execution | Close-out documents | 2026-02-23 | Delayed

## Slide 30
Resource plan
Role | Count | Basis
Project Manager | 1 | ceil(33000 sft / 40000) per norms-v1:resourceRoleNorms
Site Engineer (Civil/Interior) | 3 | ceil(33000 sft / 12000) per norms-v1:resourceRoleNorms
MEP Engineer | 2 | ceil(33000 sft / 25000) per norms-v1:resourceRoleNorms
Design Lead | 1 | ceil(33000 sft / 40000) per norms-v1:resourceRoleNorms
Procurement Owner | 1 | ceil(33000 sft / 40000) per norms-v1:resourceRoleNorms
Safety Officer | 2 | ceil(33000 sft / 30000) per norms-v1:resourceRoleNorms
QC / Snag Engineer | 2 | ceil(33000 sft / 30000) per norms-v1:resourceRoleNorms

## Slide 31
To-do list — next 21 days (1/8)
End date | Responsibility | Description | Priority | Status
2025-06-20 | Project head | Project resource allocation confirmed (PM, site engineer, MEP, design, procurement) | HIGH | Delayed
2025-06-21 | Project head | Project tool creation — tracker, folder structure and access | MEDIUM | Delayed
2025-06-22 | Project head | Client WhatsApp group creation with the agreed participants | MEDIUM | Delayed
2025-06-23 | Project head | Wispr onboarding for the project team | MEDIUM | Delayed
2025-06-23 | Project head | Welcome email issued to the client with team and escalation matrix | MEDIUM | Delayed
2025-06-24 | Site engineer | Site verification against the GFC layout | HIGH | Delayed
2025-06-24 | Site engineer | Building permissions, gate pass and work permits obtained | HIGH | Delayed
2025-06-24 | Site engineer | Day-0 site photographs and dilapidation record filed | MEDIUM | Delayed
2025-06-25 | Site engineer | Site marking completed and signed off | HIGH | Delayed
2025-06-25 | Site engineer | Labour onboarding, ID cards and safety induction | HIGH | Delayed
2025-06-26 | Project head | Kick-off meeting with the client and consultants | HIGH | Delayed
2025-06-27 | Site engineer | Temporary power, water and site lighting arranged | HIGH | Delayed
2025-06-27 | Procurement | Release PO: Miscellaneous | MEDIUM | Delayed
2025-07-01 | Design lead | Issue for approval: Fire Evacuation Plan | MEDIUM | Delayed
2025-07-01 | Design lead | Issue for approval: Skirting & T Profile | MEDIUM | Delayed

## Slide 32
To-do list — next 21 days (2/8)
End date | Responsibility | Description | Priority | Status
2025-07-03 | Design lead | Issue for approval: Wallpaper & Graphics | MEDIUM | Delayed
2025-07-03 | Design lead | Issue for approval: Blinds | MEDIUM | Delayed
2025-09-03 | Procurement | Release PO: Civil & Interior | MEDIUM | Delayed
2025-09-20 | Procurement | Release PO: Fire Fighting and Safety | MEDIUM | Delayed
2025-09-20 | Design lead | Issue for approval: Base Build Layout | HIGH | Delayed
2025-09-21 | Procurement | Release PO: Wet Works (PHE) | MEDIUM | Delayed
2025-09-29 | Design lead | Issue for approval: 3D Views — Detailed & Client Approval | HIGH | Delayed
2025-10-01 | Procurement | Release PO: Electrical Works | MEDIUM | Delayed
2025-10-02 | MEP design lead | Issue for approval: Fire Sprinkler Layout | HIGH | Delayed
2025-10-04 | Design lead | Issue for approval: Partition Layout | HIGH | Delayed
2025-10-04 | Design lead | Issue for approval: TD — Civil & Interior | HIGH | Delayed
2025-10-04 | Design lead | Issue for approval: Elevation — Reception & Lounge | HIGH | Delayed
2025-10-04 | Design lead | Issue for approval: Elevation — Workstations | HIGH | Delayed
2025-10-04 | Design lead | Issue for approval: Elevation — Cabins & Meeting Rooms | HIGH | Delayed
2025-10-04 | Design lead | Issue for approval: Elevation — Boardroom | HIGH | Delayed

## Slide 33
To-do list — next 21 days (3/8)
End date | Responsibility | Description | Priority | Status
2025-10-04 | Design lead | Issue for approval: Elevation — Cafeteria & Pantry | HIGH | Delayed
2025-10-04 | Design lead | Issue for approval: Elevation — Toilets | HIGH | Delayed
2025-10-04 | Design lead | Issue for approval: Elevation — Support & Server | HIGH | Delayed
2025-10-08 | Procurement | Release PO: HVAC | MEDIUM | Delayed
2025-10-08 | MEP design lead | Issue for approval: PHE DBR & Plumbing Layout | HIGH | Delayed
2025-10-08 | Design lead | Issue for approval: Sanitary Fixtures | MEDIUM | Delayed
2025-10-09 | Design lead | Issue for approval: Door Schedule Layout | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: RCP Layout | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: Carpentry Laminates & Veneer Shades — Reception & Lounge | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: Carpentry Laminates & Veneer Shades — Workstations | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: Carpentry Laminates & Veneer Shades — Cabins & Meeting Rooms | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: Carpentry Laminates & Veneer Shades — Boardroom | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: Carpentry Laminates & Veneer Shades — Cafeteria & Pantry | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: Carpentry Laminates & Veneer Shades — Toilets | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: Carpentry Laminates & Veneer Shades — Support & Server | HIGH | Delayed

## Slide 34
To-do list — next 21 days (4/8)
End date | Responsibility | Description | Priority | Status
2025-10-09 | Design lead | Issue for approval: Grid & Stretch Ceiling — Reception & Lounge | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: Grid & Stretch Ceiling — Workstations | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: Grid & Stretch Ceiling — Cabins & Meeting Rooms | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: Grid & Stretch Ceiling — Boardroom | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: Grid & Stretch Ceiling — Cafeteria & Pantry | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: Grid & Stretch Ceiling — Toilets | HIGH | Delayed
2025-10-09 | Design lead | Issue for approval: Grid & Stretch Ceiling — Support & Server | HIGH | Delayed
2025-10-11 | Design lead | Issue for approval: Acoustics / Fluted Panel — Reception & Lounge | MEDIUM | Delayed
2025-10-11 | Design lead | Issue for approval: Acoustics / Fluted Panel — Workstations | MEDIUM | Delayed
2025-10-11 | Design lead | Issue for approval: Acoustics / Fluted Panel — Cabins & Meeting Rooms | MEDIUM | Delayed
2025-10-11 | Design lead | Issue for approval: Acoustics / Fluted Panel — Boardroom | MEDIUM | Delayed
2025-10-11 | Design lead | Issue for approval: Acoustics / Fluted Panel — Cafeteria & Pantry | MEDIUM | Delayed
2025-10-11 | Design lead | Issue for approval: Acoustics / Fluted Panel — Toilets | MEDIUM | Delayed
2025-10-11 | Design lead | Issue for approval: Acoustics / Fluted Panel — Support & Server | MEDIUM | Delayed
2025-10-16 | Design lead | Issue for approval: Lighting Layout (with dimensions) | HIGH | Delayed

## Slide 35
To-do list — next 21 days (5/8)
End date | Responsibility | Description | Priority | Status
2025-10-16 | MEP design lead | Issue for approval: Electrical SLD Layout | HIGH | Delayed
2025-10-16 | MEP design lead | Issue for approval: Electrical Load Calculation | HIGH | Delayed
2025-10-16 | MEP design lead | Issue for approval: Power, Data & Switch Board Layout | HIGH | Delayed
2025-10-16 | MEP design lead | Issue for approval: UPS Calculation & Specification | HIGH | Delayed
2025-10-16 | Design lead | Issue for approval: Carpet / SPC Flooring — Reception & Lounge | HIGH | Delayed
2025-10-16 | Design lead | Issue for approval: Carpet / SPC Flooring — Workstations | HIGH | Delayed
2025-10-16 | Design lead | Issue for approval: Carpet / SPC Flooring — Cabins & Meeting Rooms | HIGH | Delayed
2025-10-16 | Design lead | Issue for approval: Carpet / SPC Flooring — Boardroom | HIGH | Delayed
2025-10-16 | Design lead | Issue for approval: Carpet / SPC Flooring — Cafeteria & Pantry | HIGH | Delayed
2025-10-16 | Design lead | Issue for approval: Carpet / SPC Flooring — Toilets | HIGH | Delayed
2025-10-16 | Design lead | Issue for approval: Carpet / SPC Flooring — Support & Server | HIGH | Delayed
2025-10-16 | Design lead | Issue for approval: Decorative Lights | HIGH | Delayed
2025-10-18 | Design lead | Issue for approval: Flooring Layout | HIGH | Delayed
2025-10-18 | Design lead | Issue for approval: Raised Flooring Layout | HIGH | Delayed
2025-10-18 | MEP design lead | Issue for approval: Electrical DBR | HIGH | Delayed

## Slide 36
To-do list — next 21 days (6/8)
End date | Responsibility | Description | Priority | Status
2025-10-18 | MEP design lead | Issue for approval: Raceway Layout | HIGH | Delayed
2025-10-18 | MEP design lead | Issue for approval: Cable Tray Layout | HIGH | Delayed
2025-10-18 | MEP design lead | Issue for approval: Lighting Looping Layout | HIGH | Delayed
2025-10-18 | MEP design lead | Issue for approval: Panel & DB Position Layout | HIGH | Delayed
2025-10-18 | Design lead | Issue for approval: Floor and Dado Tiles — Reception & Lounge | HIGH | Delayed
2025-10-18 | Design lead | Issue for approval: Floor and Dado Tiles — Workstations | HIGH | Delayed
2025-10-18 | Design lead | Issue for approval: Floor and Dado Tiles — Cabins & Meeting Rooms | HIGH | Delayed
2025-10-18 | Design lead | Issue for approval: Floor and Dado Tiles — Boardroom | HIGH | Delayed
2025-10-18 | Design lead | Issue for approval: Floor and Dado Tiles — Cafeteria & Pantry | HIGH | Delayed
2025-10-18 | Design lead | Issue for approval: Floor and Dado Tiles — Toilets | HIGH | Delayed
2025-10-18 | Design lead | Issue for approval: Floor and Dado Tiles — Support & Server | HIGH | Delayed
2025-10-18 | Design lead | Issue for approval: Switch Sockets | MEDIUM | Delayed
2025-10-19 | Design lead | Issue for approval: Floor Marking Layout | MEDIUM | Delayed
2025-10-23 | MEP design lead | Issue for approval: HVAC Heat Load | HIGH | Delayed
2025-10-23 | MEP design lead | Issue for approval: HVAC Layout | HIGH | Delayed

## Slide 37
To-do list — next 21 days (7/8)
End date | Responsibility | Description | Priority | Status
2025-10-25 | MEP design lead | Issue for approval: HVAC DBR | HIGH | Delayed
2025-10-29 | Procurement | Release PO: Passive Networking | MEDIUM | Delayed
2025-11-01 | Design lead | Issue for approval: Wall Finishes Layout | HIGH | Delayed
2025-11-01 | Design lead | Issue for approval: Paint Shades — Reception & Lounge | MEDIUM | Delayed
2025-11-01 | Design lead | Issue for approval: Paint Shades — Workstations | MEDIUM | Delayed
2025-11-01 | Design lead | Issue for approval: Paint Shades — Cabins & Meeting Rooms | MEDIUM | Delayed
2025-11-01 | Design lead | Issue for approval: Paint Shades — Boardroom | MEDIUM | Delayed
2025-11-01 | Design lead | Issue for approval: Paint Shades — Cafeteria & Pantry | MEDIUM | Delayed
2025-11-01 | Design lead | Issue for approval: Paint Shades — Toilets | MEDIUM | Delayed
2025-11-01 | Design lead | Issue for approval: Paint Shades — Support & Server | MEDIUM | Delayed
2025-11-13 | MEP design lead | Issue for approval: FA / PA System Layout | HIGH | Delayed
2025-11-13 | MEP design lead | Issue for approval: ACS / CCTV / WiFi Layout | HIGH | Delayed
2025-11-15 | MEP design lead | Issue for approval: LV DBR | HIGH | Delayed
2025-12-01 | Procurement | Release PO: Soft Cost (furniture & furnishing) | MEDIUM | Delayed
2025-12-16 | Design lead | Issue for approval: Furniture Layout | HIGH | Delayed

## Slide 38
To-do list — next 21 days (8/8)
End date | Responsibility | Description | Priority | Status
2025-12-16 | Design lead | Issue for approval: Modular Layout | HIGH | Delayed
2025-12-16 | Design lead | Issue for approval: Chairs & Loose Furniture | HIGH | Delayed
2025-12-18 | Design lead | Issue for approval: Furniture Dimensions Layout | HIGH | Delayed
2025-12-18 | Design lead | Issue for approval: TD — Soft Cost (furniture & furnishing) | HIGH | Delayed
2025-12-30 | Design lead | Issue for approval: Demountable Glass Partition | HIGH | Delayed
2026-01-01 | Design lead | Issue for approval: Backpainted Glass | MEDIUM | Delayed

## Slide 39
Client / builder open points (1/2)
Sr | Area | Description | Responsibility | Plan date | Status
1 | Kick Off | Site kick-off meeting and pooja | Client/FS | 2025-06-23 | Delayed
2 | Commercial | Project PO / signed agreement | Client | 2025-06-23 | Delayed
3 | Commercial | Project advance payment | Client | 2025-06-30 | Delayed
4 | Design | Layout approval | Client | 2025-09-16 | Delayed
5 | Design | 3D approvals | Client | 2025-09-30 | Delayed
6 | Design | Material sampling approval | Client/FS | 2025-10-14 | Delayed
7 | Design | MEP drawings approval | Client/PMC | 2025-10-10 | Delayed
8 | Design | Electrical / IT requirement and load confirmation | Client | 2025-10-10 | Delayed
9 | Operation | Builder permissions and mobilisation clearance | FS/Builder | 2025-09-19 | Delayed
10 | Operation | Mathadi clearance | FS | 2025-09-19 | Delayed
11 | Operation | Fire NOC / CFO approval | FS/Builder | 2025-09-29 | Delayed
12 | Operation | BMC / statutory approval | FS/Builder | 2025-09-12 | Delayed
13 | Operation | Temporary power and water availability | Builder | 2025-10-19 | Delayed
14 | Operation | Lift availability for material movement | Builder | 2025-09-23 | Delayed
15 | Operation | Work hours clarity in building | Builder | 2025-09-23 | Delayed

## Slide 40
Client / builder open points (2/2)
Sr | Area | Description | Responsibility | Plan date | Status
16 | Operation | Heat load approval / CFM availability | Builder | 2025-10-17 | Delayed
17 | Operation | Wi-Fi and access point locations | Client | 2025-11-11 | Delayed
18 | Operation | Modular vendor closure for site marking | Client | 2025-12-10 | Delayed
19 | Design/Operation | Client-supplied items (IT / AV) delivery | Client | 2025-11-11 | Delayed
20 | Operation | Store space and debris removal area | Builder | 2025-09-23 | Delayed

## Slide 41
Assumptions, gaps and risks
Area | Note | Visibility
manpower | carpentry: 1920 man-days across 115 working days needs 17 workers, above the 16 cap. Extend the window, split the front, or raise the cap in Settings. | internal only
manpower | electrical: 1810 man-days across 111 working days needs 17 workers, above the 14 cap. Extend the window, split the front, or raise the cap in Settings. | internal only
manpower | general: 2116 man-days across 245 working days needs 9 workers, above the 8 cap. Extend the window, split the front, or raise the cap in Settings. | internal only
manpower | Manpower curve is peaky (average 62 vs peak 130). Consider re-sequencing overlapping trades. | internal only
procurement | Package "UPS" has no mapped site activity; order-by date not computed. | internal only
procurement | Package "Surveillance" has no mapped site activity; order-by date not computed. | internal only