## Slide 1
INTERNAL — NOT FOR CLIENT ISSUE
KOHLER OS, Pune
Kohler India Corporation Pvt. Ltd. · 7th Floor (7A), ITC, Pune
Execution Plan · confidence 98% · norms norms-v1
DnB Planning Engine v1.0.0

## Slide 2
Position
INTERNAL TARGET
2026-11-03
120 wd (CPM)
CONTRACT FINISH
2026-11-04
BUFFER
1d
invariant holds
CRITICAL
30 / 66
zero float
PEAK MANPOWER
72
2026-09-25
MARGIN
—
6 RA milestones
Confidence basis: 9/9 inputs provided; 1/19 packages unmapped; buffer 1d.
Phase | Start | End | On critical path
Mobilisation | 2026-07-07 | 2026-07-18 | YES
Survey & Make-Safe | 2026-07-14 | 2026-07-23 | YES
Demolition & Dismantling | 2026-07-17 | 2026-08-03 | YES
Debris Removal | 2026-07-24 | 2026-07-29 | YES
Site Clearance & Handover | 2026-07-31 | 2026-08-08 | YES
Milestone | 2026-08-05 | 2026-11-03 | YES
Civil Works | 2026-08-06 | 2026-08-24 | YES
Services - Phase I | 2026-08-21 | 2026-09-17 | YES
Ceiling Works | 2026-08-25 | 2026-09-07 | YES
Services - Phase II | 2026-09-17 | 2026-10-16 | YES
IT, AV & Signage | 2026-09-24 | 2026-10-04 | YES
Testing & Handover | 2026-09-26 | 2026-11-03 | YES
Finishes | 2026-08-21 | 2026-10-19 | YES
Joinery | 2026-09-25 | 2026-10-12 | YES
Furniture | 2026-09-27 | 2026-10-15 | —
Toilet Works | 2026-08-27 | 2026-09-17 | —

## Slide 3
Critical path — 30 activities, zero float (1/3)
# | Activity | Trade | Dur | Start | Finish
1.1 | Site mobilisation & access setup | general | 3d | 2026-07-07 | 2026-07-09
2.1 | Existing condition / dilapidation survey | civil | 2d | 2026-07-14 | 2026-07-15
2.3 | Hazardous material check & clearance | civil | 2d | 2026-07-18 | 2026-07-19
2.4 | Disconnection & isolation of existing services | civil | 3d | 2026-07-21 | 2026-07-23
3.1 | Dismantling of false ceiling & services below | civil | 5d | 2026-07-17 | 2026-07-21
3.2 | Dismantling of partitions, glazing & doors | civil | 5d | 2026-07-23 | 2026-07-27
3.6 | Civil breaking / hard demolition | civil | 4d | 2026-07-26 | 2026-07-29
4.1 | Debris segregation & stacking | civil | 6d | 2026-07-24 | 2026-07-29
4.2 | Debris removal & disposal | civil | 2d | 2026-07-28 | 2026-07-29
5.1 | PCC & self-levelling screed preparation | general | 4d | 2026-07-31 | 2026-08-03
5.2 | Site deep cleaning & dust clearance | cleaning | 4d | 2026-08-05 | 2026-08-08
5.3 | Joint survey of cleared shell | general | 1d | 2026-08-05 | 2026-08-05
5.4 | Cleared shell handover - Phase 1 completion | general | 0d | 2026-08-05 | 2026-08-05
6.1 | Setting out & marking as per layout | civil | 3d | 2026-08-06 | 2026-08-08

## Slide 4
Critical path — 30 activities, zero float (2/3)
# | Activity | Trade | Dur | Start | Finish
6.3 | Gypsum partition framing & ply backing | civil | 12d | 2026-08-08 | 2026-08-19
7.1 | HVAC works - Phase I (ducting & piping) | hvac | 28d | 2026-08-21 | 2026-09-17
7.2 | Electrical works - Phase I (conduiting & cabling) | electrical | 20d | 2026-08-21 | 2026-09-09
7.5 | Passive networking - Phase I (cable laying) | lv | 12d | 2026-09-05 | 2026-09-16
7.7 | Services Phase-I inspection & sign-off | general | 2d | 2026-09-10 | 2026-09-11
8.1 | Gypsum board Partition & ceiling - framing | ceiling | 8d | 2026-08-25 | 2026-09-01
8.2 | Gypsum board ceiling - boarding & services integration | ceiling | 9d | 2026-08-29 | 2026-09-06
8.3 | Ceiling close-out inspection | ceiling | 2d | 2026-09-06 | 2026-09-07
9.2 | Flooring works - tile, marble, wooden & carpet | flooring | 25d | 2026-09-25 | 2026-10-19
10.1 | Reception, display & water-body joinery | carpentry | 18d | 2026-09-25 | 2026-10-12
12.1 | AV system installation | lv | 11d | 2026-09-24 | 2026-10-04
14.4 | AV & IT integration testing | lv | 6d | 2026-10-10 | 2026-10-15
11.1 | Electrical works - Phase II (fixtures, switches & light fixtures) | electrical | 12d | 2026-10-05 | 2026-10-16
14.2 | Electrical testing & commissioning | electrical | 5d | 2026-10-05 | 2026-10-09

## Slide 5
Critical path — 30 activities, zero float (3/3)
# | Activity | Trade | Dur | Start | Finish
14.6 | Integrated systems commissioning | general | 7d | 2026-10-10 | 2026-10-16
14.9 | Handover documentation & training | general | 4d | 2026-10-31 | 2026-11-03

## Slide 6
Full activity schedule with float (1/5)
# | Activity | Phase | Dur | Start | Finish | Float
1.1 | Site mobilisation & access setup | Mobilisation | 3d | 2026-07-07 | 2026-07-09 | 0d
1.2 | Hoarding, barricading & signages | Mobilisation | 2d | 2026-07-11 | 2026-07-12 | 108d
1.3 | HSE setup, permits & site induction | Mobilisation | 2d | 2026-07-14 | 2026-07-15 | 111d
1.4 | Temporary power, water & lighting arrangement | Mobilisation | 2d | 2026-07-17 | 2026-07-18 | 108d
2.1 | Existing condition / dilapidation survey | Survey & Make-Safe | 2d | 2026-07-14 | 2026-07-15 | 0d
2.2 | Existing services mapping & tagging | Survey & Make-Safe | 2d | 2026-07-14 | 2026-07-15 | 5d
2.3 | Hazardous material check & clearance | Survey & Make-Safe | 2d | 2026-07-18 | 2026-07-19 | 0d
2.4 | Disconnection & isolation of existing services | Survey & Make-Safe | 3d | 2026-07-21 | 2026-07-23 | 0d
3.1 | Dismantling of false ceiling & services below | Demolition & Dismantling | 5d | 2026-07-17 | 2026-07-21 | 0d
3.2 | Dismantling of partitions, glazing & doors | Demolition & Dismantling | 5d | 2026-07-23 | 2026-07-27 | 0d
3.3 | Removal of existing flooring & floor chipping | Demolition & Dismantling | 4d | 2026-07-31 | 2026-08-03 | 92d
3.4 | Dismantling of joinery, pantry & fixtures | Demolition & Dismantling | 3d | 2026-07-17 | 2026-07-19 | 107d
3.5 | Dismantling of existing services (cable, duct, pipe) | Demolition & Dismantling | 4d | 2026-07-21 | 2026-07-24 | 3d
3.6 | Civil breaking / hard demolition | Demolition & Dismantling | 4d | 2026-07-26 | 2026-07-29 | 0d
4.1 | Debris segregation & stacking | Debris Removal | 6d | 2026-07-24 | 2026-07-29 | 0d
4.2 | Debris removal & disposal | Debris Removal | 2d | 2026-07-28 | 2026-07-29 | 0d

## Slide 7
Full activity schedule with float (2/5)
# | Activity | Phase | Dur | Start | Finish | Float
5.1 | PCC & self-levelling screed preparation | Site Clearance & Handover | 4d | 2026-07-31 | 2026-08-03 | 0d
5.2 | Site deep cleaning & dust clearance | Site Clearance & Handover | 4d | 2026-08-05 | 2026-08-08 | 0d
5.3 | Joint survey of cleared shell | Site Clearance & Handover | 1d | 2026-08-05 | 2026-08-05 | 0d
5.4 | Cleared shell handover - Phase 1 completion | Milestone | 0d | 2026-08-05 | 2026-08-05 | 0d
6.1 | Setting out & marking as per layout | Civil Works | 3d | 2026-08-06 | 2026-08-08 | 0d
6.2 | AAC block masonry work | Civil Works | 9d | 2026-08-09 | 2026-08-17 | 14d
6.3 | Gypsum partition framing & ply backing | Civil Works | 12d | 2026-08-08 | 2026-08-19 | 0d
6.4 | Self-levelling screed flooring | Civil Works | 8d | 2026-08-13 | 2026-08-20 | 75d
6.5 | Waterproofing - wet areas | Civil Works | 4d | 2026-08-21 | 2026-08-24 | 14d
7.1 | HVAC works - Phase I (ducting & piping) | Services - Phase I | 28d | 2026-08-21 | 2026-09-17 | 0d
7.2 | Electrical works - Phase I (conduiting & cabling) | Services - Phase I | 20d | 2026-08-21 | 2026-09-09 | 0d
7.3 | FLSS works - Phase I (sprinkler piping & rough-in) | Services - Phase I | 14d | 2026-08-21 | 2026-09-03 | 6d
7.4 | PHE works - Phase I (drainage & water lines) | Services - Phase I | 6d | 2026-08-21 | 2026-08-26 | 14d
7.5 | Passive networking - Phase I (cable laying) | Services - Phase I | 12d | 2026-09-05 | 2026-09-16 | 0d
7.7 | Services Phase-I inspection & sign-off | Services - Phase I | 2d | 2026-09-10 | 2026-09-11 | 0d
8.1 | Gypsum board Partition & ceiling - framing | Ceiling Works | 8d | 2026-08-25 | 2026-09-01 | 0d

## Slide 8
Full activity schedule with float (3/5)
# | Activity | Phase | Dur | Start | Finish | Float
8.2 | Gypsum board ceiling - boarding & services integration | Ceiling Works | 9d | 2026-08-29 | 2026-09-06 | 0d
8.3 | Ceiling close-out inspection | Ceiling Works | 2d | 2026-09-06 | 2026-09-07 | 0d
11.2 | HVAC works - Phase II (indoor units & diffusers) | Services - Phase II | 8d | 2026-09-18 | 2026-09-25 | 8d
11.5 | Passive networking - Phase II (termination & racks) | Services - Phase II | 8d | 2026-09-17 | 2026-09-24 | 10d
12.3 | Active networking & IT commissioning | IT, AV & Signage | 6d | 2026-09-24 | 2026-09-29 | 10d
14.1 | HVAC testing & balancing | Testing & Handover | 6d | 2026-09-26 | 2026-10-01 | 8d
9.1 | Gypsum plaster & POP punning | Finishes | 8d | 2026-08-21 | 2026-08-28 | 32d
9.2 | Flooring works - tile, marble, wooden & carpet | Finishes | 25d | 2026-09-25 | 2026-10-19 | 0d
10.1 | Reception, display & water-body joinery | Joinery | 18d | 2026-09-25 | 2026-10-12 | 0d
10.2 | Cafeteria & pantry joinery | Joinery | 12d | 2026-09-25 | 2026-10-06 | 4d
11.3 | FLSS works - Phase II (heads, detectors & PA system) | Services - Phase II | 8d | 2026-09-25 | 2026-10-02 | 7d
11.4 | PHE works - Phase II (sanitaryware & fixtures) | Services - Phase II | 5d | 2026-09-18 | 2026-09-22 | 42d
12.1 | AV system installation | IT, AV & Signage | 11d | 2026-09-24 | 2026-10-04 | 0d
14.4 | AV & IT integration testing | Testing & Handover | 6d | 2026-10-10 | 2026-10-15 | 0d
9.3 | Modular glass partitions & doors installation | Finishes | 10d | 2026-09-25 | 2026-10-04 | 30d
10.3 | Doors & ironmongery installation | Joinery | 6d | 2026-09-25 | 2026-09-30 | 34d

## Slide 9
Full activity schedule with float (4/5)
# | Activity | Phase | Dur | Start | Finish | Float
12.5 | Blinds installation | IT, AV & Signage | 5d | 2026-09-29 | 2026-10-03 | 31d
9.4 | Painting works - primer & first coat | Finishes | 8d | 2026-09-08 | 2026-09-15 | 22d
11.1 | Electrical works - Phase II (fixtures, switches & light fixtures) | Services - Phase II | 12d | 2026-10-05 | 2026-10-16 | 0d
12.2 | Access control & CCTV installation | IT, AV & Signage | 6d | 2026-09-24 | 2026-09-29 | 7d
14.2 | Electrical testing & commissioning | Testing & Handover | 5d | 2026-10-05 | 2026-10-09 | 0d
14.3 | Fire & life-safety system testing | Testing & Handover | 4d | 2026-09-29 | 2026-10-02 | 7d
14.6 | Integrated systems commissioning | Testing & Handover | 7d | 2026-10-10 | 2026-10-16 | 0d
14.9 | Handover documentation & training | Testing & Handover | 4d | 2026-10-31 | 2026-11-03 | 0d
9.5 | Graphics & films application | Finishes | 6d | 2026-10-07 | 2026-10-12 | 22d
10.4 | Planters installation | Joinery | 4d | 2026-09-27 | 2026-09-30 | 34d
12.4 | Signage & wayfinding installation | IT, AV & Signage | 5d | 2026-09-27 | 2026-10-01 | 33d
9.6 | Painting works - final coat | Finishes | 5d | 2026-09-24 | 2026-09-28 | 20d
13.1 | Modular furniture installation | Furniture | 8d | 2026-09-27 | 2026-10-04 | 17d
13.2 | Loose furniture & chairs installation | Furniture | 6d | 2026-10-10 | 2026-10-15 | 4d
TW.1 | Toilet works (cubicles, cladding, ceiling & sanitaryware) | Toilet Works | 22d | 2026-08-27 | 2026-09-17 | 33d
14.7 | Snagging & de-snagging | Testing & Handover | 11d | 2026-10-17 | 2026-10-27 | 4d

## Slide 10
Full activity schedule with float (5/5)
# | Activity | Phase | Dur | Start | Finish | Float
14.8 | Final cleaning | Testing & Handover | 3d | 2026-10-28 | 2026-10-30 | 4d
14.10 | Project handover - Phase 2 completion | Milestone | 0d | 2026-11-03 | 2026-11-03 | 1d

## Slide 11
Design tracker — GFC / MEP / Sampling (1/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
GFC | GFC | Base Build Layout | Very Critical | 2026-07-08 | Delayed | 2026-07-13 | Delayed
GFC | GFC | Furniture Layout | Very Critical | 2026-07-21 | Delayed | 2026-07-28 | WIP
GFC | GFC | Furniture Dimensions Layout | High | 2026-07-19 | Delayed | 2026-07-24 | Delayed
GFC | GFC | Partition Layout | Very Critical | 2026-07-19 | Delayed | 2026-07-24 | Delayed
GFC | GFC | Flooring Layout | High | 2026-08-07 | WIP | 2026-08-12 | WIP
GFC | GFC | Floor Marking Layout | Medium | 2026-08-08 | WIP | 2026-08-12 | WIP
GFC | GFC | Raised Flooring Layout | High | 2026-08-07 | WIP | 2026-08-12 | WIP
GFC | GFC | Door Schedule Layout | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started
GFC | GFC | Wall Finishes Layout | High | 2026-09-02 | Not Started | 2026-09-07 | Not Started
GFC | GFC | Modular Layout | Very Critical | 2026-07-21 | Delayed | 2026-07-28 | WIP
GFC | GFC | RCP Layout | Very Critical | 2026-08-17 | WIP | 2026-08-24 | Not Started
GFC | GFC | Lighting Layout (with dimensions) | Very Critical | 2026-08-13 | WIP | 2026-08-20 | Not Started
GFC | GENERAL | Wallpaper & Graphics | Low | 2026-08-15 | WIP | 2026-08-20 | Not Started
GFC | GENERAL | Fire Evacuation Plan | Medium | 2026-08-15 | WIP | 2026-08-20 | Not Started
GFC | 3D | 3D Views — Detailed & Client Approval | Very Critical | 2026-07-27 | Delayed | 2026-08-06 | WIP

## Slide 12
Design tracker — GFC / MEP / Sampling (2/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
MEP | MEP | Electrical DBR | Very Critical | 2026-08-15 | WIP | 2026-08-20 | Not Started
MEP | MEP | Electrical SLD Layout | Very Critical | 2026-08-13 | WIP | 2026-08-20 | Not Started
MEP | MEP | Electrical Load Calculation | Very Critical | 2026-08-13 | WIP | 2026-08-20 | Not Started
MEP | MEP | Power, Data & Switch Board Layout | Very Critical | 2026-08-13 | WIP | 2026-08-20 | Not Started
MEP | MEP | Raceway Layout | Very Critical | 2026-08-15 | WIP | 2026-08-20 | Not Started
MEP | MEP | Cable Tray Layout | High | 2026-08-15 | WIP | 2026-08-20 | Not Started
MEP | MEP | Lighting Looping Layout | High | 2026-08-15 | WIP | 2026-08-20 | Not Started
MEP | MEP | Panel & DB Position Layout | High | 2026-08-15 | WIP | 2026-08-20 | Not Started
MEP | MEP | UPS Calculation & Specification | High | 2026-08-13 | WIP | 2026-08-20 | Not Started
MEP | MEP | HVAC DBR | Very Critical | 2026-08-15 | WIP | 2026-08-20 | Not Started
MEP | MEP | HVAC Heat Load | Very Critical | 2026-08-13 | WIP | 2026-08-20 | Not Started
MEP | MEP | HVAC Layout | Very Critical | 2026-08-13 | WIP | 2026-08-20 | Not Started
MEP | MEP | PHE DBR & Plumbing Layout | High | 2026-08-15 | WIP | 2026-08-20 | Not Started
MEP | MEP | Fire Sprinkler Layout | Very Critical | 2026-08-10 | WIP | 2026-08-20 | Not Started
MEP | MEP | FA / PA System Layout | High | 2026-08-28 | Not Started | 2026-09-04 | Not Started

## Slide 13
Design tracker — GFC / MEP / Sampling (3/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
MEP | MEP | ACS / CCTV / WiFi Layout | High | 2026-08-28 | Not Started | 2026-09-04 | Not Started
MEP | MEP | LV DBR | High | 2026-08-30 | Not Started | 2026-09-04 | Not Started
SAMPLING | Finishes | Floor and Dado Tiles — Reception & Lounge | High | 2026-08-07 | WIP | 2026-08-12 | WIP
SAMPLING | Finishes | Floor and Dado Tiles — Workstations | High | 2026-08-07 | WIP | 2026-08-12 | WIP
SAMPLING | Finishes | Floor and Dado Tiles — Cabins & Meeting Rooms | High | 2026-08-07 | WIP | 2026-08-12 | WIP
SAMPLING | Finishes | Floor and Dado Tiles — Boardroom | High | 2026-08-07 | WIP | 2026-08-12 | WIP
SAMPLING | Finishes | Floor and Dado Tiles — Cafeteria & Pantry | High | 2026-08-07 | WIP | 2026-08-12 | WIP
SAMPLING | Finishes | Floor and Dado Tiles — Toilets | High | 2026-08-07 | WIP | 2026-08-12 | WIP
SAMPLING | Finishes | Floor and Dado Tiles — Support & Server | High | 2026-08-07 | WIP | 2026-08-12 | WIP
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Reception & Lounge | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Workstations | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Cabins & Meeting Rooms | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Boardroom | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Cafeteria & Pantry | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Toilets | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started

## Slide 14
Design tracker — GFC / MEP / Sampling (4/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
SAMPLING | Finishes | Carpentry Laminates & Veneer Shades — Support & Server | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started
SAMPLING | Finishes | Paint Shades — Reception & Lounge | Medium | 2026-09-02 | Not Started | 2026-09-07 | Not Started
SAMPLING | Finishes | Paint Shades — Workstations | Medium | 2026-09-02 | Not Started | 2026-09-07 | Not Started
SAMPLING | Finishes | Paint Shades — Cabins & Meeting Rooms | Medium | 2026-09-02 | Not Started | 2026-09-07 | Not Started
SAMPLING | Finishes | Paint Shades — Boardroom | Medium | 2026-09-02 | Not Started | 2026-09-07 | Not Started
SAMPLING | Finishes | Paint Shades — Cafeteria & Pantry | Medium | 2026-09-02 | Not Started | 2026-09-07 | Not Started
SAMPLING | Finishes | Paint Shades — Toilets | Medium | 2026-09-02 | Not Started | 2026-09-07 | Not Started
SAMPLING | Finishes | Paint Shades — Support & Server | Medium | 2026-09-02 | Not Started | 2026-09-07 | Not Started
SAMPLING | Finishes | Carpet / SPC Flooring — Reception & Lounge | High | 2026-08-05 | WIP | 2026-08-12 | WIP
SAMPLING | Finishes | Carpet / SPC Flooring — Workstations | High | 2026-08-05 | WIP | 2026-08-12 | WIP
SAMPLING | Finishes | Carpet / SPC Flooring — Cabins & Meeting Rooms | High | 2026-08-05 | WIP | 2026-08-12 | WIP
SAMPLING | Finishes | Carpet / SPC Flooring — Boardroom | High | 2026-08-05 | WIP | 2026-08-12 | WIP
SAMPLING | Finishes | Carpet / SPC Flooring — Cafeteria & Pantry | High | 2026-08-05 | WIP | 2026-08-12 | WIP
SAMPLING | Finishes | Carpet / SPC Flooring — Toilets | High | 2026-08-05 | WIP | 2026-08-12 | WIP
SAMPLING | Finishes | Carpet / SPC Flooring — Support & Server | High | 2026-08-05 | WIP | 2026-08-12 | WIP

## Slide 15
Design tracker — GFC / MEP / Sampling (5/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
SAMPLING | Partitions | Demountable Glass Partition | Very Critical | 2026-09-17 | Not Started | 2026-09-24 | Not Started
SAMPLING | Partitions | Backpainted Glass | Medium | 2026-09-19 | Not Started | 2026-09-24 | Not Started
SAMPLING | Ceiling | Grid & Stretch Ceiling — Reception & Lounge | High | 2026-08-17 | WIP | 2026-08-24 | Not Started
SAMPLING | Ceiling | Grid & Stretch Ceiling — Workstations | High | 2026-08-17 | WIP | 2026-08-24 | Not Started
SAMPLING | Ceiling | Grid & Stretch Ceiling — Cabins & Meeting Rooms | High | 2026-08-17 | WIP | 2026-08-24 | Not Started
SAMPLING | Ceiling | Grid & Stretch Ceiling — Boardroom | High | 2026-08-17 | WIP | 2026-08-24 | Not Started
SAMPLING | Ceiling | Grid & Stretch Ceiling — Cafeteria & Pantry | High | 2026-08-17 | WIP | 2026-08-24 | Not Started
SAMPLING | Ceiling | Grid & Stretch Ceiling — Toilets | High | 2026-08-17 | WIP | 2026-08-24 | Not Started
SAMPLING | Ceiling | Grid & Stretch Ceiling — Support & Server | High | 2026-08-17 | WIP | 2026-08-24 | Not Started
SAMPLING | Ceiling | Acoustics / Fluted Panel — Reception & Lounge | Medium | 2026-08-19 | Not Started | 2026-08-24 | Not Started
SAMPLING | Ceiling | Acoustics / Fluted Panel — Workstations | Medium | 2026-08-19 | Not Started | 2026-08-24 | Not Started
SAMPLING | Ceiling | Acoustics / Fluted Panel — Cabins & Meeting Rooms | Medium | 2026-08-19 | Not Started | 2026-08-24 | Not Started
SAMPLING | Ceiling | Acoustics / Fluted Panel — Boardroom | Medium | 2026-08-19 | Not Started | 2026-08-24 | Not Started
SAMPLING | Ceiling | Acoustics / Fluted Panel — Cafeteria & Pantry | Medium | 2026-08-19 | Not Started | 2026-08-24 | Not Started
SAMPLING | Ceiling | Acoustics / Fluted Panel — Toilets | Medium | 2026-08-19 | Not Started | 2026-08-24 | Not Started

## Slide 16
Design tracker — GFC / MEP / Sampling (6/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
SAMPLING | Ceiling | Acoustics / Fluted Panel — Support & Server | Medium | 2026-08-19 | Not Started | 2026-08-24 | Not Started
SAMPLING | MEP | Switch Sockets | Medium | 2026-08-15 | WIP | 2026-08-20 | Not Started
SAMPLING | MEP | Decorative Lights | High | 2026-08-13 | WIP | 2026-08-20 | Not Started
SAMPLING | MEP | Sanitary Fixtures | Medium | 2026-08-15 | WIP | 2026-08-20 | Not Started
SAMPLING | Furniture | Chairs & Loose Furniture | High | 2026-07-19 | Delayed | 2026-07-26 | Delayed
SAMPLING | Finishes | Blinds | Medium | 2026-08-15 | WIP | 2026-08-20 | Not Started
SAMPLING | Finishes | Skirting & T Profile | Low | 2026-08-16 | WIP | 2026-08-20 | Not Started
GFC | TD | TD — Interior Works | Very Critical | 2026-07-19 | Delayed | 2026-07-24 | Delayed
GFC | TD | TD — Modular Glass Partitions & Doors | Very Critical | 2026-07-19 | Delayed | 2026-07-24 | Delayed
GFC | TD | TD — Modular Furniture | Very Critical | 2026-07-19 | Delayed | 2026-07-24 | Delayed
GFC | TD | TD — Loose Furniture & Chairs | Very Critical | 2026-07-19 | Delayed | 2026-07-24 | Delayed
GFC | Elevations | Elevation — Reception & Lounge | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started
GFC | Elevations | Elevation — Workstations | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started
GFC | Elevations | Elevation — Cabins & Meeting Rooms | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started
GFC | Elevations | Elevation — Boardroom | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started

## Slide 17
Design tracker — GFC / MEP / Sampling (7/7)
Category | Sub | Drawing | Crit | Ready by | Status (INT) | Approval by | Status (client)
GFC | Elevations | Elevation — Cafeteria & Pantry | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started
GFC | Elevations | Elevation — Toilets | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started
GFC | Elevations | Elevation — Support & Server | High | 2026-09-19 | Not Started | 2026-09-24 | Not Started

## Slide 18
Procurement — order-by and delivery required (1/2)
Category | Sub | Criticality | Order by | Delivery required | Order status | Gated by
Civil Works | Civil consumables | Low | 2026-07-05 | 2026-07-12 | Open | Base Build Layout (client approval 2026-07-13)
Interior Works | Interior boards/ply (Gyproc/ply norms) | Low | 2026-07-25 | 2026-08-06 | Open | —
Modular Glass Partitions & Doors | Glass partitions (partition glass norm) | Very Critical | 2026-08-09 | 2026-09-23 | Open | Demountable Glass Partition (client approval 2026-09-24)
Signages | Signages | Medium | 2026-09-04 | 2026-09-25 | Open | —
Graphics & Films | Graphics & films (frosting norm) | Very Critical | 2026-08-16 | 2026-10-05 | Open | —
Blinds | Blinds | High | 2026-08-28 | 2026-09-27 | Open | —
Planters | Planters | Medium | 2026-09-04 | 2026-09-25 | Open | —
Toilet Works | default | Medium | 2026-08-04 | 2026-08-25 | Open | —
Carpet Flooring | Carpet flooring | High | 2026-07-02 | 2026-08-11 | Open | Flooring Layout (client approval 2026-08-12)
Modular Furniture | Modular furniture | Very Critical | 2026-08-11 | 2026-09-25 | Open | —
Loose Furniture & Chairs | Loose furniture & chairs | Very Critical | 2026-08-24 | 2026-10-08 | Open | —
Electrical Works | Electrical switchgear/cabling | High | 2026-07-20 | 2026-08-19 | Open | Lighting Layout (with dimensions) (client approval 2026-08-20)
Light Fixtures | Light fixtures | High | 2026-08-29 | 2026-10-03 | Open | —
HVAC | default | Medium | 2026-07-29 | 2026-08-19 | Open | HVAC DBR (client approval 2026-08-20)

## Slide 19
Procurement — order-by and delivery required (2/2)
Category | Sub | Criticality | Order by | Delivery required | Order status | Gated by
Passive Networking | default | Medium | 2026-08-13 | 2026-09-03 | Open | FA / PA System Layout (client approval 2026-09-04)
Plumbing Works | default | Medium | 2026-07-29 | 2026-08-19 | Open | PHE DBR & Plumbing Layout (client approval 2026-08-20)
FLSS Works | default | Medium | 2026-07-29 | 2026-08-19 | Open | Fire Sprinkler Layout (client approval 2026-08-20)
Dishwash Area | default | Medium | 2026-07-29 | 2026-08-19 | Open | —
Kitchen Equipments & Others | default | Medium | — | — | Open | —

## Slide 20
Manpower — levelled contractor gangs
Trade | From | To | Days | Man-days | Core gang | Peak
carpentry | 2026-09-25 | 2026-10-15 | 21 | 432 | 16 | 16
ceiling | 2026-08-25 | 2026-09-07 | 14 | 152 | 11 | 14
civil | 2026-07-14 | 2026-08-24 | 42 | 560 | 14 | 16
cleaning | 2026-08-05 | 2026-10-30 | 87 | 70 | 6 | 6
electrical | 2026-08-21 | 2026-10-16 | 57 | 370 | 7 | 9
finishing | 2026-08-21 | 2026-10-12 | 53 | 114 | 4 | 4
flooring | 2026-08-13 | 2026-10-19 | 68 | 198 | 4 | 4
general | 2026-07-07 | 2026-11-03 | 120 | 152 | 3 | 4
glass | 2026-09-25 | 2026-10-04 | 10 | 50 | 5 | 5
hvac | 2026-08-21 | 2026-10-01 | 42 | 336 | 8 | 8
lv | 2026-09-05 | 2026-10-15 | 41 | 324 | 8 | 10
painting | 2026-09-08 | 2026-09-28 | 21 | 104 | 5 | 5
plumbing | 2026-08-21 | 2026-09-22 | 33 | 132 | 4 | 4
sprinkler | 2026-08-21 | 2026-10-02 | 43 | 130 | 4 | 5

## Slide 21
RA billing milestones — readiness against site progress
MILESTONES
6
CLAUSES TRACKED
59
CONTRACT VALUE
INR 5,70,04,000
RA | Due | % | Amount | Clauses | Status
ADV | 2026-07-07 | 30% | INR 1,71,01,200 | 1 | Delayed
RA1 | 2026-08-21 | 20% | INR 1,14,00,800 | 18 | Not Started
RA2 | 2026-09-15 | 15% | INR 85,50,600 | 12 | Not Started
RA3 | 2026-09-30 | 15% | INR 85,50,600 | 14 | Not Started
RA4 | 2026-10-25 | 15% | INR 85,50,600 | 12 | Not Started
RA5 | 2026-11-04 | 5% | INR 28,50,200 | 2 | Not Started

## Slide 22
RA milestone clauses — what must be true before billing (1/4)
RA | Kind | Clause | Planned | Status
ADV | execution | Project mobilisation | 2026-07-09 | Delayed
RA1 | execution | Demolition | 2026-07-29 | WIP
RA1 | execution | Partition line marking | 2026-08-08 | WIP
RA1 | execution | Frameworks | 2026-08-21 | Not Started
RA1 | execution | Single-side skinning | 2026-08-21 | Not Started
RA1 | execution | Civil wall | 2026-07-29 | WIP
RA1 | execution | Plastering | 2026-08-21 | Not Started
RA1 | execution | Plumbing | 2026-08-21 | Not Started
RA1 | execution | Ceiling | 2026-07-21 | Delayed
RA1 | execution | Wall electrical conduiting | 2026-09-09 | Not Started
RA1 | execution | Floor raceway laying | 2026-08-03 | WIP
RA1 | material | Gypsum frames | 2026-08-21 | Not Started
RA1 | material | Gypsum sheets | 2026-08-21 | Not Started
RA1 | material | Electrical conduits | 2026-08-21 | Not Started
RA1 | material | Raceway | 2026-08-21 | Not Started
RA1 | material | Siporex blocks | 2026-08-21 | Not Started

## Slide 23
RA milestone clauses — what must be true before billing (2/4)
RA | Kind | Clause | Planned | Status
RA1 | order | HVAC | 2026-08-21 | Not Started
RA1 | order | Fire alarm system | 2026-08-21 | Not Started
RA1 | order | Carpentry | 2026-08-21 | Not Started
RA2 | execution | Closing of partitions from double side | 2026-07-27 | Delayed
RA2 | execution | Electrical wiring | 2026-09-09 | Not Started
RA2 | execution | Fire sprinkler piping | 2026-09-03 | Not Started
RA2 | execution | FAS wiring | 2026-09-15 | Not Started
RA2 | material | Duct material | 2026-09-15 | Not Started
RA2 | material | Wires/cables | 2026-09-15 | Not Started
RA2 | material | Ply for carpentry items | 2026-09-15 | Not Started
RA2 | material | Vitrified tiles | 2026-09-15 | Not Started
RA2 | order | Modular furniture | 2026-09-15 | Not Started
RA2 | order | Chairs | 2026-09-15 | Not Started
RA2 | order | Carpets | 2026-09-15 | Not Started
RA2 | order | Glass | 2026-09-15 | Not Started
RA3 | execution | Painting base-coat preparation | 2026-09-15 | Not Started

## Slide 24
RA milestone clauses — what must be true before billing (3/4)
RA | Kind | Clause | Planned | Status
RA3 | execution | Glass channel | 2026-10-04 | Not Started
RA3 | execution | HVAC duct installation | 2026-07-24 | Delayed
RA3 | execution | False ceiling framing | 2026-07-21 | Delayed
RA3 | material | Carpets | 2026-09-30 | Not Started
RA3 | material | Sanitary fittings | 2026-09-30 | Not Started
RA3 | material | Fixtures | 2026-09-30 | Not Started
RA3 | material | Doors | 2026-09-30 | Not Started
RA3 | material | DB/MCB | 2026-09-30 | Not Started
RA3 | order | Decorative elements | 2026-09-30 | Not Started
RA3 | order | Glass films | 2026-09-30 | Not Started
RA3 | order | Wallpapers | 2026-09-30 | Not Started
RA3 | order | Canvas frames | 2026-09-30 | Not Started
RA3 | order | Branding | 2026-09-30 | Not Started
RA4 | execution | Electrical switches/sockets | 2026-10-16 | Not Started
RA4 | execution | Sanitary fixtures | 2026-07-19 | Delayed
RA4 | execution | Carpentry structures ready | 2026-10-25 | Not Started

## Slide 25
RA milestone clauses — what must be true before billing (4/4)
RA | Kind | Clause | Planned | Status
RA4 | execution | Flush doors | 2026-07-27 | Delayed
RA4 | execution | First coat of paint | 2026-09-15 | Not Started
RA4 | execution | False ceiling | 2026-07-21 | Delayed
RA4 | execution | Before HVAC final commissioning | 2026-09-17 | Not Started
RA4 | execution | Before LV commissioning | 2026-09-29 | Not Started
RA4 | material | Modular furniture on site | 2026-10-25 | Not Started
RA4 | material | Carpet on site | 2026-10-25 | Not Started
RA4 | material | Before chair delivery | 2026-10-25 | Not Started
RA4 | order | Deep cleaning | 2026-10-25 | Not Started
RA5 | execution | Release against unconditional bank guarantee of equal amount | 2026-11-04 | Not Started
RA5 | execution | Valid for 6 months Defects Liability Period | 2026-11-04 | Not Started

## Slide 26
Resource plan
Role | Count | Basis
Project Manager | 1 | ceil(14905 sft / 40000) per norms-v1:resourceRoleNorms
Site Engineer (Civil/Interior) | 2 | ceil(14905 sft / 12000) per norms-v1:resourceRoleNorms
MEP Engineer | 1 | ceil(14905 sft / 25000) per norms-v1:resourceRoleNorms
Design Lead | 1 | ceil(14905 sft / 40000) per norms-v1:resourceRoleNorms
Procurement Owner | 1 | ceil(14905 sft / 40000) per norms-v1:resourceRoleNorms
Safety Officer | 1 | ceil(14905 sft / 30000) per norms-v1:resourceRoleNorms
QC / Snag Engineer | 1 | ceil(14905 sft / 30000) per norms-v1:resourceRoleNorms

## Slide 27
To-do list — next 21 days (1/7)
End date | Responsibility | Description | Priority | Status
2026-07-02 | Procurement | Release PO: Carpet Flooring | HIGH | Delayed
2026-07-04 | Project head | Project resource allocation confirmed (PM, site engineer, MEP, design, procurement) | HIGH | Delayed
2026-07-05 | Project head | Project tool creation — tracker, folder structure and access | MEDIUM | Delayed
2026-07-05 | Procurement | Release PO: Civil Works | MEDIUM | Delayed
2026-07-06 | Project head | Client WhatsApp group creation with the agreed participants | MEDIUM | Delayed
2026-07-07 | Project head | Wispr onboarding for the project team | MEDIUM | Delayed
2026-07-07 | Project head | Welcome email issued to the client with team and escalation matrix | MEDIUM | Delayed
2026-07-08 | Site engineer | Site verification against the GFC layout | HIGH | Delayed
2026-07-08 | Site engineer | Building permissions, gate pass and work permits obtained | HIGH | Delayed
2026-07-08 | Site engineer | Day-0 site photographs and dilapidation record filed | MEDIUM | Delayed
2026-07-08 | Design lead | Issue for approval: Base Build Layout | HIGH | Delayed
2026-07-09 | Site engineer | Site marking completed and signed off | HIGH | Delayed
2026-07-09 | Site engineer | Labour onboarding, ID cards and safety induction | HIGH | Delayed
2026-07-10 | Project head | Kick-off meeting with the client and consultants | HIGH | Delayed
2026-07-11 | Site engineer | Temporary power, water and site lighting arranged | HIGH | Delayed

## Slide 28
To-do list — next 21 days (2/7)
End date | Responsibility | Description | Priority | Status
2026-07-19 | Design lead | Issue for approval: Furniture Dimensions Layout | HIGH | Delayed
2026-07-19 | Design lead | Issue for approval: Partition Layout | HIGH | Delayed
2026-07-19 | Design lead | Issue for approval: Chairs & Loose Furniture | HIGH | Delayed
2026-07-19 | Design lead | Issue for approval: TD — Interior Works | HIGH | Delayed
2026-07-19 | Design lead | Issue for approval: TD — Modular Glass Partitions & Doors | HIGH | Delayed
2026-07-19 | Design lead | Issue for approval: TD — Modular Furniture | HIGH | Delayed
2026-07-19 | Design lead | Issue for approval: TD — Loose Furniture & Chairs | HIGH | Delayed
2026-07-20 | Procurement | Release PO: Electrical Works | HIGH | Delayed
2026-07-21 | Design lead | Issue for approval: Furniture Layout | HIGH | Delayed
2026-07-21 | Design lead | Issue for approval: Modular Layout | HIGH | Delayed
2026-07-25 | Procurement | Release PO: Interior Works | MEDIUM | Delayed
2026-07-27 | Design lead | Issue for approval: 3D Views — Detailed & Client Approval | HIGH | Delayed
2026-07-29 | civil lead | In progress: Civil breaking / hard demolition | HIGH | WIP
2026-07-29 | civil lead | In progress: Debris segregation & stacking | HIGH | WIP
2026-07-29 | civil lead | Start: Debris removal & disposal | HIGH | Not Started

## Slide 29
To-do list — next 21 days (3/7)
End date | Responsibility | Description | Priority | Status
2026-07-29 | Procurement | Release PO: HVAC | MEDIUM | Not Started
2026-07-29 | Procurement | Release PO: Plumbing Works | MEDIUM | Not Started
2026-07-29 | Procurement | Release PO: FLSS Works | MEDIUM | Not Started
2026-07-29 | Procurement | Release PO: Dishwash Area | MEDIUM | Not Started
2026-08-03 | civil lead | Start: Removal of existing flooring & floor chipping | MEDIUM | Not Started
2026-08-03 | general lead | Start: PCC & self-levelling screed preparation | HIGH | Not Started
2026-08-04 | Procurement | Release PO: Toilet Works | MEDIUM | Not Started
2026-08-05 | general lead | Start: Joint survey of cleared shell | HIGH | Not Started
2026-08-05 | general lead | Start: Cleared shell handover - Phase 1 completion | HIGH | Not Started
2026-08-05 | Design lead | Issue for approval: Carpet / SPC Flooring — Reception & Lounge | HIGH | WIP
2026-08-05 | Design lead | Issue for approval: Carpet / SPC Flooring — Workstations | HIGH | WIP
2026-08-05 | Design lead | Issue for approval: Carpet / SPC Flooring — Cabins & Meeting Rooms | HIGH | WIP
2026-08-05 | Design lead | Issue for approval: Carpet / SPC Flooring — Boardroom | HIGH | WIP
2026-08-05 | Design lead | Issue for approval: Carpet / SPC Flooring — Cafeteria & Pantry | HIGH | WIP
2026-08-05 | Design lead | Issue for approval: Carpet / SPC Flooring — Toilets | HIGH | WIP

## Slide 30
To-do list — next 21 days (4/7)
End date | Responsibility | Description | Priority | Status
2026-08-05 | Design lead | Issue for approval: Carpet / SPC Flooring — Support & Server | HIGH | WIP
2026-08-07 | Design lead | Issue for approval: Flooring Layout | HIGH | WIP
2026-08-07 | Design lead | Issue for approval: Raised Flooring Layout | HIGH | WIP
2026-08-07 | Design lead | Issue for approval: Floor and Dado Tiles — Reception & Lounge | HIGH | WIP
2026-08-07 | Design lead | Issue for approval: Floor and Dado Tiles — Workstations | HIGH | WIP
2026-08-07 | Design lead | Issue for approval: Floor and Dado Tiles — Cabins & Meeting Rooms | HIGH | WIP
2026-08-07 | Design lead | Issue for approval: Floor and Dado Tiles — Boardroom | HIGH | WIP
2026-08-07 | Design lead | Issue for approval: Floor and Dado Tiles — Cafeteria & Pantry | HIGH | WIP
2026-08-07 | Design lead | Issue for approval: Floor and Dado Tiles — Toilets | HIGH | WIP
2026-08-07 | Design lead | Issue for approval: Floor and Dado Tiles — Support & Server | HIGH | WIP
2026-08-08 | cleaning lead | Start: Site deep cleaning & dust clearance | HIGH | Not Started
2026-08-08 | civil lead | Start: Setting out & marking as per layout | HIGH | Not Started
2026-08-08 | Design lead | Issue for approval: Floor Marking Layout | MEDIUM | WIP
2026-08-09 | Procurement | Release PO: Modular Glass Partitions & Doors | HIGH | Not Started
2026-08-10 | MEP design lead | Issue for approval: Fire Sprinkler Layout | HIGH | WIP

## Slide 31
To-do list — next 21 days (5/7)
End date | Responsibility | Description | Priority | Status
2026-08-11 | Procurement | Release PO: Modular Furniture | HIGH | Not Started
2026-08-13 | Procurement | Release PO: Passive Networking | MEDIUM | Not Started
2026-08-13 | Design lead | Issue for approval: Lighting Layout (with dimensions) | HIGH | WIP
2026-08-13 | MEP design lead | Issue for approval: Electrical SLD Layout | HIGH | WIP
2026-08-13 | MEP design lead | Issue for approval: Electrical Load Calculation | HIGH | WIP
2026-08-13 | MEP design lead | Issue for approval: Power, Data & Switch Board Layout | HIGH | WIP
2026-08-13 | MEP design lead | Issue for approval: UPS Calculation & Specification | HIGH | WIP
2026-08-13 | MEP design lead | Issue for approval: HVAC Heat Load | HIGH | WIP
2026-08-13 | MEP design lead | Issue for approval: HVAC Layout | HIGH | WIP
2026-08-13 | Design lead | Issue for approval: Decorative Lights | HIGH | WIP
2026-08-15 | Design lead | Issue for approval: Wallpaper & Graphics | MEDIUM | WIP
2026-08-15 | Design lead | Issue for approval: Fire Evacuation Plan | MEDIUM | WIP
2026-08-15 | MEP design lead | Issue for approval: Electrical DBR | HIGH | WIP
2026-08-15 | MEP design lead | Issue for approval: Raceway Layout | HIGH | WIP
2026-08-15 | MEP design lead | Issue for approval: Cable Tray Layout | HIGH | WIP

## Slide 32
To-do list — next 21 days (6/7)
End date | Responsibility | Description | Priority | Status
2026-08-15 | MEP design lead | Issue for approval: Lighting Looping Layout | HIGH | WIP
2026-08-15 | MEP design lead | Issue for approval: Panel & DB Position Layout | HIGH | WIP
2026-08-15 | MEP design lead | Issue for approval: HVAC DBR | HIGH | WIP
2026-08-15 | MEP design lead | Issue for approval: PHE DBR & Plumbing Layout | HIGH | WIP
2026-08-15 | Design lead | Issue for approval: Switch Sockets | MEDIUM | WIP
2026-08-15 | Design lead | Issue for approval: Sanitary Fixtures | MEDIUM | WIP
2026-08-15 | Design lead | Issue for approval: Blinds | MEDIUM | WIP
2026-08-16 | Procurement | Release PO: Graphics & Films | HIGH | Not Started
2026-08-16 | Design lead | Issue for approval: Skirting & T Profile | MEDIUM | WIP
2026-08-17 | civil lead | Start: AAC block masonry work | MEDIUM | Not Started
2026-08-17 | Design lead | Issue for approval: RCP Layout | HIGH | WIP
2026-08-17 | Design lead | Issue for approval: Grid & Stretch Ceiling — Reception & Lounge | HIGH | WIP
2026-08-17 | Design lead | Issue for approval: Grid & Stretch Ceiling — Workstations | HIGH | WIP
2026-08-17 | Design lead | Issue for approval: Grid & Stretch Ceiling — Cabins & Meeting Rooms | HIGH | WIP
2026-08-17 | Design lead | Issue for approval: Grid & Stretch Ceiling — Boardroom | HIGH | WIP

## Slide 33
To-do list — next 21 days (7/7)
End date | Responsibility | Description | Priority | Status
2026-08-17 | Design lead | Issue for approval: Grid & Stretch Ceiling — Cafeteria & Pantry | HIGH | WIP
2026-08-17 | Design lead | Issue for approval: Grid & Stretch Ceiling — Toilets | HIGH | WIP
2026-08-17 | Design lead | Issue for approval: Grid & Stretch Ceiling — Support & Server | HIGH | WIP
2026-08-19 | civil lead | Start: Gypsum partition framing & ply backing | HIGH | Not Started
2026-08-20 | flooring lead | Start: Self-levelling screed flooring | MEDIUM | Not Started

## Slide 34
Client / builder open points (1/2)
Sr | Area | Description | Responsibility | Plan date | Status
1 | Kick Off | Site kick-off meeting and pooja | Client/FS | 2026-07-07 | Delayed
2 | Commercial | Project PO / signed agreement | Client | 2026-07-07 | Delayed
3 | Commercial | Project advance payment | Client | 2026-07-14 | Delayed
4 | Design | Layout approval | Client | 2026-07-04 | Delayed
5 | Design | 3D approvals | Client | 2026-07-17 | Delayed
6 | Design | Material sampling approval | Client/FS | 2026-08-03 | Pending
7 | Design | MEP drawings approval | Client/PMC | 2026-08-07 | Pending
8 | Design | Electrical / IT requirement and load confirmation | Client | 2026-08-07 | Pending
9 | Operation | Builder permissions and mobilisation clearance | FS/Builder | 2026-07-07 | Delayed
10 | Operation | Mathadi clearance | FS | 2026-07-07 | Delayed
11 | Operation | Fire NOC / CFO approval | FS/Builder | 2026-08-07 | Pending
12 | Operation | BMC / statutory approval | FS/Builder | 2026-06-30 | Delayed
13 | Operation | Temporary power and water availability | Builder | 2026-08-16 | Pending
14 | Operation | Lift availability for material movement | Builder | 2026-07-11 | Delayed
15 | Operation | Work hours clarity in building | Builder | 2026-07-11 | Delayed

## Slide 35
Client / builder open points (2/2)
Sr | Area | Description | Responsibility | Plan date | Status
16 | Operation | Heat load approval / CFM availability | Builder | 2026-08-07 | Pending
17 | Operation | Wi-Fi and access point locations | Client | 2026-08-26 | Pending
18 | Operation | Modular vendor closure for site marking | Client | 2026-07-21 | Delayed
19 | Design/Operation | Client-supplied items (IT / AV) delivery | Client | 2026-08-26 | Pending
20 | Operation | Store space and debris removal area | Builder | 2026-07-11 | Delayed

## Slide 36
Assumptions, gaps and risks (1/3)
Area | Note | Visibility
manpower | carpentry: 432 man-days across 21 working days needs 21 workers, above the 16 cap. Extend the window, split the front, or raise the cap in Settings. | internal only
manpower | Manpower curve is peaky (average 34 vs peak 72). Consider re-sequencing overlapping trades. | internal only
procurement | Package "Kitchen Equipments & Others" has no mapped site activity; order-by date not computed. | internal only
billing | Package A1: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package A2: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package A3: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package A4: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package A5: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only

## Slide 37
Assumptions, gaps and risks (2/3)
Area | Note | Visibility
billing | Package A6: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package A7: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package A8: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package B1: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package B2: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package B3: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package C1: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package C2: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only

## Slide 38
Assumptions, gaps and risks (3/3)
Area | Note | Visibility
billing | Package D1: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package E1: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package F1: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package G: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package H1: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only
billing | Package H2: BCS cost missing; margin for it assumed at the 28% norm from the BOQ_BCS margin column. | internal only